## Slide 1: Hydra - SL75 “Seductive Extravaganza“ Product Status Report at M1, 10.12.04
Daniela Culmbacher (SPM BA), Karsten Sørensen (PL T), Ansgar Tröster (SPM)
– Confidential –
Copyright © Siemens AG 2004: Copying of this document and giving it to others and the use or communication of the contents thereof, are forbidden without express authority. Offenders are liable to the payment of damages. All rights reserved in the event of the grant of a patent or the registration of a utility model or design.

## Slide 2: This document has been reviewed and agreed by the extended Hydra Core Team
__________________ __________________ __________________
SPM PLT SPM BA
__________________ __________________ __________________
Sales SCM QM
Signed, Ansgar Tröster
Signed, Poul Søndergaard
Signed, Heike Evangelista
Signed, Jens Riedel
Signed, Karsten Sørensen
Signed, Daniela Culmbacher
Due to the PSR decision as of Oct 27, 04 all extended core team members have to commit to the content of this presentation and “virtually” sign the presentation! Please send email to SPM.

## Slide 3: Quality Gate Rating Hydra 1/2 Status M1
Profitability
Project Quality
Sales Fit
Product Quality
Strategy
Fit
Time-to-Market
Sales Fit
Customer feedback shows that Design, size, customization is ok; feature level compared to UMTS phones at same price point (subsidized) might be too low
Price line at risk (currently 258€ =ASP, 305€ =launch price), 275€ launch price suggested by Sales incl. slightly higher volume (not synch’d w/ pricing office)
1'01 units; decrease of 27% (1'4 units at M0) due to feedback from countries.
Profitability
11,7% (= 30'5€, curent) vs. 20% (= 52'1€, target) --> deviation: 41,4%
BC highly price sensitive.
Opportunities to increase volume over life cycle identified and being pursued.
Rating Meeting: Dec 2, Update Dec 3 PSO support: G. Blecher
Strategy Fit
High fit as Hydra continues slider success story, only product in exclusive segment; key brand building product
An ad hoc evaluation of 6 important AD change requests by the PD SWC was positive; however, the detailed evaluation is not yet finalized.
Notes: <number>
<footer>
<header>
<date/time>

## Slide 4: Quality Gate Rating Hydra 2/2 Status M1
Profitability
Project Quality
Sales Fit
Product Quality
Strategy
Fit
Time-to-Market
Time-to-Market
22.09.2005 (current DS) vs. 09/2005 (as of M0 and Roadm. Dec 3)
High confidence to reach S3-HW by Hydra PD team, however only moderate confidence to reach TTM due to platform dependency
SW maturity (“for operator approvals”) at AS critical as scheduled only 2wks after S25.
M1 2.12.04, M2 8.7.05, AS 8.7.05, S3 26.8.05, DS 22.9.05
Project Quality
Rea.Team staffing: Gen 65 still binds resources, refreshes might further endanger situation (GPM, PM).
Primavera: Masterplan agreed and resources are secured, interlinking of detailed work packages ongoing
Product Quality-Hydra
EMC/Antenna: Radiated power not yet measured with right plastic material (risk: low radiated power due to form factor).
Latent risk due to lead free process, in case corrective actions necessary this might result in additional cost and TTM impact
Product Quality-Platform
High dependency to SW deliverables esp. by OpenWave
I3s for SGold2, Camera, Display, EGPRS modem missing, waiting for software for real network test; late availability of gimmick chip (time schedule)
Rating Meeting: Dec 2, Update Dec 3 PSO support: G. Blecher
Notes: <number>
<footer>
<header>
<date/time>

## Slide 5: Comparison Business Case - Compared to M0, the M1 Business Case indicates 40m EUR less Profit
  Lifecycle:
  As DS is now planned for September’05 the lifecycle extends to 13 months
  Units:
  Compared to M0 volume has been reduced by 400k units down to 1,010k (87% EMEA, 7% APAC and 6% LAM)
  ASP:
  A decrease in ASP of 45 Euro is being caused by a lower price line (Launch price now 305 Euro instead of 350 Euro at M0) and the diminished volume over life cycle (1,010k compared to 1,410k)
  HK:
  Actual BOM based on GS Life cycle commitment plus € 1.92 for partly planned briefcase bundling and special packaging for APAC variant and plus € 0.74 for chrome plated slider unit instead of painted
  Conversion Cost (10.64 Euro) based on production site split indicated by GO (KLF 87%, SSMC 7%, Manaus 6%)
  Licenses (5.79 Euro): Audio/Video Levies (€ 3.71) only considered for EMEA quantities
  CCQ:
  Service costs diminished due to lower RR (16.1% compared to 17.3%) and decreased service costs per return (46.35 Euro compared to 47.53 Euro)
  R&D:
  R&D budget increased by 1.5m Euro due to higher efforts for X75 platform (direct platform R&D: 6’7 Euro compared to 2’9 Euro at M0).
  Marcom:
  MarCom based on revised budget indication from S&M (€ 5.0 per Unit sold plus 7% of T/O plus € 2’5 HQ budget).
Deviation Analysis

## Slide 6: Measures, Responsibles and Due Dates
Problem/ risk Action Resp. due status
Strategy fit --
Sales fit price volume scenario review for DS pricing and life cycle Culmbacher QPM before volume plan until QPM before M2 w/ PO 8.7.05 open
Profitability further BOM reduction target - € 8,46 (not commited) negotiations, DTC Svendsen ongoing open
pursue extension of lifecycle (Q4 05) allignment w/ G85 roadmap Tröster 8.7.05 open
Platform Quality Openwave deliveries on critical path AI plan to be excecuted until Klebsch ongoing open Minos AS (approval start) Henneberger
Product Quality Feasibility of leadfree production Continue task force to secure Eickholt 31.1.05 open not finally secured leadfree soldering feasibility
antenna performance not finally measurement in production Sørensen B1 open confirmed plastic parts, corrective actions
TTM AS maturity Ensure maturity for op. approvals Sørensen 8.7.05 open
confidence level on platform transparent project management Sørensen ongoing open
Project quality Rea.Team resources ensure availability of all members Tröster ongoing open

## Slide 7: Decisions Proposals in case of yellow Q-Gate
A.) Go ahead with project
Impacts on TTM, EBIT, Volumes, Quality is calculated and available (see backup).
AIs will be executed
B.) Negative impact if stopped / delayed
Delay of M1 will impact DS, each week delay of DS will reduce gross margin by ~ € 3’9
Loss of so far cumulated EGK: € 9’8
Loss / delay of key brand building product
PSR decision: continue
PSR decision: stop

## Slide 8
Backup

## Slide 9
Positioning:
Exclusive Class, SL75
„Seductive Extravaganza “
Highlight:
The style statement captivating people with desire for extravagance and superb quality in detail
Key consumer benefits:
The slider style demonstrates extravagant taste that makes it an object of desire
The premium finishing, display & slider mechanism are expressing the extraordinary value
Key operator benefits:
Push messaging (video, text, still pictures)
Push of portal services
Outstanding sound format (encourage download of sound & ring tones)
High quality display & slider mechanism leading to customer delight
Business (PSR at M1 declaration):
Lifecycle:13 months, Volumes: 1'010 pc
Launch: 09.05/ 305 €, EOL: 10.06, ASP: 258 €
EBIT: __ %, [removed for confidentiality reasons]
Brand Contribution:
Hydra is an ingenious product which combines extraordinary yet timeless design with a superior quality making it the perfect choice for a demanding consumer.
Differentiation to Competition:
Outstanding style statement
Best in class material & finishing
High quality slider mechanism (‚Soft Slider‘)
Premium transflective display with high colour
depth
Differentiation to MP products:
To Orion: Higher price position, less feature oriented, more exclusive & refined design, ‚soft slider‘, premium transflective display
To Wolf 4: see above
Product Profile

## Slide 10
2003 | 2004 |  |  |  | 2005 | 
Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q4
€600
€400
Launch price
€550
€500
€450
Panasonic
X70
- Display 65k
CIF camera
4 MB internal mem.
No audio, no video
No IMPS, PaT
Sharp TM100
VGA camera w. night mode
No video stream.
Ausio na.
No IMPS, PaT
+ Display 240x320
+ SD slot
Nokia 7200
- VGA camera with night mode
Display 65k / 128x128
No video streaming
4MB internal mem.
No MP3 ringtónes, AAC(++)
No BT, no PaT
+ Exchangeable parts
+ FM radio
+ EDGE
Motorola
V80
- Display 65k
VGA camera w/o LED flash
No video
5MB internal mem.
No PaT
+ Display 176x220
Samsung
E800
- VGA camera
Display 65k / 128x160
No video streaming
No E-Mail, no BT
No MP3 Ringtones
No AAC(++)
No IMPS, PaT
Innostream
Inno 75
1 Mpx. Camera with night mode
Display 65k
No PaT
+ Display 208x176
+ 64MB RS MMC slot
+ Series 60
Nokia 7610
Hydra
Size 92x48x23
Display 262k / 132x176
Automatic Slider
1,3 Mpx. Camera
LED camera light
Bluetooth
>20 MB internal mem.
Music player + ringtones MP3, ACC, AAC+, AAC++
64 chords ringtones
Video play, rec., stream
IMPS, PaT
Nokia 7280
VGA Camera
Display 65k
No PaT, Email
No MP3, AAC
+ Innovative formfactor
+ Voice interface
+ FM Radio
Samsung
D500
1 Mpx. Camera
Display 65k
No PaT
No EDGE
+ Display 176x220
+ 80 MB Memory
+ Video with 4x digital zoom
Nokia 7270
VGA Camera
Display 65k
No MP3, AAC
+ Style Packs
+ FM Radio
+ 21MB memory
VGA cam. w/o LED flash
Display resol. na.
No video streaming
No MP3 Ringtones
No AAC(++)
No BT, no IMPS, no PaT
+ Mini SD slot
+ FM radio
Motorola Razr V3
VGA Camera without flash
5 MB memory
No MP3, AAC
+ Display 176x220
+ Quad
+ Anodized Alu-Body
Competition & SWOT

## Slide 11
Notes: <number>
<footer>
<header>
<date/time>

## Slide 12
Hydra
Direct R&D-Costs
Comment :
Account: E981-0377
M0 declared 07.07.2004
M1 to be declared today 8.12.04
M3 planned 28.02.2006
Efforts after M3: 0‘6 Mio. €
Platform: 25% of X75 Platform
Cost overview until M 3

## Slide 13
Display 0,07
Speaker 0,12
Housing 4,24 FPC 2,67
Tooling 4,02
Battery 0,16 Main PCB 0,40
(Minos 6-layer)
Keypad 0,95
Slider 4,94
FY 04/05