## Slide 1: Minos “Mobile Music Connector“ Product Status Report at M1, 10.12.2004
Core team Minos SPM: Hombeck, PM: Olivan, PLT: Feldhoff, Barner, BA: Teistler
– Confidential –
Copyright © Siemens AG 2004: Copying of this document and giving it to others and the use or communication of the contents thereof, are forbidden without express authority. Offenders are liable to the payment of damages. All rights reserved in the event of the grant of a patent or the registration of a utility model or design.

## Slide 2
Signatures All team members have signed Minos M1

## Slide 3: Quality Gate Rating Minos 1/2 Status M1
Profitability
Project Quality
Sales Fit
Product Quality
Strategy
Fit
Time-to-Market
Sales Fit
No indications for price risk
Pricing Office even suggests 185€ launch price; planning: 155€ =ASP, 175€ =BC launch price
3'5 units; but no commitment by consortias yet
Profitability
8,9% (= 48'€, current) vs. 7,5% (= 40'4€, target)
Moderate confidence for BC; launch date and approval schedule critical for BC (peak volume planned for 10-11/2005).
Strategy Fit
Modest fit due to changes of SW features after M0 declaration (e.g. multitasking, Real 8 codec)
An ad hoc evaluation of 6 important AD change requests by the PD SWC was positive; however, the detailed evaluation is not yet finalized.
QG
Rating Meeting: Dec 1, Update Dec 8, PSO support: G. Blecher
Notes: <number>
<footer>
<header>
<date/time>

## Slide 4: Quality Gate Rating Minos 2/2 Status M1
Profitability
Project Quality
Sales Fit
Product Quality
Strategy
Fit
Time-to-Market
Time-to-Market
09/2005 (current DS) vs. 09/2005 Roadmap Dec. 3rd (M0 target 07/2005)
Moderate confidence by PL-T to reach TTM.
Any delay in SW delivery from OpenWave will impact DS
Project Quality
Staffing of Rea Team currently insufficient: 2nd PL-T (U. Barner) agreed but not finally confirmed for Minos
Quality of masterplan satisfactory
Product Quality-Platform
High dependency to SW deliverables esp. by OpenWave
I3s for SGold2, Camera, Display, EGPRS modem missing (SW for real network test available CW3); late availability of gimmick chip (B1 prototype run adapted for CW3)
QG
Product Quality-Minos
Latent risk due to leadfree process (8-layer PCB already included in BC)
Rating Meeting: Dec 1, Update Dec 8, PSO support: G. Blecher
Notes: <number>
<footer>
<header>
<date/time>

## Slide 5: Comparison Business Case Compared to M0, the M1 Business Case indicates +14,9 m EUR Profit
  M1 LC BOM commitment 11,88 € below M0 Team commitment
  Committed savings for BOM FY04/05 vs. GS Budget BOM NES: -11,0 Euro DTC: -2,03 Euro Special effects: -1,91 Euro
  Further DTC potential of 0,96 Euro if 6 Layer PCB can be realized -> EBIT potential 3’3 Euro
  Total LC HK vs. M0 decreased by 13,00 € to 95,09€
  Return Rate increased to 12,5% based on S4 planning for 01/06
Deviation Analysis
*w/o variant adder

## Slide 6: Measures, Responsibles and Due Dates

## Slide 7: Decisions Proposals in case of yellow Q-Gate
A.) Go ahead with project
Impacts on TTM, EBIT, Volumes, Quality is calculated and available
(see backup).
AIs +Next Steps (including resp. and due date) to come back to green
As defined on separate slide (measures, responsibilities and due dates)
PSR decision: continue
PSR decision: stop

## Slide 8
Backup

## Slide 9
Product Profile Minos – the mobile music connector
Positioning / Brand: Product Segment : Emotion Class
Target Group: Unisex, age 20-45,
(low) - mid income, community centric,
mix of private and business usage
Business: Lifecycle, Volume: 09/05-09/06, 3.475 units Price , ASP, EBIT: 175€ launch, ASP
155€, 48 Mio € Ebit
Against Competition:
Above average feature set & performance for planned price point (music player, Mpix camera, full video, Bluetooth®, RS-MultiMediaCard slot, PIM functions,…)
Customized to operator demands
Consumer Highlights:
Relaxation and enjoyment on the move via a surprising multimedia feature set (music player*, Mpix camera, video,…)
Easy life organization via efficient management functions (ext. PIM, phone book presence enh.,…)
Well accepted design via valuable material finishing
Operator Benefits:
Advanced operator customization
Above average feature set & performance for planned price point
Variety of ARPU & content download generating functions
Differentiation within MP:
First EDGE-Product
Advanced UI customization
Phoenix: no EDGE, no video & audio streaming, less UI customization
Virgo: clam shell, more design oriented
  *without RS-MultiMediaCard bundled

## Slide 10
Mobile music connector

## Slide 11
1.3 mega pixel camera plus integrated camera light & full video function
EDGE
The Minos is a Edge phone equipped with technology for the ultimate multi-media experience in the mass market. It offers all relevant music & other entertainment features and above-average daily life management functions for an efficient connection of business & private life, generating personal time outs for relaxation and enjoyment.
Mobile music connector
Music MP3, AAC(+), AAC++, video Real Audio 8, OTA download

## Slide 12
Key user
benefits
Key selling
points
Key
features
Enjoyment and spontaneous relaxation on the move
Generation of personal timeouts via smooth networking
Sophisticated design and convenient size
Advanced operator customization
Full multimedia capabilities (e.g. music player w. download capability)
Complete range of quick & easy daily life management functions
High value material finishing
EDGE Class 10
Music player (multi-standards) *
MP3/AAC (+)(++), audio streaming
1.3 Mpix camera, int. LED flash
Video recording, play, streaming
20MB free user memory
RS-MultiMediaCard slot & headset
PIM function, Bluetooth
Mobile music connector

## Slide 13: Price-Volume-Scenario Over Life-Cycle 3.475 k units are planned to be sold, at an ASP of 155 EUR
Analysis
  Launch: 175,-
  EOL: 125,-
  ASP: 155,-
Price in EUR
k Units
EMEA
APAC
LAM
NAM
Price
Source
Volumes
  Volume FY03/04: 0‘1; FY04/05: 3‘4
  Peak volume is 420k units in November 04
  Over Life Cycle a price decrease of 29% is foreseen
Prices
EMEA 3‘1
APAC 0‘2
LAM 0‘2
NAM -
WORLD 3‘5
  Based on M1 commitment by Global Sales
  Agreed by PBM Pricing Office
Prices
Volumes
  Based on M1 commitment by Global Sales
  Ramp-up volumes commited by SCM
Total
2005
2006
Notes: <number>
<footer>
<header>
<date/time>
STRICTLY CONFIDENTIAL

## Slide 14: MTA at M1

## Slide 15
Minos
Direct R&D-Costs
Comment :
Account: E981-0291
M0 declared 30.06.2004
M1 planned 29.10.2004 declared 30.11.2004
DS planned 15.09.05
M3 planned 28.02.2006 (at M0: 28.10.2005)
Efforts after M3: 0,62 Mio. €
Platform: 25% of X75 Platform
Cost overview until M 3

## Slide 16: Action Items until S2
  TTM:
  Jürgen Schmitz Define process & setup concerning operator approval samples until 31.12.04 (“reference samples”) as jointly committed by NPI3 and ST2
  SM Product naming has to be finalized and agreed upon until end of december
  PMM Launch event, traide fair time schedule and overall MARCOM until end of december time schedule have to be defined
  SPM When MMI spec is available violation of registered brands has until end of december to be checked in detail
  Top Mgmt Management support to secure tight timeline for Openwave SW until approval start (AS) delivery (based on top management contacts to Openwave management)
  Jürgen Schmitz Second PLT for Minos to be committed until 10.12.04
  Profit:
  SPM until S2 License cost evaluation of MP3 has to be updated if new input has been confirmed in written
  RED AIs: out of scope of project team, portfolio relevance

## Slide 17
Competition and SWOT (1) Competitor Overview
  *Without RS-MMC card bundled
 | Siemens Minos | SE K700i | Motorola E398 | Nokia 6170 | Motorola V555 | Nokia 6230
Network | Tri | Tri | Tri | Tri | Quad | Tri
Launch time/price € | 07 2005 / tbd. | Q2 2004 / 400 | Q3 2004 / 350 | Q4 2004 / 250 | Q4 2004 / na. | Q2 2004 / 500
CRP, € (Q3 04) | tbd. | 260 | 160 | na. | na. | na.
Dimension, mm | 103x47,5x18,5 | 99x46,5x19,5 | 108x46x20,6 | 88x46x22 | 89x49x25 | 103x44x20
Weight, g | tbd. | 93 | 110 | 121 | 120 | 97
Display | 262k / 132x176 / 1.8’’ | 65k / 176x220 | 65k / 176x220 | 65k / 128x160 | 65k / 176x220 | 65k / 128x128
MMS / E-Mail |  /  |  /  |  /  |  /  |  /  |  / 
Camera / Light | 1.3 Mpix /  | VGA / tbc. | VGA /  | VGA / tbc. | VGA /  | VGA / Night mode
Video play/rec/stream |  /  /  |  /  /  |  /  /  |  /  /  |  /  /  |  /  / 
Internal Memory MB | 20 | 32 | 5 | tbc. | 5,5 | 6
External Memory | RS-MultiMediaC. slot |  | Trans flash |  |  | MMC-Slot + 32 MB MMC-Card
Audio / FM Radio | AAC(+) ringt., music player** /  | MP3 /  | MP3 player /  | 40 Polyph. /  | MP3 ringt. /  | MP3, AAC / 
BT / IrDA |  /  |  /  |  /  |  /  |  /  |  / 
PaT / IM / IMPS |  /  /  |  /  /  |  /  /  |  /  /  |  /  /  |  /  / 
Battery, mAh | 750 | 780 | 700 | 760 | na. | 780
Standby time, h | 250 | 300 | 270 | 270 | 225 | 300
Talk time, min | 300 | 420 | 590 | 240 | 210 | 300
Others | EDGE, audio streaming | No EDGE, no audio streaming | No EDGE, no audio streaming | EDGE, audio streaming | EDGE, no audio stream., SyncML | EDGE, no audio streaming

## Slide 18: Risk Assessment (1) Contingency Plan
Rea Team
PD Team
Software

## Slide 19: Decisions Proposals in case of red Q-Gate
A.) Go ahead with project
No Impacts on TTM, EBIT, Volumes, Quality if project staffing can be secured
(see AIs below).
AIs +Next Steps (including resp. and due date)
2nd PLT must be committed for X75 lead project Minos (Schmitz/Klebsch, 17.12.2004)
B.) Stop the project:
Impacts on TTM, EBIT, Volumes, Quality is calculated and available
(see backup)
Impact on MD: Lead project for new platform cancelled, entire SG2 platform endangered
We propose decision:
X
A
B