## Slide 1
CF62 Lifecycle Extension – M1 Declaration
Date: 2004-12-10
PM: Li Tao (Thomas)
PL-T: Sun Hong Liang (Tony)
SPM BA: Aicher Markus
CF62

## Slide 2: This document is reviewed and agreed by the extended REA Team
__________________ __________________ __________________
(S)PM PLT SPM BA
__________________ __________________ __________________
Sales SCM QM
sgd. Li Tao (Thomas)
sgd. Heiko Kuehling
sgd. Graham Breen
sgd. Shao Xiongyin
sgd. Sun Hong Liang (Tony)
sgd. Markus Aicher
CF62

## Slide 3: Delta description with old Leopard -- International variant
CF62
Product design:
1. New high valuable colors and finishing
2. Chrome rings around the phone
Transparent galvanization to the light loops
3. Blue LED for the dynamic light
4. Red LED for the keypad lighting
Black demon
Silver-black
Chrome rings
BOM :
BOM w/o cost adder: € 48,29
Additional cost adder: € 1,52
Risk adder: € 1,67
Current BOM incl. risk adder: € 51,48

## Slide 4: Delta description with old Leopard -- TMO US variant
CF62
Product design:
1. No Chrome rings around the phone
2. No Blue LED for the dynamic light
3. Specific color: Late Night
*
BOM & volume:
NO additional cost adder to US variants
BOM incl. risk adder: € 49.61
Committed lifecycle volume: 775K
Late Night

## Slide 5
CF62
Project Status
Timing
Financial
PSR 24/11 Update schedule
M1 15, Dec. 04 10, Dec. 04
DS 28, Feb. 05 4, Feb. 05
Product
Mechanical design is finished
SW is same as Leopard
EMC/Antenna got the test result: Antenna retuning is NOT necessary for international variant.
Dispo. variants BOM is already set up
Standard variants BOM is already set up
ASP: 70,72€ (Launch: 80€ ; EOL: 65€)
Volume: 2`26 Mio units (first shipment in 02/2005)
HK: 57,03€ (BoM: 50,82€ ; CoC: 5,24€ ; V-Adder: 0,97€ )
Profit: 0`3 Mio € (0,17% of T/O)
Gross Margin in FY04/05: 17`5 Mio €

## Slide 6
Due
Responsible
Action
Risk
Risk Assessments
Include Risk adder into BC
Promote CF62 in key countries
BOM increase if volumes do not reach commitment which was given to suppliers (3`2m units)
Markus Aicher
Olaf Weber
Done
End of January
Availability of PTCRB approval in time (lead time)
Drive approvals (R&TTE, GCF, PTCRB) in parallel
Huang Haiyun
Tony Sun
20th, Dec. 2004
CF62
Notes: <number>
<footer>
<header>
<date/time>

## Slide 7: Leopard refresh – M1 Business Case
  Launch price: 80€ ; EOL price: 65€
  Launch: 02/2005 ; EOL: 09/2005
  Volume: 2`26 Mio units total APAC: 0`13 Mio units EMEA: 1`14 Mio units LAM: 0`21 Mio units NAM: 0`78 Mio units
  BOM: includes “GS-risk-adder” of 1,67€. Thereof 1,20€ for quantity risk and 0,47€ for single source risk
  R&D: Direct 0,6 Mio €, indirect 0,3 Mio€
  Marcom: acc. to Budget
Analysis
CF62

## Slide 8: Decisions Proposal
A.) M1 is agreed, go ahead with project
Additional 2’26m volume to CF62
Gross Margin in FY04/05: 17`6 Mio €
Revenue in FY04/05: 159`5 Mio €
We propose decision:
A
CF62
x

## Slide 9
CF62
Backup
Notes: <number>
<footer>
<header>
<date/time>

## Slide 10: Leopard lifecycle extension Product Profile Stylish and Clever
CF62
Consumer Highlights:
Easy to use functionalities
Phonebook storage indicator
Calling face(*.bmp or *.jpg)
Predictive text input (T9)
Hand free speaker
Outstanding value for money
Cool and trendy look
Technical data:
Dimensions: 81.5 x 45.2 x 21.9 mm (L x W x H)
Volume: 78 cm³
Weight: 85 g
Standby time: up to 220 h
Talk time: up to 300 min
Battery: Li-Ion 600 mAh
Charging time: < 2 h for 100%
Egold-V3 platform
Main display: 130x130pix, 64K, CSTN
Sub-display: 96x64pix, B/W
Antenna: External loop
SIM: Plug-in (1.8 or 3V)
Operator Benefits:
  State of the art services like MMS, WAP, Java
  Operator customization
Positioning / Brand:
High end entry level clamshell for Fashionable Community Centrics
Female ~ Male, age focus 18-25, low income and focus on private usage.
High value feature set :
  High valuable color and finishing
  Chrome ring around the phone
  Blue illumination for dynamic light and red Color
  WAP 1.2.1
  GPRS class 10
  Attachable camera

## Slide 12: Ramp-up Planning
CF62
Notes: <number>
<footer>
<header>
<date/time>