## Slide 1: S64 (S65 w/o Camera) Product Status Report at M1, 10.12.04
Date 10.12.2004
Milestone M1
SPM Christian Baumgart
PM Hans-Martin Mues-Hane
BO PL Katia Rizzello
SPM BA Julio Carilla
Confidential

## Slide 2
S64 – Penelope w/o Camera Status M1 Declaration
Material | Supplier | SQM | Qualification Status/Problem |  | Action Items |  | Deadline
Battery cover | Balda | Lübbers | Reference samples for laquering released |  | Abrasion test failed ( parts reach only 7m instead of <10m ) Balda verifies together with Berlac. |  | CW18
RS MMC Lid | Balda | Lübbers | Additional fixation ribs will be implemented to secure that the lid not opens autonomous. |  | Follow up qualification process. |  | CW18
Rear cover | Balda | Lübbers | Reference samples for laquering released |  | Abrasion test failed ( parts reach only 7m instead of <10m ) Balda verifies together with Berlac. |  | CW18
Camera loop | Sunarrow ITT | Lübbers | PM decides to use only the silver chromatic camera loop. Color matching from Sunarrow has to be improved, samples from ITT show folding-lines on surface. ITT requested an radius from 0,8mm instead off 0,2mm. |  | PM does not want the bigger radius and accepts the folding-lines. ITT trys to improve the quality. An range has been forwarded to PM for acceptance. Risk release for 30k given to ITT. Decision for single source with ITT is in discussion. Sunarrow improves his samples to reach gloss level and color.New samples expected for cw18 |  | CW18
Keypad | Youeal | Lübbers | Youeal has partly scratches on surface |  | Youeal improves process to get rid of scratches. |  | CW18
 | Sunarrow | Lübbers | Color matching is released Tooltransfer to Beijing in cw17, FRT in cw19 |  | Follow up qualification process. Location for Ramp up will be Beijing instead of Shenzhen |  | ongoing
Joystick knob | Sunarrow Youeal | Lübbers | For Joystick knobs the pull off test method is cancelled and changed to lateral abrasion test. The adhesion between soft touch material and knob has to improved by both suppliers |  | Youeal performed the lateral abrasion test on 50 parts. Results where ok. R&D requested samples with 2 different surfaces for evaluation from Youeal.Samples expected middle of CW18. Clearify leadtime and feaseble impact to ramp up if change will be made. |  | CW18
status risk
S64
The S64 M1 document is reviewed and agreed by the S64 PD and REA Team
All PD and REA Team members have signed the S64 M1.

## Slide 3
Quality Gate Rating S64 (I) Status M1
Material | Supplier | SQM | Qualification Status/Problem |  | Action Items |  | Deadline
Battery cover | Balda | Lübbers | Reference samples for laquering released |  | Abrasion test failed ( parts reach only 7m instead of <10m ) Balda verifies together with Berlac. |  | CW18
RS MMC Lid | Balda | Lübbers | Additional fixation ribs will be implemented to secure that the lid not opens autonomous. |  | Follow up qualification process. |  | CW18
Rear cover | Balda | Lübbers | Reference samples for laquering released |  | Abrasion test failed ( parts reach only 7m instead of <10m ) Balda verifies together with Berlac. |  | CW18
Camera loop | Sunarrow ITT | Lübbers | PM decides to use only the silver chromatic camera loop. Color matching from Sunarrow has to be improved, samples from ITT show folding-lines on surface. ITT requested an radius from 0,8mm instead off 0,2mm. |  | PM does not want the bigger radius and accepts the folding-lines. ITT trys to improve the quality. An range has been forwarded to PM for acceptance. Risk release for 30k given to ITT. Decision for single source with ITT is in discussion. Sunarrow improves his samples to reach gloss level and color.New samples expected for cw18 |  | CW18
Keypad | Youeal | Lübbers | Youeal has partly scratches on surface |  | Youeal improves process to get rid of scratches. |  | CW18
 | Sunarrow | Lübbers | Color matching is released Tooltransfer to Beijing in cw17, FRT in cw19 |  | Follow up qualification process. Location for Ramp up will be Beijing instead of Shenzhen |  | ongoing
Joystick knob | Sunarrow Youeal | Lübbers | For Joystick knobs the pull off test method is cancelled and changed to lateral abrasion test. The adhesion between soft touch material and knob has to improved by both suppliers |  | Youeal performed the lateral abrasion test on 50 parts. Results where ok. R&D requested samples with 2 different surfaces for evaluation from Youeal.Samples expected middle of CW18. Clearify leadtime and feaseble impact to ramp up if change will be made. |  | CW18
status risk
S64
Profitability
Project Quality
Sales Fit
Product Quality
Strategy
Fit
Time-to-Market
Sales Fit
162€ ASP, 170€ launch price, 155€ EOL
Price risk: 5-10% due to naming issues (S64 is realized by customer as of “lower value”).
Profitability
Impact in FY05: T/O 24’6, GM 8’7, PROFIT 16% (= 3'9€) current vs. 20% (target) --> deviation: 4%
High confidence of BA to realize BC
Strategy Fit
Planned as S65 w/o camera (targeting corporate market).
QG
Rating Meeting: December 9 PSO support: G. Blecher

## Slide 4
Quality Gate Rating S64 (II) Status M1
Material | Supplier | SQM | Qualification Status/Problem |  | Action Items |  | Deadline
Battery cover | Balda | Lübbers | Reference samples for laquering released |  | Abrasion test failed ( parts reach only 7m instead of <10m ) Balda verifies together with Berlac. |  | CW18
RS MMC Lid | Balda | Lübbers | Additional fixation ribs will be implemented to secure that the lid not opens autonomous. |  | Follow up qualification process. |  | CW18
Rear cover | Balda | Lübbers | Reference samples for laquering released |  | Abrasion test failed ( parts reach only 7m instead of <10m ) Balda verifies together with Berlac. |  | CW18
Camera loop | Sunarrow ITT | Lübbers | PM decides to use only the silver chromatic camera loop. Color matching from Sunarrow has to be improved, samples from ITT show folding-lines on surface. ITT requested an radius from 0,8mm instead off 0,2mm. |  | PM does not want the bigger radius and accepts the folding-lines. ITT trys to improve the quality. An range has been forwarded to PM for acceptance. Risk release for 30k given to ITT. Decision for single source with ITT is in discussion. Sunarrow improves his samples to reach gloss level and color.New samples expected for cw18 |  | CW18
Keypad | Youeal | Lübbers | Youeal has partly scratches on surface |  | Youeal improves process to get rid of scratches. |  | CW18
 | Sunarrow | Lübbers | Color matching is released Tooltransfer to Beijing in cw17, FRT in cw19 |  | Follow up qualification process. Location for Ramp up will be Beijing instead of Shenzhen |  | ongoing
Joystick knob | Sunarrow Youeal | Lübbers | For Joystick knobs the pull off test method is cancelled and changed to lateral abrasion test. The adhesion between soft touch material and knob has to improved by both suppliers |  | Youeal performed the lateral abrasion test on 50 parts. Results where ok. R&D requested samples with 2 different surfaces for evaluation from Youeal.Samples expected middle of CW18. Clearify leadtime and feaseble impact to ramp up if change will be made. |  | CW18
status risk
S64
Profitability
Project Quality
Sales Fit
Product Quality
Strategy
Fit
Time-to-Market
Time-to-Market
April 18, 2005 (10k in VKL CW15, challenge to reach target March)
High confidence by PL-T to reach April 18 (based on reuse of existing antenna / moderate confidence if antenna has to be adjusted, could result in 2wks delay)
Project Quality
PPLs in place and resources agreed
Formal planning issues
Product Quality
Prolonging the lifecycle process into CY2006 would result in switch to lead free.
QG
Rating Meeting: December 9 PSO support: G. Blecher

## Slide 5
Decision Proposals in case of yellow Q-Gate
Material | Supplier | SQM | Qualification Status/Problem |  | Action Items |  | Deadline
Battery cover | Balda | Lübbers | Reference samples for laquering released |  | Abrasion test failed ( parts reach only 7m instead of <10m ) Balda verifies together with Berlac. |  | CW18
RS MMC Lid | Balda | Lübbers | Additional fixation ribs will be implemented to secure that the lid not opens autonomous. |  | Follow up qualification process. |  | CW18
Rear cover | Balda | Lübbers | Reference samples for laquering released |  | Abrasion test failed ( parts reach only 7m instead of <10m ) Balda verifies together with Berlac. |  | CW18
Camera loop | Sunarrow ITT | Lübbers | PM decides to use only the silver chromatic camera loop. Color matching from Sunarrow has to be improved, samples from ITT show folding-lines on surface. ITT requested an radius from 0,8mm instead off 0,2mm. |  | PM does not want the bigger radius and accepts the folding-lines. ITT trys to improve the quality. An range has been forwarded to PM for acceptance. Risk release for 30k given to ITT. Decision for single source with ITT is in discussion. Sunarrow improves his samples to reach gloss level and color.New samples expected for cw18 |  | CW18
Keypad | Youeal | Lübbers | Youeal has partly scratches on surface |  | Youeal improves process to get rid of scratches. |  | CW18
 | Sunarrow | Lübbers | Color matching is released Tooltransfer to Beijing in cw17, FRT in cw19 |  | Follow up qualification process. Location for Ramp up will be Beijing instead of Shenzhen |  | ongoing
Joystick knob | Sunarrow Youeal | Lübbers | For Joystick knobs the pull off test method is cancelled and changed to lateral abrasion test. The adhesion between soft touch material and knob has to improved by both suppliers |  | Youeal performed the lateral abrasion test on 50 parts. Results where ok. R&D requested samples with 2 different surfaces for evaluation from Youeal.Samples expected middle of CW18. Clearify leadtime and feaseble impact to ramp up if change will be made. |  | CW18
status risk
S64
A.) Go ahead with project
Impacts on TTM, EBIT, Volumes, Quality is calculated and available
(see backup, Impact on the overall MD portfolio in FY05 is: 160K units, T/O 24’6, GM 8’7, Profit 3’9).
Approve M1
X
PSR decision: approve M1
PSR decision: stop

## Slide 6
S64 – Penelope w/o Camera Backup
Material | Supplier | SQM | Qualification Status/Problem |  | Action Items |  | Deadline
Battery cover | Balda | Lübbers | Reference samples for laquering released |  | Abrasion test failed ( parts reach only 7m instead of <10m ) Balda verifies together with Berlac. |  | CW18
RS MMC Lid | Balda | Lübbers | Additional fixation ribs will be implemented to secure that the lid not opens autonomous. |  | Follow up qualification process. |  | CW18
Rear cover | Balda | Lübbers | Reference samples for laquering released |  | Abrasion test failed ( parts reach only 7m instead of <10m ) Balda verifies together with Berlac. |  | CW18
Camera loop | Sunarrow ITT | Lübbers | PM decides to use only the silver chromatic camera loop. Color matching from Sunarrow has to be improved, samples from ITT show folding-lines on surface. ITT requested an radius from 0,8mm instead off 0,2mm. |  | PM does not want the bigger radius and accepts the folding-lines. ITT trys to improve the quality. An range has been forwarded to PM for acceptance. Risk release for 30k given to ITT. Decision for single source with ITT is in discussion. Sunarrow improves his samples to reach gloss level and color.New samples expected for cw18 |  | CW18
Keypad | Youeal | Lübbers | Youeal has partly scratches on surface |  | Youeal improves process to get rid of scratches. |  | CW18
 | Sunarrow | Lübbers | Color matching is released Tooltransfer to Beijing in cw17, FRT in cw19 |  | Follow up qualification process. Location for Ramp up will be Beijing instead of Shenzhen |  | ongoing
Joystick knob | Sunarrow Youeal | Lübbers | For Joystick knobs the pull off test method is cancelled and changed to lateral abrasion test. The adhesion between soft touch material and knob has to improved by both suppliers |  | Youeal performed the lateral abrasion test on 50 parts. Results where ok. R&D requested samples with 2 different surfaces for evaluation from Youeal.Samples expected middle of CW18. Clearify leadtime and feaseble impact to ramp up if change will be made. |  | CW18
status risk
S64
Backup

## Slide 7: S64 Conservative business case indicates 8’7 Gross Margin & 3’9 Profit in FY05
  Upside with LC extension
  Price difference to S65 : - EUR 10 during LC
  Price risk 5% over LC in BC considered
  HK 88,9 per unit
  Direct R&D effort Mio. 1‘4
  Marcom efforts of Mio.1’0 considered (4% of Turnover) or 6 EUR per unit.
Comments

## Slide 8
S64 – Penelope w/o Camera Product Status
Applications
Timing/Market Introduction
Financials
Product
Accessories
S25 15.02.05, S3 11.03.05, S4 11.04.05, M3 20.05.05 DS 04/05 18.04.2005
EMEA international variant planned (No operator variant e.g. Vodafone planned)
Life cycle until end 09/2005
Volume 160 K
Delta M1 (10.12.2004))
Product modification Basis S65 “No Camera” => Rear cover modification Software modification (Exclude camera support) Antenna modification
Same as S65 except: No flash support
Same as S65 except: No java “Photo editor” / No java “Worms” Instead java “Chess”
Material | Supplier | SQM | Qualification Status/Problem |  | Action Items |  | Deadline
Battery cover | Balda | Lübbers | Reference samples for laquering released |  | Abrasion test failed ( parts reach only 7m instead of <10m ) Balda verifies together with Berlac. |  | CW18
RS MMC Lid | Balda | Lübbers | Additional fixation ribs will be implemented to secure that the lid not opens autonomous. |  | Follow up qualification process. |  | CW18
Rear cover | Balda | Lübbers | Reference samples for laquering released |  | Abrasion test failed ( parts reach only 7m instead of <10m ) Balda verifies together with Berlac. |  | CW18
Camera loop | Sunarrow ITT | Lübbers | PM decides to use only the silver chromatic camera loop. Color matching from Sunarrow has to be improved, samples from ITT show folding-lines on surface. ITT requested an radius from 0,8mm instead off 0,2mm. |  | PM does not want the bigger radius and accepts the folding-lines. ITT trys to improve the quality. An range has been forwarded to PM for acceptance. Risk release for 30k given to ITT. Decision for single source with ITT is in discussion. Sunarrow improves his samples to reach gloss level and color.New samples expected for cw18 |  | CW18
Keypad | Youeal | Lübbers | Youeal has partly scratches on surface |  | Youeal improves process to get rid of scratches. |  | CW18
 | Sunarrow | Lübbers | Color matching is released Tooltransfer to Beijing in cw17, FRT in cw19 |  | Follow up qualification process. Location for Ramp up will be Beijing instead of Shenzhen |  | ongoing
Joystick knob | Sunarrow Youeal | Lübbers | For Joystick knobs the pull off test method is cancelled and changed to lateral abrasion test. The adhesion between soft touch material and knob has to improved by both suppliers |  | Youeal performed the lateral abrasion test on 50 parts. Results where ok. R&D requested samples with 2 different surfaces for evaluation from Youeal.Samples expected middle of CW18. Clearify leadtime and feaseble impact to ramp up if change will be made. |  | CW18
status risk
S64
Conservative BC: LC 0405-0905; 160k units; ASP 153,75 ( Offer to market € 10 under S65 Price , in BC additional price risk 5% considered)
T/O 24‘6; HK 88,9 per unit, GM 8’7, PROFIT 3‘9 (16% of turnover)
Marcom 6€ per Box; direct R&D 1’4

## Slide 9: S64: Conservative business case shows 10’4 SM & 3’9 Profit