## Slide 1: Albatros Product Status Report before M0 – Dec 22, 04
B. Sommerer (PDM)/O. Girke (SPM)/S. Tan (PLT)/J. Carilla (BA)

## Slide 2: This document is review and agreed by the extended Albatros REA Team
__________________ __________________ __________________
SPM PLT SPM BA
__________________ __________________ __________________
Sales SCM QM
Signed, <Oliver Girke>
Signed, <Britta Hentges>
Signed, <Oliver Nam; Graham Breen>
Signed, <Angela Gong>
Signed, <Susan Tan>
Signed, <Thorsten Keller>
Due to the PSR decision as of Oct 27, 04 all extended core team members have to commit to the content of this presentation and “virtually” sign the presentation! Please send email to SPM.

## Slide 3: Quality Gate Rating Albatros 1/2 Status pre M0
Profitability
Project Quality
Sales Fit
Product Quality
Strategy
Fit
Time-to-Market
Sales Fit
Very negative design feedback in Poland, China, Mexico, Brazil with various focus groups and from RHQs
Feature set is no problem within this class
Major loss of reputation if we bring the product to market with its current design
Currently pricing and volume planning is under re-evaluation after the roadmap change as of CW 51
However the volume decrease will be more than 20% compared to Malpha (4'5 volume)
Profitability
No stable business case available as BOM, service and conversion costs need to be updated
Strategy Fit
Quick Pic Camera cannot be attached correctly
Strong fit to positioning in the roadmap
Segment of low to mid class phones ("below 100€") for markets like China (APAC ca 34%), Europe (22%), LAM. Clear USP differentiates from competitors ("Most reliable phone below 100€“)
QG
Rating Meeting: Dec 21, 04 PSO support: Dr. M. Assan
Notes: <number>
<footer>
<header>
<date/time>

## Slide 4: Quality Gate Rating Albatros 2/2 Status pre M0
Profitability
Project Quality
Sales Fit
Product Quality
Strategy
Fit
Time-to-Market
Time-to-Market
Requested M0 delay to be integrated in the project plan
Current Primavera DS: 13.10.05 (2 weeks delay)
Realistic DS considering design rework: beginning of Nov 05 (5 weeks delay)
Project Quality
Risk management plan for Rea team is not available and is incomplete for PD team
AD and SP need to be included in the project plan
Overdue activities and activities without assigned resources in the project planning
Product Quality
Changes in mechanical design requested
BOM, conversion costs, ramp-up plan and manufacturing locations have to be reworked
No further major issues as Albatros is a reuse of the Pegasus platform
QG
Rating Meeting: Dec 21, 04 PSO support: Dr. M. Assan
Notes: <number>
<footer>
<header>
<date/time>

## Slide 5: Decisions Proposals
A1) Go ahead with project – use existing “Bell” design (NOT recommended by REA team)
Launch in 10/05 still possible. Volumes & priceline will have to be reduced due to new Pegasus
Priceline & roadmap changes. New BC to be calculated until beginning of 01/05.
A2) Go ahead with project – with new design
Launch in 10/05 no longer possible. Minimum delay TTM of 5 weeks. Volumes & priceline will also
have to be reduced due to new Pegasus Priceline & roadmap changes.
New BC to be calculated until beginning of 01/05.
A3) Remodel project to Hera robust phone incl. Push to talk – with new design
Project info incl. launch to be provided by PG65.
B.) Stop the project:
Loss of about 33 mio € profit according to Malpha
We propose decision:
A1
B
A2
A3

## Slide 6
Backup

## Slide 7: Albatros: Business Case M-beta vs. M-alpha Status Dec 17th 2004
  LC reduction until 0906 under evaluation due to potential market entry of successor (95 Gen) at Christmas business 2006
  Volume reduction under evaluation due to LC reduction and new product ‘Aries’ on roadmap (Cannibalism)
  Price line under discussion, because feature delta to ‘Pegasus’ is only robustness and impact of new products like ‘Aries’ on roadmap have to be clarified.
  New BoM available: 34,68 € over LC (based on 4’5 units over LC) => € 4 lower than at M-Alpha
Indications for upcoming M0
Notes: <number>
<footer>
<header>
<date/time>

## Slide 8
A1 Schedule:
M0 23.12.04
S0 14.01.05
M1 04.02.05
M2 02.09.05
S3 12.09.05
PS 12.09.05
DS 17.10.05
S4 28.10.05
M3 18.11.05
Milestones Albatros Status before M0
A2 Schedule:
M0 31.01.05
S0 18.02.05
M1 18.03.05
M2 14.10.05
S3 24.10.05
PS 24.10.05
DS 28.11.05
S4 09.12.05
M3 30.12.05
Notes: <number>
<footer>
<header>
<date/time>

## Slide 9
Comment :
Account: E981-0683
M0 to be declared today (22.12.)
M1 planned 04.02.2005
M3 planned 19.11.2005
Efforts after M3: 0‘1 Mio. €
Cost overview until M 3
R&D Spending Albatros