## Slide 1: Adonis “My stylish socialiser” Product Status Report at M1, 22.12.04
COM MD PBM PG75, Vinzenz Greger (SPM), Carlos Schmidt (SPM BA), Emily Zhao (PM)
– Confidential –
Copyright © Siemens AG 2004: Copying of this document and giving it to others and the use or communication of the contents thereof, are forbidden without express authority. Offenders are liable to the payment of damages. All rights reserved in the event of the grant of a patent or the registration of a utility model or design.

## Slide 2: This document is reviewed and agreed by the extended Adonis Rea-Team
SPM: Vinzenz Greger 
PLT: John Wei / Richard 
SPM BA: Carlos Schmidt 
Sales: Patric Reiff 
SCM: Shao Xionyin 
Q: Li Ping 

## Slide 3: Adonis Industrial Design

## Slide 4: Quality Gate Rating Adonis 1/2 Status M1
Profitability
Project Quality
Sales Fit
Product Quality
Strategy
Fit
Time-to-Market
Sales Fit
102 € ASP, 115 € launch, 95 € EOL
ASP risk < 5%
3'807 units (current) vs. 2'795 units (M0)
Risk to lose up to 20% volume over lifecycle, if CMCC and I-Mode customisation will not be implemented -> CR will be launched
Good feedback from regions and high to moderate Sales confidence level
Profitability
EBIT 2.3% (8’3 €, current) vs. 7.5% (27’1 €, C-class target) --> negative deviation: -69% (-18’8 €)
high confidence in BC
Strategy Fit
All key features according to position in roadmap and story line
Definition is in line with AD requirements
QG
Rating Meeting: Dec 15, 04 (update on Dec 21) PSO support: Dr. M. Assan
Notes: <number>
<footer>
<header>
<date/time>

## Slide 5: Quality Gate Rating Adonis 2/2 Status M1
Profitability
Project Quality
Sales Fit
Product Quality
Strategy
Fit
Time-to-Market
Time-to-Market
Moderate TTM confidence because project is already delayed in comparison to M0
Challenging cycle time between M1-DS: 7 months
  S3: 01.06.05
  PS: 13.06.05
  DS: 13.07.05 (3 weeks delay to M0)
  S4: 13.07.05
Same date for DS / S4 as pilot series start 6 weeks earlier
Project Quality
Staffing of Rea & PD team complete
No frequent Primavera update from EA, NPI2, NPI31
Product Quality
BYD: 2nd supplier for camera not available, yet (current SCM audit for camera: 56%)
BYD: no 2nd supplier for display possible (otherwise 4 months delay)
BYD: FPC test is currently not passed and FPC second supplier is not available
Test and qualification plan for 2nd suppliers are missing
QG
Rating Meeting: Dec 15, 04 (update on Dec 21) PSO support: Dr. M. Assan
Notes: <number>
<footer>
<header>
<date/time>

## Slide 6: Measures, Responsible and Due Dates

## Slide 7: Comparison Business Case The current status of the BC is the M1; profitability keeps stable on M0’s level
  Volumes cover the regions EMEA, LAM, APAC. BRA and NAFTA not foreseen.
  Launch price at EUR 115 Phase out price (EoL) EUR 95
  Manufacturing costs have been improved in spite of design changes (higher value finishing)
  Conversion cost site planning includes SSMC (29%), ZALA (16%) and SSMC NoID / KLF Config (55%). Manaus not foreseen
  Further risks: - one supplier (BYD) strategy might influence time-to-market and higher return rates (about 4% incl.)
Deviation Analysis

## Slide 8: Decision Proposal
A.) Approve M1
Approve M1 status connected with the following conditions / actions:
Risk and Actions as listed on previous slide.
B) Stop project. Impact on the overall MD portfolio is: 3’8 units, 361’ Revenue, 8’3 Profit.
A) PSR decision: continue, approve conditional M1
B) PSR decision: stop

## Slide 9
Backup

## Slide 10
Product Profile - Adonis “My Stylish Socialiser”
Consumer Highlights:
Source: PDM/MM/BA
Against Competition:
Attractive, fashionable and stylish design in a modern form factor (clamshell).
State of the art camera and messaging features.
All end consumer relevant basic features included.
Operator Benefits:
  Fitting “Ultra low” requirements
  128*160 pxl, 65k colour display
  VGA Camera
  Picture messaging
Positioning / Brand:
Product Segment: Emotional Connection C Class
Target Group: Slightly more female, age 16-35 yrs, mid income, community centric, focus on private use
Differentiation within MP:
Phoenix: different form factor, more ‘fashion’ oriented, less features (video, bluetooth, AAC, RS-MMC)
Wega: different target group, less elegant
Pegasus: different formfactor, more ‘fashion’ oriented, more features (camera, display resolution)
My stylish Socialiser - A stylish, state-of-the-art (color, camera) phone for socializing with my friends and structuring my life.
Have fun together in the peer group – share insights, photos, latest rumors (camera, messaging)
Basic, easy to use feature set - no pure gadgets
Easy planning of daily life (reminder, address book, basic calendar functions)
Business:
  Volume: 3’6
  ASP: 102€

## Slide 11: Adonis Highlights
1st: C-STN 65k colours 128x160; 2nd: C-STN 4k col. 96x64
VGA; 5x digital zoom
Tri-Band
SMS, EMS, MMS, IMPS
Java 2.0; WAP 2.0
Product Highlights
Video functionality not integrated
Competing internally with Wega
Competitive risks
My stylish Socialiser - A stylish, state-of-the-art (color, camera) phone for socializing with my friends and structuring my life.
USP
Attractive, fashionable and stylish design in a modern form factor (Clamshell).
State of the art camera and messaging features.
All end consumer relevant basic features included.
Competitive strengths
Mission
Continue successful clamshell story in Connection segment with an evolution of the CF 62.
Adonis

## Slide 12: My stylish socialiser as central Consumer Value Proposition for Adonis
Adonis
Mission
Continue successful clamshell story in Connection segment with an evolution of the CF 62.
1
2
3
My stylish Socialiser - A stylish, state-of-the-art (color, camera) phone for socializing with my friends and structuring my life.
USP and Value Proposition (What)?
Young and fashionable design with clamshell form - stylish with a slight touch for showing of
Have fun together in the peer group – share insights, photos, latest rumors (camera, messaging)
Basic, easy to use feature set - no pure gadgets
Easy planning of daily life (reminder, address book, basic calendar functions)
USP
VP
Benefit (Why)?
Immediate connectivity (Voice, Messaging)
Surprising Entertainment features, but no childish gimmicks
Technical solutions easing daily life e.g. easy planning of day-to-day tasks
Target Group (Who)?
Socializing, having fun & excitements are main issues
They want to keep up with current fashion, trends & brands
They often spend more money than they should (they want to indulge themselves).
They represent the mass market hype of everything what is really successful

## Slide 13: Adonis fits to the strategy of major operators
Orange
TMO
VF
CMCC
Key Buying Factors
Operator Value Proposition
Minimum formal requirements
Siemens Strategic Fit
Comments
Consumer Segments
Adonis
CARRING & DEPENDABLE
Price
Simplicity
Voice
Autonomy
Picture Messaging
Voice
Autonomy
Picture Messaging
PRAGMATIST
Basic features
Classic Design
Reliabilty
Quality and Reliability
Value for money
Picture Messaging
TEENS
Entertainment
Brand/Design
Price
Picture Messaging
Voice Messaging
IM
120*160, 65k
Camera
GPRS Class 8
Fits*
Fits
Fits
M-Zone
Design/Brand
Features
Price
Picture Messaging
4k colours
Camera
Irda/BT/USB (2 out of 3)
Features OK*
Features OK
Features OK
No CMCC Customisation
* 2004 requirements; 2005 to be clarified
CR will be
handed in
to suit
M-Zone-
custom-
ization

## Slide 14: Comparison with competition
* Nokia 3120 includes USB
Adonis
Motorola V 500
Nokia 6170
Phillips
655
Siemens Adonis
VGA
128x160
IMPS
Price 200 €
Talktime 300 min
No nightmode
No Video Rec./ Play
No Email
VGA
176 x 220
Email
Talktime 390 min
No nightmode
No Video Rec./ Play
No IMPS
Price 400 €
VGA
128x160
Video Rec./ Play
Email
IMPS
No nightmode
Price 250 €
Talktime 240 min
VGA/ nightmode
128 x 160
Video Rec./ Play
Email
No IMPS
Price 350 €
Talktime 240 min
94x47x22 mm (tbc, incl. antenna)
Q2 2005
95x49x26 mm
Q3 2004
88x46x22 mm
Q4 2004
85x45x24 mm
Q1 2005
Size &
Launch date
Extract -
Not for external
communication
Notes: <number>
<footer>
<header>
<date/time>
STRICTLY CONFIDENTIAL

## Slide 15: Adonis SWOT
Weaknesses
Video functionality not integrated – until product launch video functionality might be available for the same price point (activation made possible via map-file)
Competing internally with Wega
Strength
Attractive, fashionable and stylish design in a modern form factor (Clamshell).
State of the art camera and messaging features.
All end consumer relevant basic features included.
Threats
Competition is quite strong in this price segment
Quality & TTM threatened due to new supplier which is not yet qualified at this stage
Opportunities
Address market segment which is looking for a fashionable phone at an affordable price.
Capitalizing on the market trend: Clamshells for an affordable price
Adonis

## Slide 16
Milestone Planning
 | M1 Status
M0 | November, 10th 2004
S0 | November, 12th 2004
M1 | December, 22rd 2004
S2 | March, 3rd 2005
S25 | April, 27th 2004
M2 | May, 6th 2004
S3 | May, 30th 2005
Production Start | June, 13th 2005
S4, Delivery Start | July, 11th 2005
Notes: <number>
<footer>
<header>
<date/time>

## Slide 17
MTA Adonis Status M1
Delay M0 -> M1:
  1 week delay of S0
  Shortened approval-time (as suggested by PD) could not be confirmed at M1.
Notes: <number>
<footer>
<header>
<date/time>

## Slide 18
Adonis Direct R&D-Costs
Comment :
Account: E981-0651
M0 declared 27.10.2004
M1 to be declared 21.12.04
M3 planned 29.07.2005
Efforts after M3: 1‘1 Mio. €
Cost overview until M 3

## Slide 19: Risks and actions, M1

## Slide 20: Risks and actions, PD-Team 1 of 2

## Slide 21: Risks and actions, PD-Team 2 of 2

## Slide 22
Risks and Actions Adonis 1/3 (as shown at M0)
done
done
done
done
Notes: <number>
<footer>
<header>
<date/time>

## Slide 23
closed
done
closed
Risks and Actions Adonis 2/3 (as shown at M0)
Notes: <number>
<footer>
<header>
<date/time>

## Slide 24
done
done
Risks and Actions Adonis 3/3 (as shown at M0)
Notes: <number>
<footer>
<header>
<date/time>

## Slide 25: Quality Management update in M1
Critical risk: main supplier BYD, which is not qualified.
Risk of higher field return rate and unacceptable higher failure rate in mass production:
  BYD does not fulfil the requirements of a capable supplier. (76% for plastic / design part Class B, 56% for cameras Class C , required AB (>=80%)).
  BYD has a lot of deficiencies in their QM system and process.
  Increased risks for the supply with sample parts and constant quality for the mass production.
Risk of endangered TTM: supplied quality and the amount of delivery are not guaranteed for ramp-up and mass production. This could lead to a delayed „Time to Market“.
QM Actions update in M1:
  Task force to improve BYD quality: SCM QM, Henning Haase,
    corrective actions and coordinate continuous improvement of BYD on a full time basis
    Latest camera audit score is 56% (better than 37% in M0&S0) .
    Next follow up audit is planed for Jan. 14-20.
  Push PD team to have second supplier of FPC, Camera, Battery: SCM QM, PQA, PM, PL-T,PD
    Battery: Take Leopard battery as fallback solution;--done
    FPC and camera: second supplier of FPC and Camera are under estimation;
    --name specific supplier, complete test and qualification plan, due date CW52;
    LCD doesn’t have second supplier, which is accepted by MP board.
    --complete BYD feasibility analyse report based on BYD display and camera TTD, due date: Dec.31

## Slide 26: Increase of thickness compared to M0
Reasons: Keypad changed to bridgeless  +0,3mm
Two colors in inner-side of upper-part (frame)  +0,3mm
Acoustic-Outlet realized with gap  +0,3mm
Overall changes: 21,3mm  22,2mm
22.17mm
21.7mm
21.54mm
22.02mm
22.17mm

## Slide 27: Competitors as evaluated in QPM, 10.9.

## Slide 28: Competitors: View from Orange

## Slide 29
Design profile - Adonis
Among the Adonis design ID´s, the appearance of A. “Belt” was rated very well. It's profile
seems to fulfils the “requirements of both worlds” the professional one in terms of being
timeless and classical but nevertheless being trendy, modern and eye-catching as well.
Eye Catching
Valuable
Nothing special
Timeless
Old-fashioned
Modern
Classical
Inferior
Extravagant
Futuristic
Sporty
Robust
Trendy
Base: N=163
Q: Which cell phone model corresponds best to following statements? (Multiple answers)
A. „Belt“
A. „Tongue“
A. „Jew. Box“
Notes: <number>
<footer>
<header>
<date/time>

## Slide 30
Method: Focus group discussions (personal interviews)
Test – Regions: EMEA/ AIP/ NAP/ NAM/ LAM
Test – Countries: EMEA: Italy (Milano) / Germany (Munich)
AIP: Thailand (Bangkok), NAP: China (Beijing)
NAM: USA (San Francisco / Chicago)
LAM: Mexico (M. City) / Brazil (Sao Paulo)
Sample size: N = 163 (2 groups per town/ ~10 resp. each)
Field work: Nov 15-30, 2004
Institutes (Field): Coord.: Neue Marktforschung GmbH/ Cologne
Milano: Muller & Associati s.l.r.,
Munich: Teststudio Knigge
Bangkok: TNS Thailand, Beijing: AC Nielsen Beijing Ltd.
San Francisco: Fleischmann Field Research
Chicago: Murray Hill Center (Loc.)
Mexiko: Estadística Aplicada,
Sao Paulo: Escritório de Pesquisa
Study design/ Methodology
Notes: <number>
<footer>
<header>
<date/time>