## Slide 1: Quality Gate Rating Quail 1/2 Status M0
Profitability
Project Quality
Sales Fit
Product Quality
Strategy
Fit
Time-to-Market
Sales Fit
Launch price 68€, ASP 60€ , 55€ EOL; no price risk
3’37 units, volume risks (based on 68€ launch): EE 20-50%, WE >50%, Americas 24%, AIP >50%, China 52%, MEA 81%
APMs: positive feedback on 2nd design and feature set
EE: CSTN display is not well accepted
MEA: very thick, camera is missing
Missing customer requirements: camera, bluetooth/Irda
Profitability
Profit: +6’0€ (+3.1%, current) vs. + 8’0€ (+4.0%, target) --> deviation: -25% (based on 65€ launch, 3’37 units)
75% confidence in current BC; Risk on pricing and BOM-commitment of SP implemented;
Strategy Fit
First clam shell in A-class / entry level. New form factors are needed to strengthen the position in entry class.
Product fits strongly to definition. Minor upgrades due to market situation (external display in 4k colour)
Lifecycle of 13 months
Addressable market: 150’6 units, market share 2.2%; regional split: EMEA 56%, LAM 24%, APAC 20%
QG
Rating Meeting: 23-Mar-05 (updated 3-May-05) PSO support: G. Blecher, M. Assan
Notes: <number>
<footer>
<header>
<date/time>

## Slide 2: Quality Gate Rating Quail 2/2 Status M0
Profitability
Project Quality
Sales Fit
Product Quality
Strategy
Fit
Time-to-Market
Time-to-Market
Low TTM confidence because no supplier is yet selected, it is the first implementation of new antenna concept and the request to reuse the Polaris battery is not yet evaluated
  M1 30.05.05 (3 workday delay)
  S25 11.11.05 (0 workday delay)
  DS 23.01.06 (4 workdays delay)
  S4 03.02.06 (2 workdays earlier)
Project Quality
Plan: Some critical activities overdue up to 18d
Risk management under preparation, pending due to supplier selection
Product Quality
Antenna radiation performance in GSM 900 band in closed position does not full FBT by 1dB
Microphone type selection is still open due to open antenna concept
QG
Rating Meeting: 23-Mar-05 (updated 3-May-05) PSO support: G. Blecher, M. Assan
Notes: <number>
<footer>
<header>
<date/time>

## Slide 3: Comparison Business Case The current Business Case shows a profit of 6’0 EUR or 3,1% of Turnover
  Volumes increased by 840k compared to Roadmap Scenario 2C’ due to cancellation of Albatros.
  Average CRP by 16% or 11 EUR per unit lower than Roadmap Scenario 2C’. New launch price at EUR 67,- Phase-out price EUR 52,-.
  BoM over LC 36,52 as indicated by PE for S0.
  Manufacturing costs decreased by 1% or 0,39 EUR per unit compared to Roadmap Scenario 2C‘.
  Conversion cost: site planning includes SSMC (76%) and Manaus (24%). KLF not foreseen.
  Further risks:
  Acoording to planning in Primavera the DS will be Jan 23, 2006 instead of the target of Jan 17, 2006. Therefore delivery in Jan 06 will be only 15k (instead of 100k) acc. to Ramp-up plan. To be confirmed before M1.
Deviation / Analysis
Quail