## Slide 1: Quality Gate Rating Finch 1/2 Status M0
Profitability
Project Quality
Sales Fit
Product Quality
Strategy
Fit
Time-to-Market
Sales Fit
Launch price 60€, ASP 52€, EOL 45€; APM: price position is too high, max. 52€ launch
6'65 units, total volume ~50% (based on 60€ launch): WE no risk, EE 20-50%, Americas 51%, MEA 90%, APAC 100 %, China 40%
Missing customer requirements: camera, bluetooth or Irda
Positive design acceptance test: ranking for Pipe design: 3rd place (1st was Around design, preferred by APMs)
AIP: No USP (me-too), only compete on price or brand
Profitability
Profit: -7’0 € (-2.4%, current) vs. +11’7€ (+4%, target) --> deviation: -160% (based on 52€ launch, 6'65 units)
60% confidence in the current BC; Risk on pricing and BOM-commitment of SP implemented
Strategy Fit
Modest fit to roadmap and story line: standby time (270h vs. 410h) is not USP, is considered to be competitive and is a compromise to meet the required dimension and costs
Huge impact on portfolio as Finch addresses the entry level colour segment & midrange A-class (high volumes)
Life cycle of 12 months
Large, mature market; addressable market: 191'8 units, market share: 3.46%
QG
Rating Meeting: 11-Apr-05 (updated 3-May-05) PSO support: Dr. M. Assan
Notes: <number>
<footer>
<header>
<date/time>

## Slide 2: Quality Gate Rating Finch 2/2 Status M0
Profitability
Project Quality
Sales Fit
Product Quality
Strategy
Fit
Time-to-Market
Time-to-Market
85% TTM confidence level: RF evaluation is open
  M1 23.05.05 (4 days delay)
  S25 02.11.05 (2 days earlier)
  DS 25.01.06 (1 day earlier)
  S4 22.02.06 (8 days earlier)
Project Quality
Staffing is complete, but resources for the LAM 850 variant evaluation are missing if SD2 RF solution is used
Product Quality
RF: Antenna performance in GSM850 is not yet committed to meet the FBT requirement
HW: Microphone and vibrator are on the same side. This might cause an EMC problem.
MD: The two decorations on the top and bottom of the housing are a potential risk for the drop test.
QG
Rating Meeting: 11-Apr-05 (updated 3-May-05) PSO support: Dr. M. Assan
Notes: <number>
<footer>
<header>
<date/time>

## Slide 3: Comparison Current Business Case The current Business Case shows a profit of -7’0 EUR or -2,4% of Turnover
  Volumes remained stable
  Average CRP decreased by 8,- Euro compared to Roadmap Scenario 2C’. Launch price at EUR 52,-. Phase out price EUR 37,-.
  HK decreased by 17.4% or 11,3 EUR to 35,08 EUR compared with Scenario 2C‘.
  New BOM from CW17: 29,70 EUR per unit.
  Production site split: SSMC (72%), Manaus (28%). KLF not foreseen.
  R&D cost decreased by 1,3m EUR after re-planning.
  MarCom: A-class costs for push-budget (1,50 EUR per unit) and pull-budget (1% of T/O) as well as HQ-Fund (1‘5 Mio EUR) considered.
  EBIT indication of -7,0m EUR or -2% of Turnover. The profit went down by 10,1m compared with preliminary BC due to lower pricing.
Deviation / Analysis
Finch