## Slide 1: Siskin “Fashionable snapshot phone” Product Status Report at M0
COM MD PLM Emily Zhao, Carlos Schmidt, Paul Xu
April 29th, 2005

## Slide 2: This document is review and agreed by the extended Siskin REA Team
__________________ __________________ __________________
PM PLT SPM BA
__________________ __________________ __________________
Sales SCM QM
Signed, Emily Zhao
Signed, Li Ping
Signed, Oliver Nam
Signed, Mike Cai
Signed, Paul Xu
Signed, Carlos Schmidt
Siskin

## Slide 3: Quality Gate Rating Siskin 1/2 Status M0
Profitability
Project Quality
Sales Fit
Product Quality
Strategy
Fit
Time-to-Market
Sales Fit
ASP 95€ , launch price 115€, 80€ EOL: No price risk
2’12 units, 36% total volume risks (based on 115€ launch) (WE, EE no major risk, Americas 61%, AIP 100% !, China 64%, MEA 63%)
A too-thick mock-up was used in the design acceptance test (medium ranking); Dr. Lepold is reported to have accepted the right mock-up
APM: Very negative feedback on design (loop antenna), positive feedback on features
Missing customer requirements: Bluetooth, EDGE, flash, orange- & i-mode-customisation
Profitability
Profit +0’4€ (+0.2%, current) vs. +15’9€ (+7.5%, target) (based on 115€ launch, 2’12 units) --> profit deviation: -97%
High confidence in current BC for M0 status
Volume increase is crucial for BC improvement, reduction of the manufacturing cost is main potential
Strategy Fit
Strong fit to story line & high portfolio impact, as Siskin is the only C-Class image clamshell in 06 (Baya & Macaw cancelled)
Life cycle of 12 months
The addressable market of Siskin is still a mainstream market. 67’2 units, market share: 4%
QG
Rating Meeting: 29-Mar-05 (updated 3-May-05) PSO support: G. Blecher, M. Assan
Notes: <number>
<footer>
<header>
<date/time>

## Slide 4: Quality Gate Rating Siskin 2/2 Status M0
Profitability
Project Quality
Sales Fit
Product Quality
Strategy
Fit
Time-to-Market
Time-to-Market
Low TTM confidence due to late availability of software driver which is needed for a display and camera upgrade
  S0 22.04.05 (21 workdays delay)
  M1 06.05.05 (19 workdays delay)
  S25 12.09.05 (10 workdays delay)
  DS 08.12.05 (no delay)
  S4 06.01.06 (1 workday delay)
Project Quality
Plan: 6 overdue activities
Risk management plan not finalised, yet
Product Quality
Worst-case SAR value does not meet SAG requirements (1.3 vs. 0.8 W/kg over 1g). However, Siskin reuses the mechanical & antenna concept of Leopard/Adonis, thus same values are expected.
Risk of an increased return rate due to new technology for internal display lens (die cut glass lens)
One-stop solution, BYD, last audit result for Adonis is 76% for plastic/design part (Class B), 71% for cameras (Class C). However, required is >=80% (AB)
QG
Rating Meeting: 29-Mar-05 (updated 3-May-05) PSO support: G. Blecher, M. Assan
Notes: <number>
<footer>
<header>
<date/time>

## Slide 5: Measures, Responsibles and Due Dates
Siskin

## Slide 6: Comparison Business Case The current Business Case shows a profit of 0,4m EUR or 0,2% of Turnover
Deviation Analysis / Assumptions
  „Fast track“ model; w/o M-Alpha/Beta
  Volume reduction by 20% or 558k units over LC due to sales risks
  Average CRP increased by 31% or 22,5 EUR to 95,2 EUR compared to Roadmap Scenario 2C’. Launch price at EUR 115,- / Phase out price at EUR 80,-.
  Actual HK increased by 8,26 EUR per unit compared to Roadmap Scenario 2C‘. New BOM: 59,55 EUR per unit.
  Cost per Return: EUR 45,02. Return Rate in FY06: 9,2% and in FY07 8,7%.
  Direct R&D costs of 2,5m EUR, including platform costs of 1,2m EUR.
  Marcom costs: 7,7 EUR per unit.
  EBIT of 0,4m EUR or 0,2% of Turnover
Siskin

## Slide 7: Decisions Proposals in case of red Q-Gate
A.) Go ahead with project until M1 Approve M0 status connected with the following conditions / actions:
Improve the BOM  Magnus/ Nadine till M1
  lift part (BYD)
  E-BOM cost (Infinion)
  Conversion Cost
Implement measures to secure M0 timeline  Paul, M1
  Monitor Epson 758 deliver schedule
Implement measures to secure product quality  Paul, M1
  SAR,
  Epson 758
B.) Stop the project: impact on overall MD portfolio is :2’2 unites, 213’ Revenue, no competitive image phone in 2006, due to Baya and Macaw were canceled
A
B
We propose decision:
X
Siskin

## Slide 8
Backup
Siskin

## Slide 9
Product Profile - Siskin Fashionable snapshot phone
Consumer Highlights:
Fashionable snapshot phone –
The fashionable companion always ready to capture instant snapshots of your favorite moments.
Very fashionable Clamshell with 1.3 Mpix camera and 262k TFT display for a competitive price
Source: PDM/MM/BA
Against Competition:
Attractive, fashionable and stylish design in a modern form factor (clamshell). Slim—with the thickness of 21.1 mm.
1.3 M camera with 262K TFT display and messaging features.
All end consumer relevant basic features included.
Operator Benefits:
Fashionable clamshell attracts a big target group
Integrated 1.3 Mpix camera and MMS for additional ARPU
Java and WAP for download over the air
Doja 1.2 to meet I-Mode entry level phone’s requirement.
Positioning / Brand:
C-Class, Emotional Connection
Slightly more female(60%)
Age: 16 – 35
Low to mid income
Focus on private use
Differentiation within MP:
Quail: Pure voice communication – Modern-styled clamshell for pure voice communication.
Swift: Eye-catching multimedia slider – Offers instant entertainment and infotainment in QVGA quality in a valuable, eye-catching slider design
Business:
  Volume: 2’232 units ASP: EUR 95.24 / HK: EUR 70.88
  RD: EUR 7‘4 / MARCOM: EUR 17‘2
  Profit: EUR 0‘4 (0,2% resp. EUR 0,01 per unit)
Siskin

## Slide 10: Siskin Competitors
  Display 176*220, 260K TFT
  1.3 Mpix camera/flash
  5M shared memory + T-flash
  MP3 & Poly
  Display 176*220, 260K TFT, 2nd display 65K TFT
  1.3Mpix camera/flash
  96M shared memory
  MP3 & 40 poly
  Display:260K TFD, 240*320
  1.3Mpix camera
  15M shared memory+SD card
  64 poly & MP3
  Feature
  2nd display 4096 CSTN
  Size:88x47x24
  2nd display 120* 160
  Size: 105*49*24
  Display 260K TFT
  1.3Mpix camera
  Size: 93x46x21.1
  Display size: 128*160, 2nd display 96*64 CSTN
  No MP3
Siemens Siskin
Motorola V635
LG L5100
Mitsubishi M900
Siskin
Notes: <number>
<footer>
<header>
<date/time>
STRICTLY CONFIDENTIAL

## Slide 11: Versus the Competition
  1.3Mpix camera
  MP3
  Display 260K TFT
  size: 176*220, 2nd display 65K OLED
  1.3Mpix camera/flash
  90M shard memory
  MP3 & 64 poly
  Display 260K TFT , 176*220, 2nd display OLED
  1.3Mpix camera
  50M shared memory
  64 Poly
  Display:128*160
  Thickness: 24mm
Siemens Siskin
Innostream A10
Samsung E720
Samsung
SGH z300
Benchmark
  Display 260K TFT
  1.3Mpix camera
  Size: 93x46x21.1
  Display size: 128*160, 2nd display 96*64 CSTN
  No MP3
Size: 89×47×26
Siskin
Notes: <number>
<footer>
<header>
<date/time>
STRICTLY CONFIDENTIAL

## Slide 12: Siskin SWOT
Strength | Weakness
Fashionable but clear design in a modern form factor (Clam-Shell). High resolution camera phone. (1.3M pix) All end consumer relevant features included. | Current profit performance of the product below target Bluetooth not included
Opportunities | Threats
Address market segment which is looking for a fashionable phone at an competitive price (at 115 Euro). Capitalizing on the market trend: Clam shells for an affordable and attractive price | Competition becomes quite strong in the Clam Shell market. Competition with Adonis internally
Source: Verena Pannenbaecker
Siskin
Notes: <number>
<footer>
<header>
<date/time>

## Slide 13: Key-parameters / input for the Reverse Calculation Product: Siskin
PRC | Development (direct) | € 2’5
 | Marketing (direct) per unit sold | € 7,70
 | Return rate | 9,1
 | Cost per return | € 45,02
 | Return costs per unit | 4,3%
Manu-factur-ing Costs | Ø Manufacturing Costs | € 70,88
 | Conversion Costs | € 6,75
 | Ø BOM | € 59,55
 | BOM price decrease over lifecycle | 10,3%
 | Variant Adder | € 1,12
 | Licenses | € 3,46
TCG | Target Cost Gap | - € 15’5 50’387
 | Target Cost Gap per Unit | - € 6,93
General | Launch date | 12/05
 | End of Life | 12/06
 | Positioning | mid tier
T/O | Units | 2’232
 | Launch price | € 115
 | EOL price | € 80
 | ASP | € 95,24
 | Price decrease over life-cycle | -30,4%
Profit | Target Profit | € 15’944
 | Target Profit in % of T/O | 7,5%
OH I | Administration in % of T/O | 1,2%
OH II | Development (indirect) in % of Development (direct) | 102%
 | Marketing (indirect) in % of T/O | 4,0%
 | Selling Expenses in % of T/O | 5,0%
 | SCM Costs in % of T/O | 2,0%
 | Other GOGS in % of T/O | 1,3%
Analysis
  Positive Profit: EUR 0‘4 (0,2% / € 0,01 per unit)
  Potential for improvements especially in Service costs, CC and Marketing
Siskin

## Slide 14: Siskin – Business Case The actual Business Case of the Siskin shows a Profit of EUR 470k (0,2%)
Siskin

## Slide 15: Siskin – Reverse Calculation
Siskin

## Slide 16: MTA
Siskin

## Slide 17
Siskin
Direct R&D-Costs
Comment :
Account: E981-0722
M0 to be declared today (04.05.05)
M1 planned 21.04.2005
M3 planned 02.02.2006
Efforts after M3: 0’03 Mio. €
EGK-Factor of 85 Gen.
04/05: 2,21
05/06: 1,9
Platform: 1/3 of X75 / 85 Platform
(not approved yet)
Date of FC: M0 Plan (15.04.05)
Cost overview until M 3
Siskin

## Slide 18
Risks and Actions Siskin
SAR Value | Value is about 1.4. Latest result is the SAR value may be is smaller than adonis SAR value | Performance problem | Medium | Continue to put effort for reducing SAR value | Yan Hai Tao | M1
Acoustic | Gap between Liftpart and Basepart is small (<0.5mm) Back Volume is small (<1.5cc) | Performance problem | Medium | PM to accept the current performance | Zhao Li | 
EPSON 758 Issue A | Devliery time will affect Liftpart delivery | Performance problem and TTM | High | Constant monitoring of EPSON delivery schedule. | Ingrid Kremmer Nadine Rohde | 
EPSON 758 Issue B | Delivery time will affect 1.Component qualifiaction 2.Application qualification | TTM | High | 1.Constant monitoring of project schedule. 2. Set up the detail plan in PV | Chen Zhuo Dong Run Sheng | 
EPSON 758 Issue C | Delivery time will affect SW development plan 1. Camera 1,3Meg CMOS Camera 2. TFT 272K LCD | TTM | High | 1.Constant monitoring of project schedule. 2. Set up the detail plan in PV in order to analyse the schedule | Huang Kan | 
EPSON 758 Issue D | 1,3Meg CMOS Camera(Radermacher klaus concerns the development, because 1.3Meg CMOS Camera will involved optical issues) | Performance problem and TTM | High | 1.Constant monitoring of project schedule. 2. Collecting development experience and knowledge from other projects | Dong Run Sheng | B1
Liftpart | EMC/ESD | Performance | Medium | Continue to put effort for reducing R&D time | Yan Hai Tao | B1+
FPC M1 Declaration | FPC Delivery Schedule is not include in schedule (Only qualification schedule) | TTM delay | Medium | 1.Constant monitoring of project schedule. 2. Set up the detail plan in PV in order to analyse the schedule | Xu Haixiang | M1
Siskin
Notes: <number>
<footer>
<header>
<date/time>