## Slide 1: Polaris “Premium convenience“ Product Status Report at M0, May 4th
SPM E. Hachmann
SPM BA T. Keller
PLT T. Neumann

## Slide 2: This document is review and agreed by the extended <project> REA Team
__________________ __________________ __________________
SPM PLT SPM BA
__________________ __________________ __________________
Sales SCM QM
Eric Hachmann ( )
Zlatko Kirin ( ✓ )
Oliver Nam ( ✓ )
Antje Hartung (✓)
Thomas Neumann (✓ )
Thorsten Keller ( ✓ )
Due to the PSR decision as of Oct 27, 04 all extended core team members have to commit to the content of this presentation and “virtually” sign the presentation! Please send email to SPM.
✓ Reviewed and in agreement
X Has not reviewed or is not in agreement
✓

## Slide 3: Quality Gate Rating Polaris 1/2 Status preM0
Profitability
Project Quality
Sales Fit
Product Quality
Strategy
Fit
Time-to-Market
Sales Fit
Launch price 150€, ASP 117€, EOL 95€; 10-15% price risk (APMs: 130€ launch price would achieve the planned volume)
2’03 units, total volume risk of 35% (based on the 150€ launch) WE 50%, EE 20-50%, Americas >50%, MEA 33%, China 62%, AIP 100%!
Launch date very close to Swift which has a better feature set
Missing customer / APM requirements: no camera, no flash
Target group for convenience does not exist in Asia
“Flawless” design, ranked #1 in acceptance test in all regions
Profitability
Profit: -18’9 € (-8.8%, current) vs. 21’5€ (10.0%, target) --> profit deviation: -188% (based on 130€ launch, 2’03 units)
Medium confidence in current BC as input quality is medium (e.g. sales risks);
Strategy Fit
High portfolio impact due to volume, slimness, and continuation of convenience story from Mars
UI SW is not fully implemented due to budget constraints
Lifecycle of 14 months
Large, growing market; addressable market: 64‘6 units; market share: 3.1%; 75% EMEA, 18% APAC, 7% LAM
QG
Rating Meeting: 14-Apr-05 (updated 3-May-05) PSO support: Dr. M. Assan
Notes: <number>
<footer>
<header>
<date/time>

## Slide 4: Quality Gate Rating Polaris 2/2 Status preM0
Profitability
Project Quality
Sales Fit
Product Quality
Strategy
Fit
Time-to-Market
Time-to-Market
Insufficient confidence to reach 02/06 launch (as of roadmap) due to SW delay
No DS date available due to missing platform input (worst case risk is up to 3 months)
Project Quality
Plan: Links to platform planning are missing (esp. SW)
Plan: Some overdue activities (esp. SW dependents)
Staffing complete and already on the job working in S0 and M1 work-packages
Product Quality
SW feature list and time schedule are not available
RF: 70% of bandwidth for 1900 MHz will fulfil FBT requirements (100% in all other bandwidths)
New technology "real metal keypad“: suppliers have little experience
New technology "real metal front cover“: Colour match between Front Cover and Keypad is difficult, alternatives are being assessed
QG
Rating Meeting: 14-Apr-05 (updated 28-Apr-05) PSO support: Dr. M. Assan
Notes: <number>
<footer>
<header>
<date/time>

## Slide 5: Measures, Responsible and Due Dates
Open: CW18
Done
Done
Done
Done
Done
Status
Done
Done

## Slide 6: Comparison Business Case The M0 Business Case shows a profit of -18’9 EUR or -8,8% of Turnover
Deviation / Analysis
  „Fast track“ model; no M-Alpha milestones
  Volume increased by 40k compared to Roadmap Scenario 2C’.
  Average CRP decreased by 24 EUR per unit to 106,0 EUR per unit. Launch price 130 EUR per unit, EOL price 85 EUR per unit.
  Average HK decreased by 11% to 67,2 EUR per unit. New BOM 57,8 EUR per unit.
  Cost per Return: 41,2 EUR. Return Rate in FY06: 10,3% and in FY07 8,3%
  Direct R&D costs of 10,1m EUR, plus ‚direct platform costs‘ of 10,8m EUR considered (1/6 of X75/85G SG2 Rel.1 and 1/7 of SG2 Rel.2).
  Marcom costs based on new product name „SC120“: 27,7m EUR or 13,6 EUR per unit
  EBIT of -18‘9m EUR or -8,8% of turnover
  Team comment: Not sufficient upside potential identified for reaching EBIT target of 10% and M0 target cost gap of 19,9 EUR per unit.
Polaris

## Slide 7: Decisions Proposals in case of red Q-Gate
A.) Go ahead with project
Declare M0 maturity for all departments except PD SW (due to SG2 Rel.2 SW)
Continue working on S0 and M1 work packages
Further investment of 1.478K until SW M0 already committed in MD board (see back up)
Review impact of SW M0 delay: current worst case 3.5 months (see backup)
B.) Stop the project:
Loss of 78,6m EUR (or 37% of Turnover) Sales Margin and 2,0m units
We propose decision:
A
B
✓

## Slide 8: BACKUP
Backup:
Proposal to continue project (Inc. required investments and AIs)
Decision by W. Klebsch and R. Lepold on April 15, 2005
Timetable and estimated impact of PD SW M0 delay
Product highlights:
    Positioning (Convenience & Business)
    Consumer and Operator benefits
    Comparison against competition

## Slide 9: Polaris Issues:
Polaris: M0 maturity will be reached (all departments except PD) by May, 4th  SW is the blocking point, impacting system test and quality
TTM is highly endangered already (due to 3,5 months delay in SW M0)
 Project schedule from M0 to M3 is not available (PD can not commit milestones dates without SW planning)
 Project needs to continue to work on S0 and M1 work packages, particularly HW and mechanics (which is not possible due to process, since M0 is missing)
 Project needs a limited budget release for:
    Investments in Mechanics and HW: ~1.343K €
    SCM A1 to B1 (until M0, mid of June): ~ 135K €
    Total Investments for Polaris before M0 ~1.478K €*
The Rea Team suggests to continue working until M0 can be declared (mid of June) and the total investment of ~1.478K be released.
See details
*Amount does not include PD budget

## Slide 10: Decision by W. Klebsch and R. Lepold on April 15, 2005
Clearly communicate into organization (PBM and PD) Polaris, Swift, Ibis as High Prio products with an importance like Kestrel.
Limited release for external cost for long-runners, in order to ensure TTM for:
  Polaris: 1’478 €
  Swift: 1’800 €
Agreement on: - missing budget for Rel. 2 of 920 k€ - CR buffer for SG2 SW Rel 2 of 7 PY (3.5 PY in 04/05), leading to a total commitment of additional 1.5 mill. € budget in 04/05 for SG2 Rel. 2 *
Yes
No
With Modificat.
Decisions taken:
√
√
√
* PD will start immediately resource availability evaluation and TTM impact analysis

## Slide 11: Backup: Timeline impact for Polaris
E 02/05
E 03/05
E 04/05
E 05/05
E 06/05
E 07/05
E 08/05
Base plan
M0 = 02/05
S0 = M04/05
M1 = 05/05
PLT estimated status
M0 = M06/05
M1 = 08/05
S0 = M07/05
Click to go back

## Slide 12: Backup Polaris: Overview of investments until MO
Click to go back

## Slide 13: Price / Volume Scenarios based on feedback from APMs

## Slide 14
Product Profile - Polaris Premium Convenience
Consumer Highlights:
  Premium-value appearance, slim design with an extraordinary real metal finish
  Focus on core functions (inc. SI voice recognition, BT, excellent display and sound quality)
  Design focused on best ergonomics and usability
Against Competition:
Polaris is the only phone that combines the various properties: Pure User Interface, Pure Functionality, Premium Design, Best Ergonomics
Operator Benefits:
  Ease of use supports more frequent employment of ARPU-generating features
  "Fast calling key" and SI voice dialling enable easy and frequent voice communication (possible additive operator service opportunities)
  The target group has a low churn
Positioning / Brand:
  Premium convenience
  Supporting theme Core Business
Differentiation within MP:
  Theme successor to Mars
Business:
  Supporting theme: Addressing corporate channels with perfect core features for business users like PIM & BT.

## Slide 15
Additional Supporting Slides
Backup

## Slide 16: Enthusiasm Model for Polaris
Detailed product story / slogan for the “Premium Convenience” phone
 | Consumer requirements |  |  |  | MNO requirements |  |  |  | 
Support/ provide … | not req. | Basic | Perf. | Enth. | not req. | Basic (under fulfilled) | Perf. (meet) | Enth. (exceed) | Target values (value range)
Quality of basic functions (I/O-keypad & voice / UI / RF) |  |  |  |  |  |  |  |  | Maximum convenience UI; best usability (keys, size), best voice quality (no music), hands-free
Usage/ standby time |  |  |  |  |  |  |  |  | 690 mAh battery: Max SBT: 335h Max TT: 6.9h (but not compromising size: total thickness: 13.25mm)
Design/ Material/ Form factor |  |  |  |  |  |  |  |  | extremely slim bar phone, real metal,
Visualization (display/ lighting) |  |  |  |  |  |  |  |  | 132 x 176, focus on best contrast, brightness and viewing angle; best visibility under all conditions (as Hydra)
Imaging/Video |  |  |  |  |  |  |  |  | No camera. Video player for MMS decoding
Music/Audio |  |  |  |  |  |  |  |  | Ring tones: MP3, AAC++, MIDI, …
Gaming |  |  |  |  |  |  |  |  | 
Outdoor (robustness/location) |  |  |  |  |  |  |  |  | 
Messaging/Presence/ PoC |  |  |  |  |  |  |  |  | 
Business/ PIM/ Sync |  |  |  |  |  |  |  |  | 
Interaction with other devices |  |  |  |  |  |  |  |  | Bluetooth (for car kit and headset), (no IrDA). Inductive antenna coupling for car kit
Data storage |  |  |  |  |  |  |  |  | 8 MByte user memory
Consumer personalization/ Operator customization |  |  |  |  |  |  |  |  | convenient UI
Required air interface: GSM GPRS EDGE UMTS WLAN VoIP (WLAN) other: “…”
Preferred form factor: Bar Slider Clam New/ others:
X
X
X
SW development: No commitment to timeline
Achievement of superlative UI on time? Can convenience MMI be implemented on time?
Possible risks

## Slide 17: Product targets, idea and slogan for Premium Convenience
Premium convenience embodied in a perfect match of distinguished design and essential functions
Reason to make: Continuation of Convenience Story started with Mars to exploit new target segment: Cultivated Work & Life.
Product Idea: Premium Convenience
Key Theme: Convenience
Related use cases/ special characteristics: convenience UI, best audio (for voice), keypad layout; high value appearance
Dedicated Innovation: combination of slimness, convenience and housing
Story successor to: None
Price Point: 150€ launch
Launch date/ Lifecycle: 02/06 ~ 04/07 / 14 months
Addressable Market: 64,576 Mio. units
Planned volume/ market share: 2,030 mio. / 3,1%
Target Profit: 7,5% EBIT
Consumer (Sub-)Segment: Cultivated Work & Life
Regional Market Focus: EMEA, AIP, LAM,
Sales Channel Split: 60:40 (operator : retail)
Key operators addressed: TMO (simplicity), VF (easy phone)
Main reference/ competitor products: Currently no competitor in the market
Pro-position
Product idea
Target Positioning in Portfolio
Target Market
(Consumer and Operator)
Window of opportunity for Polaris
“Current roadmap draft to be included.”
Convenience
Polaris

## Slide 18: Premium Convenience
Product Idea, Target Group
Polaris
Product Idea
Premium convenience embodied in a perfect match of distinguished design and essential functions.
  Male : female, 50 : 50
  High income
  35 - 60 years
  Core Target group:
  Need for an intuitive, faults-preventing usability avoiding gadget elements
  Focus on key functionalities
  Request for best quality and performance, no tolerance for disappointments
  Design has to convey a personality aspect of the end user by its high-value and stylish finish
  Premium quality design is as important as price in their purchase decision
  Additional Target group: Addressing corporate channels with perfect core features for business users like PIM & BT.
Product Segment
Target Group Socio-demographic Data
Target Group Behavioural Aspects
Convenience
Back:
Notes: STRICTLY CONFIDENTIAL

## Slide 19: Key Features
  Premium slim design with an extraordinary finish
  Focus on core functions
  Comfortable usage with voice dial and voice command
  Best readability of display content under all conditions
  Design focused on best ergonomics and usability
  Car Kit BT
Key Features
Polaris
Back:
Notes: STRICTLY CONFIDENTIAL

## Slide 20: Highlights
  Reduced, classic style phone, focusing on ergonomics and usability
  Premium-value appearance (e.g., real metal front)
  Slim format
  Integrated start assistant
  Personal Information Management (PIM)
  Car Kit Bluetooth® solutions
  Headset Bluetooth®
  Data cable serial and USB
Design
Applications
Technology
  Display: 132 x 176 pixels, 1.8 inch; TFT 256 with optimal viewing angles, brightness and brilliant colours
  Excellent audio quality
  Bluetooth®
  Speaker-independent voice dialling and digit dialling
Accessories
Highlights
Polaris
Back:
Notes: STRICTLY CONFIDENTIAL

## Slide 21: Technology
Technology
Polaris
Hardware
Dimensions
Standby Time / Talk Time
Display Size
Display
Camera
Flash
Battery
107.5 x 44 x 13.2 mm
>300h / >300min.
132 x 176 pixels, 1.8 inch
Enhanced TFT 256K
–
–
Slim Li-Ion 690 mAh
Software
Messaging
Multimedia
Free Memory Capacity
Internet Access
Network Type
Data Transfer
Connectivity
Video Recording / Playback
SMS, MMS
MP3, AAC, AAC+, AAC++ ringtones, video playback
8 MB
–
Tri-band GSM 900 / 1800 / 1900
GPRS Multislot Class 10, EGSM
Bluetooth®
– / 
Back:
Notes: <number>
<footer>
<header>
<date/time>
STRICTLY CONFIDENTIAL

## Slide 22: Consumer Benefits
Premium Design Highly attractive premium design: very slim phone with real metal surface
Best Usability Product design focuses on excellent ergonomics and best usability
Best Ergonomics Ergonomic keypad (large, well-illuminated keys with good response, clear separation and labelling of keys)
Core functions Focus on core functions
Convenient use New simplified and intuitive menu structure, speaker-independent voice dialling, “fast calling key”
Premium display Best readability of display contents under all conditions
Comfortable use Convenient handling either with Bluetooth Headset or in the car through the Car Kit Comfort with inductive RF coupler and the Car Kit Bluetooth® Portable
Consumer Benefits
Polaris
Back:
Notes: STRICTLY CONFIDENTIAL

## Slide 23: Operator Benefits
Operator Benefits
  Ease of use supports more frequent employment of ARPU-generating features
  "Fast calling key" and SI voice dialling enable easy and frequent voice communication (possible additive operator service opportunities)
  The target group has a low churn
  Logo printed on the phone
ARPU drivers
Customisation Options for Operators
  Design Values
Polaris
  Addressing new customers with
  high disposable income
  Product that fulfils their needs (core features, perfect usability, premium value)
  Siemens Marketing Communication will be biased towards the Convenience Theme
  Additional segment: Addressing
  corporate channels with perfect core
  features for business users
Addressing new Market Segment
  Highly attractive premium design: very slim phone with real metal surface (brushed aluminum)
  Bar phone with excellent ergonomics
  Easy to use keypad (large, well separated keys) and screen (easily readable, large characters)
  Car Kit Comfort and Car Kit Bluetooth® solutions
  Headset Bluetooth®
  Personal Information Management (Synchronisation with PC available)
Accessories and Applications
Back:
Notes: STRICTLY CONFIDENTIAL

## Slide 24: Retailer Benefits
Retailer Benefits
Design
  Higher purchase rate due to self-explanatory product (intuitive easy-to-use menu structure)
  Extremely high sound (dual speaker) and high resolution dynamic colour display quality
  Simplicity combined with highly perceived value
  Highly attractive premium design: very slim phone with real metal surface (brushed aluminum)
  Bar phone with excellent ergonomics
  Easy to use keypad (large, well separated keys) and screen (easily readable, large characters)
Easy-to-Sell
Polaris
  Full marketing support (ATL , BTL)
  Advanced PoS Concepts
  Segment specific PoS training available
  Siemens Marketing Communication will be biased towards the Convenience Theme
  Attractive to a simplicity centric mature target group
  Excellent price/ perceived value ratio
  Additional Sell-out Potential: Highly attractive to business users
  Car Kit Comfort and Car Kit Bluetooth® solutions
  Headset Bluetooth®
  Personal Information Management (Synchronisation with PC available)
Siemens Marketing Support for Retailers
High Sell-Out Potential
Accessories and Applications
Back:
Notes: Full marketing support:
STRICTLY CONFIDENTIAL

## Slide 25: Versus the Competition
Pure UI
Pure Functionality
Pure, Premium Design
Best Ergonomics
Currently there are no Convenience phones with a comparable concept in the market. Polaris is the only phone that combines the various properties described below.
Benchmark for the different properties
Nokia 3100 & Mars
Siemens A65 & Mars
Sharp GX15 & Mars
SonyE T610 & Mars
Siemens Polaris
Benchmark
Polaris
Back:
Notes: <number>
<footer>
<header>
<date/time>
STRICTLY CONFIDENTIAL

## Slide 26
Polaris
Direct R&D-Costs
Comment :
Account: E981-0390
M0 planned 04.05.2005
(originally 31.03.05)
M1 planned 13.05.2005
M3 planned 15.04.2006
Efforts after M3: 0‘6 Mio
Platform: 1/6 of X75 Platform
1/7 of 85G Rel. 2
EGK-Factor: 85er Gen.
03/04: 1,3
04/05: 2,21
05/06: 1,9
Cost overview until M 3