## Slide 1: Phoenix “Social Life Manager” Product Status Report at S25/M2
PSR, 4th May 2005 – Confidential
M. Mildenberger (SPM), Gregor Flüge (PLT), D. Culmbacher (SPM BA)
Notes: STRICTLY CONFIDENTIAL

## Slide 2: This document is review and agreed by the extended Phoenix REA Team
Due to the PSR decision as of Oct 27, 04 all extended core team members have to commit to the content of this presentation and “virtually” sign the presentation! Please send email to SPM.
__________________ __________________ __________________
SPM PLT SPM BA
__________________ __________________
SD Q
Signed, M. Mildenberger
Signed, G. Fluege
Signed, D. Culmbacher
Signed, Z. Kirin
Signed, H. Grabas
CX75

## Slide 3: Quality Gate Rating Phoenix 1/2 Status S25/M2
CX75
Product Quality
All features are implemented and ready to test
Rear cover problems in drop test and assembly
Joystick position improved but not 100% centered
Cycling time in production is too high due to SW work- arounds
Time-to-Market
TTM can only be met with SW quality level lower than requested by QM, otherwise up to 4 weeks delay depending on incoming bugs
Reason: more incoming bugs than expected, low bug fixing rate and late assignment of additional resources
S3: 17-May-05 (no delay in Primavera)
DS: 10-Jun-05 (no delay in Primavera)
Project Quality
PD: partly missing skills in English, communication, project management and know-how about organisation
Still insufficient SW resources to improve TTM
Profitability
Project Quality
Sales Fit
Product Quality
Strategy
Fit
Time-to-Market
QG
Rating Meeting: 21-Apr-05 (update 2-May-05) PSO support: Dr. M. Assan
Notes: <number>
<footer>
<header>
<date/time>

## Slide 4: Quality Gate Rating Phoenix 2/2 Status S25/M2
CX75
Profitability
Profit +25'9€ (+8.7%, current) vs. +23‘8€ (7.7%, M1 target) based on 1'9 units and 165€ launch-CRP  positive deviation: +9%
Low confidence in Business Case due to price/volume risks
Strategy Fit
Phoenix has been upgraded (MP3 not part of initial concept)
Feature set and position are ok
Profitability
Project Quality
Sales Fit
Product Quality
Strategy
Fit
Time-to-Market
QG
Sales Fit
Current list price 179€; price risks: WE 11%, EE 10%, Americas 14%, MEA 7%, APAC 0%, China 12%
1’6 units (current ROF) vs. 1’9 units (in Business Case) vs. 1’95 units (M1)  16% volume risk
All areas: display too small
WE: Java music player does not work due to a SW problem (Java music player was not required at M1)
China: too big and bulky, feature set is fine.
Rating Meeting: 21-Apr-05 (update 2-May-05) PSO support: Dr. M. Assan
Notes: <number>
<footer>
<header>
<date/time>

## Slide 5: Comparison Business Case
CX75
  Lifecycle:
  Still M1 assumptions (06/05 – 02/06)
  Units:
  Delta: - 0’145
  M2: adjusted M1 figure (limited capacity in launch month)
  Current: PBM Input in ROF 05/05
  ASP:
  Delta: - 2€/pc
  M2: M1 figures; Current: priceline acc. QPM 04/05
  HK:
  BoM + CC still M2-values but diff. weighting due to quantities
  Cogs:
  Still M1 assumptions
  R&D:
  Delta: + 3‘2€
  M2: R&D forecast 03/05; Current: new indirect cost factors
  Marcom:
  Still M1 assumptions (3.0€/pc + 4% of T/O + € 2’5)
Deviation Analysis M2 vs. 03.05.05

## Slide 6: Proposed next steps
PD to set up crisis management team to lead the SW bug fixing process, PSR and MD board support in nominating a dedicated project leader for this task
Analyze details regarding software quality and expected return rates
Evaluate potential TTM delay / loss of volumes if software targets have to be reached
Present decision proposal to management latest end of May
PSR agrees to proposal:
yes
no
CX75

## Slide 7: Backup
CX75
Notes: <number>
<footer>
<header>
<date/time>
STRICTLY CONFIDENTIAL

## Slide 8: Measures, Responsibilities and Due Dates
CX75
Q-Gate Axis | Measure | Status | Due | Responsible
Strategy Fit | n/a |  |  | 
Sales Fit | Increase attractiveness of product: music bundle, black velvet colour | Partly done | May 15 | SPM (M. Mildenberger)
Profitability | n/a |  |  | 
Product Quality | Rear cover assembly problem solved. 100k of “old” rear covers will be assembled, additional person will secure quality in production, afterwards modified rear cover available Joystick: The identified measures have been introduced (a. joystick positioning before soldering changed b. auto assembly of keypad) but still problems. Measurements ongoing. Decision based on results. Software: Cycle time 2 seconds too long due to lots of workarounds. This will reduce capacity if not solved Sidekey: mounting in mass production difficult at the moment (conversion cost risk), Evaluation ongoing | done Open Open Open | May 11 S3 S3 | PLT (G. Flüge) PLT (G. Flüge) PLT (G. Flüge)
TTM | TTM can only be met with limited software quality. Analyse details regarding software quality and expected return rates vs. loss of volumes and present decision proposal to management. | Open | End May | SPM (M. Mildenberger)
Project Quality | See TTM |  |  | 
Other |  |  |  | 

## Slide 9: Highlights
* Headset and RS-MultiMediaCard not bundled
Key Features
Design
Accessories
Technology
Applications
  1.3-megapixel camera
  Bluetooth®
  262K colour display, 132 x 176 pixels, 1.8 inch
  Video recording and playback
  MP3 / AAC / AAC+ player *
  RS MultiMediaCard slot
  PaT via side key
  Bar phone
  High-value colour and material finish
  Timeless design with an exclusive touch
  Clearly structured keypad
Key Features
  Car Kit Bluetooth® Portable
  Mobile Music Set
  Wide range of Headsets and Car Solutions
  Tri-band (900 / 1800 / 1900)
  GPRS Class 10
  WAP 2.0
  Bluetooth®, IrDA, RS MultiMediaCard slot
  Wireless Java MIDP 2.0
  MP3/AAC / AAC +
  3D games & multiplayer games
  Printer via Bluetooth®
  Blogging Client
  Photo Editor
  Download Assistant
  Instant messaging
CX75
Update: Music bundle w/ 128MB RS-MMC and headset for an attractive price available!
Notes: <number>
<footer>
<header>
<date/time>
STRICTLY CONFIDENTIAL

## Slide 10: Multimedia without Limits
Product Idea, Target Group
Product Idea
Surprising entertainment options and multimedia features combined with efficient life management components.
  Male: Female (50:50)
  Age focus 20 - 45 years
  Low to mid income
  Focus on use for personal purposes
  They concentrate on friends & family (community-centric people) and want to enjoy life
  They are leading a turbulent and multi-faceted life juggling many activities & appointments related to their professional & personal life
  Relaxation and finding a certain balance are key requirements
  Products they own have to be surprising and give away a 'human touch'
  Image & design also have a certain importance
  Decisions are based on a mixture of design, feature and cost considerations
Product Segment
Target Group Socio-demographic Data
Target Group Behavioural Aspects
Emotion class
CX75
Notes: <number>
<footer>
<header>
<date/time>
STRICTLY CONFIDENTIAL

## Slide 13: MTA
CX75
Notes: <number>
<footer>
<header>
<date/time>
STRICTLY CONFIDENTIAL

## Slide 14
R&D Spending Phoenix
Comment :
Account: E981-0588
M0 declared 23.06.2004
M1 declared 27.10.2004
M3 planned 17.08.2005
Efforts after M3: 0‘18 Mio. €
EGK-Factor:
03/04: 2,58
04/05: 1,94
date of FC: 10.03.05
CX75