## Slide 1: Sirius “Entertainment goes outdoor” Product Status Report at S25/M2
PSR, 4th May 2005 – Confidential
M. Mildenberger (SPM), Gregor Flüge (PLT), J. Jungbauer (SPM BA)
Notes: STRICTLY CONFIDENTIAL

## Slide 2: This document is review and agreed by the extended Sirius REA Team
__________________ __________________ __________________
SPM PLT SPM BA
__________________ __________________
SD Q
Signed, M. Mildenberger
Due to a decision from last PSR all extended core team members have to commit to the content of this presentation and “virtually” sign the presentation! Please send mail to SPM.
Signed, G. Fluege
Signed, J. Jungbauer
Signed, Z. Kirin
Signed, M. Fister
M75
Signed, K. Zlatko

## Slide 3: Quality Gate Rating Sirius 1/2 Status S25/M2
M75
Strategy Fit
Feature set and position are ok
Profitability
M2: Profit +11’0€ (+7.21%) vs. M1: +24'7€ (10.1%,) based on 813k units and 200€ CRP launch price  absolute Profit deviation: -55%
Low confidence in Business Case due to price/volume risks
Profitability
Project Quality
Sales Fit
Product Quality
Strategy
Fit
Time-to-Market
Sales Fit
Launch CRP 200€; price risks: WE & EE 13%, MEA & APAC 8.5%
540k units (current demand planning) vs. 813k units (in Business Case) vs. 1’35 units (M1)  34% volume risk in BC
All areas: Keys too small, bulky appearance, proportions between display and housing is wrong
WE,EE,MEA: Capacity of MMC is too low (32 vs. 128 MB)
WE: Java music player does not work due to a problem in JAVA implementation (not required in M1).
QG
Rating Meeting: 21-Apr-05 (update 2-May-05) PSO support: Dr. M. Assan
Notes: <number>
<footer>
<header>
<date/time>

## Slide 4: Quality Gate Rating Sirius 2/2 Status S25/M2
M75
Profitability
Project Quality
Sales Fit
Product Quality
Strategy
Fit
Time-to-Market
Time-to-Market
TTM delay of up to 1.5 weeks expected due to the same reasons as Phoenix
S3: 25-May-05 (no delay in Primavera)
DS: 28-Jun-05 (no delay in Primavera)
Project Quality
PD: partly missing skills in English, communication, project management and know-how about organisation
Still insufficient SW resources to improve TTM
Product Quality
All features are implemented and ready to test
Dust on the display is not sufficient for IP54, yet
Cycling time in production is to high due to SW work- arounds
QG
Rating Meeting: 21-Apr-05 (update 2-May-05) PSO support: Dr. M. Assan
Notes: <number>
<footer>
<header>
<date/time>

## Slide 5
Comparison Business Case Current Business Case of Sirius indicates a Profit of – 1’7 (-1.2%)
M75
  Lifecycle:
  Still M1 assumptions (06/05 – 05/06)
  Units:
  Delta: +0’05
  M2: DP 04/05; Actual: PBM Input in ROF 05/05
  ASP:
  Delta: - € 17.0/unit
  M2: M1 price line; Actual: QPM 04/05
  HK:
  Increase M2 and Actual due to lower quantities (tooling invest)
  CCQ:
  Still M1 assumptions
  R&D:
  Delta: +1.2
  M2: R&D Forecast 03/05; Actual: new indirect cost factors
  Marcom:
  Still M1 assumptions (2’5 + 5% of T/O + 5 €/pc.)
Deviation Analysis M2 vs. Actual

## Slide 6: Proposed next steps
M75
PD to set up crisis management team to lead the SW bug fixing process, PSR and MD board support in nominating a dedicated project leader for this task
Analyze details regarding software quality and expected return rates
Evaluate potential TTM delay / loss of volumes in case software targets have to be reached
present decision proposal to management latest end of May
PSR agrees to proposal:
yes
no

## Slide 7: Backup
M75
Notes: <number>
<footer>
<header>
<date/time>
STRICTLY CONFIDENTIAL

## Slide 8: Measures, Responsibilities and Due Dates
Q-Gate Axis | Measure | Status | Due | Responsible
Strategy Fit | n/a |  |  | 
Profitability |  |  |  | 
Sales Fit |  |  |  | 
Product Quality | Dust on display: root cause is potentially the cushion. A new cushion will reduce or solve problem Software: Cycle time 2 seconds too long due to lots of workarounds. This will reduce capacity if not solved Joystick: Up to 40% of all joystick caps falls off after the assembly and a short time of use. Improvements are defined and will be tested until End of cw19. Joystick: 40% failure rate in customer test, under evaluation | open | May 19 | PLT
TTM |  |  |  | 
Project Quality |  |  |  | 
Other |  |  |  | 
M75

## Slide 11: MTA still shows a delivery start as agreed at M1 (28th June)
M75
Notes: <number>
<footer>
<header>
<date/time>
STRICTLY CONFIDENTIAL

## Slide 12
R&D Spending Sirius
Comment :
Account: E981-0592
M0 declared 23.06.2004
M1 declared 11.11.2004
M3 planned 17.08.2005
Efforts after M3: 0‘16 Mio. €
EGK-Factor:
03/04: 2,58
04/05: 1,94
date of FC: 10.03.05
M75

## Slide 13: Product highlights
Key Features
Technology
M75
  Siemens Protection SystemTM
  Shock, splash water and dust resistant (IP54)
  Media player (music & video)
  RS MultiMediaCard slot (card and headset bundled)
  Push and Talk (PaT)
Key Features
  Integrated 1.3-megapixel camera
  Video recording & playing
  262K colour display, TFT
  3D Java engine
  RS MultiMediaCard slot
  Bluetooth®, GPRS Class 10
Technology
  Superior outdoor bar phone
  Robust
  High value finish
  Authentic materials (metal frame and rubber protected sides)
Design
  Mobile Music Set
  Wide range of Headsets and Car Solutions
Accessories
  3D Java games and multiplayer games via Bluetooth®
  Themes, Download Assistant
  Instant messaging
  Weather forecast
Applications
Notes: <number>
<footer>
<header>
<date/time>
STRICTLY CONFIDENTIAL

## Slide 14: Entertainment Goes Outdoors
Rejoice in music and video entertainment in all circumstances with this robust phone.
  Male more than female
  Mid to high income
  Outdoor activities have a very high priority for them
  They expect robustness and reliability in their mobile devices
  They want mobile devices to fit to travel, adventure and leisure activities.
  They enjoy using mobile devices with a variety of multimedia and technologically innovative features
M-Class, Outdoor
Product Idea, Target Group
M75
Product Idea
Product Segment
Target Group Socio-demographic Data
Target Group Behavioural Aspects
Notes: <number>
<footer>
<header>
<date/time>
STRICTLY CONFIDENTIAL