## Slide 1: PSR X75 SG2 Software Status, 04.05.05 SW Platform Project Manager: Ulrike Harke SW Project Manager Minos: Stefan Miehling SW Project Manager Hydra: Flemming Mikaelsen SW Project Manager Customisation: Ulrich Meyer

## Slide 2: X75 SG2 SW Milestone status and successes
Status:
B2 Production SW for Minos and Hydra
B1+ test ongoing BT, Accessory support provided
Reached Milestones: Next Milestones according plan:
Platform Minos Hydra S25 22.07.05
M0 DS 14.10.05
S0 Next Milestones (challenge):
M1 S25 15.07.05
S2 DS 07.10.05
SIP8
Feature set:
SIP 8: B1+ test & B2 Production SW












CMMI 2,75 on risk:
SWI targets progressing
- 75% Level 2 & Level 3 ‚in use‘ reached - Assessment in 06/05 to be discussed

~4w

01.04.05 => 28.04.05



## Slide 3: X75 SG2 SW Milestones
MR1
05
09
08
06
DL
CA
Risks
07
10
C3
11
DoJA
I-Mode
Orange Help/ Homescreen
Infusio
Video/ Audio streaming Audio progr. download
DoJa/Java/AppCnt/UIOS
AppMsg/MMUI
OBSV
C3
+ 4 weeks
DS
Planned Stabilization
~ 3 weeks
Systemtest based on IDB
AS
S25
Challenge+ 3 weeks
Challenged new Milestones Platform
Analog
Audio
BasicMMI
C3
75 %
C3
C3
C3
~ 7 weeks
~ 8 weeks
~ 6 weeks
C3
~ 4 weeks
~ 5 weeks
ST2 test duration
MR2
VF Livecast
VF Classlib (as M1, without CR 260)
ATI last delivery
~ 12 weeks
Operator Approval Plan
Challenge+ 3 weeks

## Slide 4: X75 SG2 SW: Countermeasures to reduce risks for S25/DS

## Slide 5: High priority CR’s
CR number | Description | Current status
CR 00177 | 10 profiles for Consortia Initialisation | Commited for Rel1
CR 00178 | VF UE Compliance CR | Commited for Rel1
CR 00260 | VSCL | Cannot be committed due to JAVA is impacted (800 hours)
CR 00302 | Translations of second level of Media Folder | Can be committed for Rel1 with restriction that it will be stopped if there is a risk for stabilization of DS software.
CR 00196 | Customer mini monitor (no open bus) | Committed for Rel1
CR 00135 | Support alpha transparency of PNG format for icons | Shift to Rel2 (X85)
CR 00123 | Augmented Reality API for Java | Shift to Rel2 (X85)
CR 00516 | Show DRM details in File Attributes screen | Committed for Rel1

## Slide 6: Measures to secure S25
Strong cooperation between SW and Systemtest
Provision IDB SW to systemtest
Feedback about test results of Sytemtest based on IDB SW & Release Notes
IOT starting already
Daily status quo and prio decision between SW and customers
Focus in the past: B1+ test, B2 production
Focus in the future: Ensure early type/operator approval for Systemtest (ST1/ST2)
Monitoring of outstanding deliveries weekly based
Adaptation of IP plan
Incorporation of the adapted integration scenario
Insurance of weekly SW delivery cycle
Definition and installation of Interface change process
Provision of Lintable SW on CDB and IDB
Improvement of CM setup (Mch, Bejing)
Installation of integration camps and increased onsite support by dedicated team members
BT, Accessories, MM
Additional camp in case of necessity
Additional budget and ressources to ensure MM timeline
Onsite support of supplier e.g. PacketVideo in Aal

## Slide 7: VF 11/05
  Java
    VF Class Libraries
      2 class libraries (com.vodafone.util, com.vodafone.lcdui) as M1
      2 class libraries as CR 260 (com.vodafone.system, com.vodafone.midlet): evaluation continued with low priority to ensure TTM
      Effort CR 260
      C_JAVA: Effort: 800 h; 20000,-€ additional costs AppIDC: Effort: 84h Browser: Effort: 40h AppMsg: Effort: 32h; 2100,-€ additional costs PIM: Effort: 99h no other components affected