## Slide 1: Minos Product Status Report, 04.05.2005
Core team Minos SPM: Hombeck, PM: Olivan, PLT: Feldhoff, Barner, BA: Teistler, BO: Dankesreiter
– Confidential –
Copyright © Siemens AG 2005: Copying of this document and giving it to others and the use or communication of the contents thereof, are forbidden without express authority. Offenders are liable to the payment of damages. All rights reserved in the event of the grant of a patent or the registration of a utility model or design.

## Slide 2: Minos – three threads which endanger delivery start
Minos
  SGLight
  versus SG2
  resources
Topic
  Due to SW resource prioritisation a DS delay risk of three weeks is pending. Further SGLight resource demand will jeopardize SG2 timeline
Description
Impact
  HW B1+ qualification
Topic
  Due to late SW availability (January SW budget restrictions) full HW qualification is not possible in M1 timeline. Antenna stabilization may imply further DS delay
Description
Impact
  DS not before: 29.09.2005
1.
2.
3.
  SG2 SW Multimedia
Topic
  Due to SW budget restrictions from January (and corresponding delay of Multimedia features) the DS is currently delayed by 3-4 weeks
Description
Impact
  DS not before: 07.10.2005
  DS not before:
  07.10.2005

## Slide 3: HW B1+ qualification : Critical Path from HW type approval perspective
Project Status, critical path from HW approval perspective:
- SW maturity for B1+ run (some major topics) delayed by 10 weeks due to SW-budget restrictions and late ATI delivery
- Delay of B1+ testability shifts B2 tapeout and accordingly Type Approval (AS)
- 2 weeks delay of AS directly delays DS by 2 weeks (certification)
Major threats:
- B2 tape out on high risk due to self interferer problem
=> solution mandatory for B2 tapeout
Measures to prevent additional delay of DS
- task force installed to solve self interferer problem
=> To avoid further delay self interferer problem has to be solved until 10.05.05
Minos
Status M1:
Current
Status
03.05.05:
Minos

## Slide 4: Actual Topics and Business Case Impacts
Minos
  Time-to-Market
Business Case Impacts
  September quantities and up 1/3 of October quantities (250 K) are on high risk due to SW delay -> considered in BC
Description
Impact
   - 10 m EUR
  EBIT
  EBIT margin %
   - 1,6 %
  RND budget
  Due to adjustment of indirect R&D costs (overall factor has been raised by 25%) the overall Minos R&D costs have been raised by 11% -> considered in BC
   - 6 m EUR
   - 1,3%
  Volume
  Product still not listed at TMO and VF: 300k (10%) volume risk if product will be not listed by both key customers VDF and TMO globally -> not considered in BC, risk only
   - 9 m EUR
   - 1,7%
  Piano black
Actual topics
  New colour samples of preferred colour (Sales & customer) received. Qualification ongoing
Description
  TMO
  Minos is shortlisted and is part of the final selection process (inputs from the countries). Final feedback expected for latest end of next week
  Orange
  Product officially listed as Orange Q4 signature product
  VF
  Not listed as of today, no positive feedback from account managers on name / positioning change

## Slide 5: Comparison Business Case
Deviation Analysis April vs. March
Minos
  Lifecycle:
  Delivery Start shifted by 3 weeks to 07.10.05, any further delay will strongly endanger Christmas business and commercial success of project
  Units:
  Quantities reduced by 255k because of DS delay, assumption: only listed by one additional key customer (TMO or VF)
  ASP:
  Decrease of ASP by 2,40€ because of DS delay and Q2/FY06 CRP reduction from 170€ to 168 as decided in last QPM.
  HK:
  Further BOM reduction potential of up to 0,30 Euro
  -> Recalculation at S25
  Cogs:
  No change
  R&D:
  Due to adjustment of indirect RND costs (overall factor has been raised by 25%) the overall Minos R&D costs have been raised by 6’0 Euro
  Marcom:
  No change