## Slide 1: Robin “Music to the max “ Product Status Report at M0, May 4, 2005
SPM J. Hantschel; PLT K.-P. Bräuherr; SPM BA M. Aicher

## Slide 2: This document is review and agreed by the extended Robin REA Team
__________________ __________________ __________________
SPM PLT SPM BA
__________________ __________________
SCM QM
Signed, Joerg Hantschel
Signed, W. Bollin
Signed, Rolf Gillitzer
Signed, Klaus-Peter Bräuherr
Signed, Markus Aicher
Due to the PSR decision as of Oct 27, 04 all extended core team members have to commit to the content of this presentation and “virtually” sign the presentation! Please send email to SPM.

## Slide 3: Quality Gate Rating Robin 1/2 Status M0
Profitability
Project Quality
Sales Fit
Product Quality
Strategy
Fit
Time-to-Market
Sales Fit
174€ ASP, 195€ launch price, 150€ EOL; Price risks: WE: Robin cannot be sold without video telephony, EE -25€, MEA & AIP no price risk
2’2 units, volume risks: WE & EE >50%, MEA 90%, AIP 97%
WE, EE: Missing video telephony is a must, design is ok but not exceptionally (DAT results not 100% available)
AIP: 2Mpix camera is preferred
MEA: Little difference to S75 (UMTS is not important for MEA)
Profitability
Profit -24.7€ (-6.4%, current); target is not clearly defined
BC improvements vs. M: DS moved forward by 2 months, BOM reduced by 10€, dollar exchange rate has dropped
Strategy Fit
Very strong impact on portfolio, as it is the first SAG UMTS phone below CRP 200€
Fit to position in defined music theme: mp3 player, AAC++, radio, stereo headset, fast music download due to UMTS, dedicated music keys
15 months lifecycle
Large market size, growing market, addressable market within price class: 83'0 units, market share: 3%
QG
Rating Meeting: 28-Apr-05 (updated 3-May-05) PSO support: Dr. M. Assan
Notes: <number>
<footer>
<header>
<date/time>

## Slide 4: Quality Gate Rating Robin 2/2 Status M0
Profitability
Project Quality
Sales Fit
Product Quality
Strategy
Fit
Time-to-Market
Time-to-Market
High confidence due to commitment of all PD faculties to time schedule
M1: 23-Jun-05
S25: 15-Dec-05
DS: 17-Mar-06 (2 months earlier vs. roadmap)
S4: 28-Apr-06
Project Quality
Risk management plans to be updated / finalised for PD and Rea Team
Product Quality
Some license issues open and Qualcomm source code not yet available
QG
Rating Meeting: 28-Apr-05 (updated 3-May-05) PSO support: Dr. M. Assan
Notes: <number>
<footer>
<header>
<date/time>

## Slide 5
Comparison Business Case Compared to M-Alpha the M0-BC shows an EBIT improvement of 28,1 Mio€

## Slide 6: Consequences out of Sales Feedback
Implementation of video telephony
  ASP: 168 €/unit TTM + 6 weeks
  EBIT: -44´8 € (-12% of T/O) BOM + 4€ /unit
  Deviation to current M0-BC: -20´1 € (-5,6%) Size app + 5 mm length
  Price line – 25€/unit
  ASP: 149 €/unit
  EBIT: -67´2 € (-21,6% of T/O)
  Deviation to current M0-BC: -42´5 € (-15,2%)
  Volume decrease (lifecycle) – 50%
  ASP: 174 €/unit
  EBIT: -26´3 € (-13,6% of T/O)
  Deviation to current M0-BC: -1´6 € (-7,2%)

## Slide 7: Measures, Responsibles and Due Dates
Q-Gate Axis | Measure (Description of Measure) | Status | Due Date | Responsible
Strategy Fit |  | open |  | 
Sales Fit | Meet with major countries and customers to explain Robin and get feedback on price, volume, features | open | June 3, 2005 | Hantschel
Profitability | DTC Work shop Evaluate cobranding with e.g. Bose,.. | open | May 10,2005 May 20,2005 | Bräuherr Hantschel
Product Quality |  | open |  | 
TTM |  | open |  | 
Project Quality | update risk management in PD and REA | open | done | Bräuherr Hantschel
Other |  | open |  | 

## Slide 8: Decisions Proposals in case of red Q-Gate
A.) Go ahead with project
Risks on price line, volumes to be clarified with Sales
Further improvements planed on BC
B.) Stop the project:
Resources available for other projects
No entry level 3G terminal for 2006
We propose decision:
X
A
B

## Slide 9
Backup

## Slide 10: Milestones
M-alpha 16.3.2005
M0 cw 17 2005 (April)
S0 cw 20 2005 (May)
M1 cw 25 2005 (June)
S25 cw 50 2005 (December)
PS cw 8 2006 (February)
S3 cw 9 2006
DS cw 11 2006 (March)
S4/M3 cw 17 2006 (April)

## Slide 11: Product Profile
Main
Competitors
Key operator benefits
Value Proposition
Key end user benefits
Highlights
Main differentiation within MP
portfolio
Business
Positioning
Overview
MID
HIGH
EMEA
LAM
NAM
APAC
• UMTS: SE K600, SE V800, Motorola E1060
Music: SE W800i, T-mobile SDAmusic, Motorola E398, Samsung i300,
Samsung X800
• Fully enabled music phone for UMTS Market
DRM phase 1
Downloads from Operator Portal (e.g. Music files, video clips,…)
Music in Background (downloading, playing games, writing SMS, …)
• Music to the max – know the true promise of high speed music download and
music listening.
• Easy access to music (dedicated music keys)
Music Player (with FM Radio (RDS) and mobile phone in one device
Easy file transfer (USB cable bundled, USB high speed standard)
Music in Background (play games, write SMS while listening to music) tbc
• Fast download of content (UMTS)
Dedicated music keys
TransFlash card slot & Stereo Headset bundled
Excellent audio and visual performance via outstanding design and great
music experience supporting music related UMTS NOP services
Launch: March 2006
Lifecycle 15 months
Launch Price: ~195 €
ASP: ~174 €
Volume: 2,3 millions
Consumer Segment: EXPRESSIVE CONNECTION
User Profile: Unisex, Age: under 35, low to mid income, students, professionals
LOW

## Slide 12: Competition - Robin Competitor Overview
Source: Internet research
Competition
 | Sony Ericsson K600 | Sony Ericsson V800 | Motorola E1060 | T-Mobile SDA Music | Samsung i300 | Motorola E398 | Samsung X800 | Sony Ericsson W800i
Status: 21.04.05 |  |  |  |  |  |  |  | 
Network | UMTS / Tri | UMTS / Tri | UMTS / Tri | Tri | Tri | Tri | Tri | Tri
Street Price [€] (Launch) | n.a. / Q3 05 | 800 / Q4 2004 | n.a. / Q4 05 | 370€ / Nov 04 | n.a. / Q4 05 | 370 / Q3 04 | n.a. | n.a. / Q2 05
CRP [€] (Launch) | n.a. | 240 | n.a. | tbc. | n.a. | 140 (Q2 06) | n.a. | n.a.
Dimension [mm] | 104x45x19 | 102x48x26.3 | 107x53x21 | 108x47x20 | 113x48x20 | 108x46x20.5 | 88.5x45x23.5 | 100x46x20.5
Weight [g] | 105 | 128 | 125 | 100 | 130 | 110 | 89 | 99
Display | 256k | Dual 256k/64k | 256k | 64k | 256k | 64k | 256k | 256k
Display resolution | 176x220 | 176x220 | 240x320 | 176x220 | 240x320 | 176x220 | 176x220 | 176x220
GPRS Class / EDGE | 10 / − | 10 / − |  /  | 10 / − | 10 / − | 10 / − |  / − |  / −
PaT / IMPS / Email | − /  /  | − / /  |  /  /  | − / − /  | − / − /  | − / /  | − / − / − | − / / 
Camera / Flash | 1,3 Mpix /  | 1.3 Mpx. / tbc. | 1,3 Mpix / − | VGA / tbc. | 1,3 Mpix /  | VGA /  | 1 Mpx. /  | 2Mpx. / 
Video play/record/stream |  /  / n.a. |  /  /  |  /  /  |  /  / − |  /  / n.a. |  /  /  |  /  / tbc. |  /  / 
Radio / MP3 / AAC |  /  / − | − /  / − | − / / − | − /  /  | − / /  | − /  / − | − / / − |  /  / −
User Memory [MB] | 37 | 7 | 32 | 32 | 3 GB HDD | 5 | 88 | 38
External Memory | n.a. | Memory Stick | TransFlash | Mini SD | TransFlash | TransFlash | TransFlash | Mem. Stick Duo
IrDa / BT / W-LAN |  /  / − |  /  / − | − / / − |  /  / tbc. |  /  / − | − /  / − | − /  / − |  /  / −
Standby Time [h] | 240 | 240 | 170 | 140 | n.a. | 230 | n.a. | 400
Talk Time [min] | 480 | 600 | 260 | 240 | n.a. | 560 | n.a. | 540
Battery [mAh] | Li−Ion (BST 33) | 900 | n.a. | 1050 | n.a. | 830 | n.a. | 900
Extras | Video telephony | MP3,WAV,Midi files supported, Video telephony | Video telephony | OS Windows mobile 2003 | Windows OS, Dual Speaker, Bluetooth stereo headset | Stereo headset, Stereo Speakers | Dual Speaker, External music Hotkeys | Up to 30h music play time, good PC Software
UMTS
UMTS
UMTS
MUSIC
MUSIC
MUSIC
MUSIC
MUSIC

## Slide 13
Robin
 |  | Siemens Robin | Sony Ericsson K600 | Motorola E1060 | Motorola E398 | T-Mobile SDA Music | Samsung i300 | Samsung X800 | Sony Ericsson W800
 | CRP [EUR] / Launch | 195 / 03/06 | n.a. / Q3 05 | n.a. / Q4 05 | n.a. / Q3 04 | n.a. / Q4 04 | n.a. / Q4 05 | n.a. / Q2 05 | n.a. / Q2 05
 | Dedicated music keys |  | − | − | − |  | − |  | −
 | Headset / branded HS |  / tbc |  / − |  / n.a. |  / − |  / − | BT stereo / n.a. |  / n.a. |  / 
 | FM Radio / Recording |  / tbc |  / n.a. |  / − | − / − | − / − | − / − | − / − |  / n.a.
 | Battery performance | 1000mAh | 900mAh | 1000mAh | 12 h playtime / 830mAh | 1050mAh | n.a. | 700mAh | 30 h (phone off) / 15 h (on) / 900mAh
 | Exchangeable memory (card slot) | TransFlash | − | TransFlash | TransFlash (64MB bundled) | Mini SD (128 MB bundled) | Trans Flash | TransFlash | Memory Stick Duo (512MB bundled)
 | PC sync software |  |  |  |  |  |  |  | 
 | USB highspeed / Data Cable |  /  (bundled) | n.a. /  | n.a. /  | − /  | − /  |  /  (bundled) | − /  |  /  (bundled)
 | Bluetooth / IrDa |  / − |  /  |  (class 2) / − |  / − |  /  |  /  |  / − |  / 
 | Music in Background |  |  | n.a. |  (no games) |  |  | n.a. |  (tbc.)
 | Improved audio quality (e.g. HQ loudspeaker) |  (HQ loudspeaker) |  | n.a. |  (dual speaker, surround sound) | − | Dual Speaker, 3D Sound, Digital Power Amp | Dual Speaker |  (headset, equalizer,…)
 | Lightning concept (phone & music mode) | − / e.g. phone & music mode | − | n.a. | Rhythm Lights & dynamic light effects | − | n.a. | n.a. | n.a.
 | Partnerships (Co-Branding) | − / e.g. Bose, Sennheiser, … | − | − |  (Magix Music Maker) | − |  (Windows Mobile) | − |  (Walkman)
 | Sufficient memory |  (72 MB internal) | − (37 MB internal) | (32 MB internal) | 69MB (5 MB internal) | >128MB |  (3GB HDD) |  (88 MB internal) | 550 MB (38 MB internal)
 | Technology (UMTS) |  |  |  | − | − | − | − | −
 | High value finishing |  |  | − | − | − | − | − | −
 | Small & slim footprint | 112x47,5x19 | 104x45x19.2 | 107x53x21 | 108x46x20.5 | 108x47x20 | 113x48x20 | 88.5x45x23.5 | 100x46x20.5
Music Related
Others
Differentiation to top competitors (Status: 04/2005)

## Slide 14
Robin
Direct R&D-Costs
Comment :
Account: E981-0713
M0 planned to be declared 04.05.05
M1 planned 24.06.2005
M3 planned 30.06.2006
Efforts after M3: 0’57 Mio. €
EGK-Factor:
04/05: 1,39
05/06: 1,39
Date of FC: 20.04.2005 (M0)
Cost overview until M 3