## Slide 1: Swift “Slim&Brilliant“ Product Status Report, May 5, 2005
SPM A. Hauenstein
SPM BA D. Stähler

## Slide 2: Key Features
Area for Moodboard picture 1
Area for Moodboard picture 2
Area for Moodboard picture 3
Area for Moodboard picture 4
  Slim slider with real metal finish (slimness: 16.3 mm; brushed aluminium)
  Very bright QVGA Display for optimal indoor & outdoor readability, 262K
  1.3 megapixel camera with improved LED flash; video play & recording, streaming and progressive download
Key Features
Swift
Notes: STRICTLY CONFIDENTIAL

## Slide 3: Highlights
  High value slider design with metal finish (brushed aluminium)
  Semi-automatic slider mechanism
  Very slim (16,3 mm) and compact
  Highly ergonomic keypad
  Community services (e.g. blogging, my photos online)
  Preinstalled video/audio clips, video ring tones
  Music synchronisation & visualization
  (Stereo) headsets
  BT headsets
  Range of Car Kit Bluetooth solutions
  Data Cable USB
  Travel Charger, Car charger plus
  Music cable
Design
Applications
Technology
  Triband (900/1800/1900)
  QVGA display, 2.0 inches, 262K
  GPRS/EDGE
  1.3 megapixel camera, LED flash
  Video play, record, stream, download
  MP3, AAC, AAC+, AAC++
  Unified presence enhanced phone book, IMPS, PaT
Accessories
Swift
Highlights
Notes: STRICTLY CONFIDENTIAL

## Slide 4: Quality Gate Rating Swift 1/2 Status M0
Profitability
Project Quality
Sales Fit
Product Quality
Strategy
Fit
Time-to-Market
Sales Fit
Positive Design Acceptance Test.
129,31€ ASP, 100€ EOL
Volumes readjusted to 2,5’ units (before 3,3’ units)  therefore no volume risk is seen.
Positive feedback from APMs. Confidence Level is high.
Profitability
- 19’2€ (- 5,9%, current) vs. +24’5€ (+7,5%, target)
Confidence in correctness of figures, no confidence for reaching target profit
Strategy Fit
Lead product of the key product family in mid-end.
Combination of talk/standby time with other use cases may result in lower and potentially problematic levels of battery life.
Several accessories are highly endangered due to side position of I/O connector; BT-stereo HS is endangered due to missing Gimmick chip.
Addressable Market: 64’93 units, 3,9% market share
QG
Rating Meeting: Apr 8, 2005 PSO support: B. Pfeifer
Notes: <number>
<footer>
<header>
<date/time>

## Slide 5: Quality Gate Rating Swift 2/2 Status M0
Profitability
Project Quality
Sales Fit
Product Quality
Strategy
Fit
Time-to-Market
Time-to-Market
DS planned for March 06 highly endangered (risk up to 3 months) due to typical cycle time of 12 month and missing SW planning (SW - M0 in June 05)
Project Quality
SW Estimation Workshop not yet done due to overall SW situation
Primavera Plan risk due to open input on SW plan
Product Quality
SW Milestones are not aligned.  therefore also the ST planning is open.
Antenna performance in closed condition (900 MHz) does not meet FBT requirements (-1,5dB)
Missing experience with Glued 12er keypad: problems are expected in production, lifetime and service.
There’s only a single source for battery.
QG
Rating Meeting: Apr 8, 2005 PSO support: B. Pfeifer
Notes: <number>
<footer>
<header>
<date/time>

## Slide 6: Swift - Comparison Business Case The current Business Case shows a profit of -19’2 EUR or -5,9% of Turnover
Swift
* BoM figures w/o variant adder (2% of BOM), but VA included in HK position
Analysis
  „Fast track“ model; no M-Alpha milestone
  Volumes cover the regions EMEA, LAM, APAC
  Launch price at EUR 155,- Phase out price EUR 100,-
  Return Rate: 10,08%; Cost per Return: 42,95 €
  R&D: Direct R&D costs of 12,5m EUR, plus ‘direct platform costs‘ of 10,8m EUR considered (1/6 of X75/85G SG2 Rel.1 and 1/7 of SG2 Rel.2).
  Marcom: push 5€ per unit. This considers Swift as lead product of the C class until final budget decision. If Swift than won‘t longer be the lead product, reduction of push budget by 2€ per unit = savings of 5‘0€
  EBIT of -19,2m EUR or -5,9% of turnover.

## Slide 7: Key-parameters / input for the Reverse Calculation Product: Swift
PRC | Development (direct) | € 23’2
 | Marketing (direct) per unit sold | € 10,91
 | Return rate | 10,08%
 | Cost per return | €42,95
 | Return costs per unit | € 4,33
Manu-factur-ing Costs | Ø Manufacturing Costs | € 91,23
 | Conversion Costs | € 7,73
 | Ø BOM | € 77,58
 | BOM price decrease over lifecycle | 10,0%
 | Variant Adder | € 1,55
 | Licenses | € 4,37
TCG | Target Cost Gap | € -43’702
 | Target Cost Gap per Unit | - € 13,36
General | Launch date | 03/06
 | End of Life | 05/07
 | Positioning | mid tier
T/O | Units | 2’530
 | Launch price | € 155
 | EOL price | € 100
 | ASP | € 129,31
 | Price decrease over life-cycle | -35%
Profit | Target Profit | € 24’536
 | Target Profit in % of T/O | 7,5%
OH I | Administration in % of T/O | 1,2%
OH II | Development (indirect) in % of Development (direct) | ~100%
 | Marketing (indirect) in % of T/O | 4,0%
 | Selling Expenses in % of T/O | 5,0%
 | SCM Costs in % of T/O | 2,0%
 | Other GOGS in % of T/O | 1,3%
Analysis
  Negative EBIT: € -19‘166 = -5,9%
  Check all cost positions, Revise NES before M1
Swift

## Slide 8: Swift – Business Case The actual Business Case Swift shows a Profit of -19,2m EUR (-5,9%)
Swift

## Slide 9: Decisions Proposals in case of red Q-Gate
A.) Go ahead with project
Partial M0 declaration (all departments except PD SW and dependents)
Continue working on S0 and M1 work packages
New review (incl. Q-Gate) as soon as full M0 maturity reached
Apply measures as on separate chart (see: backup)
Review impact of SW M0 delay: worst case up to 3 months delay
B.) Stop the project:
Lead product for mid-end product family (Swift, Ibis, Hummingbird) would be missing, therefore dropping more than 6 mill. units volume.
Loss of 96.3 mill€ sales margin for Swift only
We propose decision:
A
B


## Slide 10: Backup: Measures, Responsibles and Due Dates
Q-Gate Axis | Measure (Description of Measure) | Status | Due Date | Responsible
Strategy Fit | Consolidated and regular update of power management progress for the platform. |  | ongoing | Hohenleitner
Strategy Fit | 1) Evaluation of alternative accessory concepts 2) CR for SW solution in phone has to be confirmed and implemented | open | April, 29 | Fischer
Profitability | Cost reduction Workshop | closed | April, 18 | Stähler
Profitability | Double check volumes/Prices | closed | April, 18 | Hauenstein
Profitability | Doublecheck Marketing spendings | started | April, 18 | Stähler
Profitability | separate platform cost from R&D cost | closed | April, 18 | Stähler
Profitability | Re-negotiation of BOM with suppliers (negotiation success) | open | April, 29 | Dunzel
Profitability | Doublecheck conversion costs and location split | open | April, 29 | Macura
Product Quality | Align SW milestones with project | open | mid June | Kockmann
Product Quality | check antenna performance at B1, B1+, .. | open | ongoing | Kockmann
Product Quality | check resources for RDP (e.g. keypad) | open | April, 29 | Kockmann
TTM | push forward HW timeline and align with SW timeline as soon as available |  | ongoing | All
Project Quality | SW planning with detailed plan available | open | mid June | Hohenleitner

## Slide 11: Backup: Timeline impact for Swift
Swift
(base plan)
M0 = 03/05
S0 = M04/05
M1 = 05/05
Swift
(estimated status)
M0 = M06
M1 = M 08/05
S0 = 06/05
E 03/05
E 04/05
E 05/05
E 06/05
E 07/05
E 08/05
E 09/05
E 10/05
E 11/05
E 12/05
E 01/06
E 02/06
E 03/06
DS= 03/06
DS = ?
?