## Slide 1: Artemis Basic Community Phone Product Status Report at DS, 19.1.05
M. Hübler, V. Greger, SPM / M. De Vries, SPM BA / Zhu Yu, PM / PL-T
– Confidential –
Copyright © Siemens AG 2005: Copying of this document and giving it to others and the use or communication of the contents thereof, are forbidden without express authority. Offenders are liable to the payment of damages. All rights reserved in the event of the grant of a patent or the registration of a utility model or design.
Notes: Product-approach to be named

## Slide 2: This document is reviewed and agreed by the extended Artemis REA Team
__________________ __________________ __________________
SPM PLT SPM BA
__________________ __________________ __________________
Sales SCM QM
Michael Hübler / Vinzenz Greger
Christine Zhu
Marjolein De Vries
Kerstin Lohmann
Cai Yu (Mike)
Britta Hentges

## Slide 3: Quality Gate Rating Artemis 1/2 Status DS
Profitability
Project Quality
Sales Fit
Product Quality
Strategy
Fit
Time-to-Market
Sales Fit
Launch Price 58€ (CRP); 50€ ASP.
Pricerisk up to 10€ seen by sales.
Volume: 3'2 units (current, acc. to ROF) vs. 4'2 units (M1) -> decrease of 23,8% (= 1'0 units).
Positive/neutral feedback from regions.
ROF insufficiently backed by order entry.
Profitability
'-0,86% (= -1'38 current) vs. 2,5% (= 4'0€, target) (@M1 7'9 = 3,6%)
CoC increased by 1€ due relocation of production
Low confidence to BC due to high pricerisk
Strategy Fit
Product as defined
QG
Rating Meeting: January14th, 2004 PSO support: G. Blecher
Notes: <number>
<footer>
<header>
<date/time>

## Slide 4: Quality Gate Rating Artemis 2/2 Status DS
Profitability
Project Quality
Sales Fit
Product Quality
Strategy
Fit
Time-to-Market
Time-to-Market
Jan 14th (current) vs. midth of January 2005 (target)
S4: Beginning of February
Product Quality
GCF fieldtrial not finished, therefore GCF certification not registered.
DS approval will subsequently only be accepted for retail variant.
Project Quality
Risk management plan not available but no major risks seen by SPM
QG
Rating Meeting: January14th, 2004 PSO support: G. Blecher
Notes: <number>
<footer>
<header>
<date/time>

## Slide 5: Measures, Responsibles and Due Dates

## Slide 6: Decisions Proposals in case of red Q-Gate
A.) Go ahead with project
3’2 units / Revenue:160’3 / Profit-1’4 / Sales Margin: 32’6
AIs
Deliver to retail market only (until GCF is approved).
Further AIs as listed on previous slide (countermeasures for improving BC as shown)
Provide update within S4-presentation  Hübler, Beginning of February
B.) Stop the project
We propose decision:
X
A
B

## Slide 7
Backup

## Slide 8: Comparison Business Case The actual Business Case indicates -1’4m EUR Loss
  Lifecycle:
  With delivery start in January’05 and phase out in April’06 lifecycle is 16 months.
  Units:
  Due to the current order situation life cycle quantities were reduced by 1’0 units from 4’251 down to 3’205 with a regional split of 76% EMEA, 17% APAC and 7% LAM
  ASP:
  Launch price of € 58 and phase out price of € 45 leads to ASP of € 50 over LC.
  HK:
  BoM: Contrary to M1 implementation of low cost display is not realizable, but the BoM increase has mostly been compensated by additional savings/negotiation successes compared to M1. However due to the volume decrease the BoM has the tendency to rise.
  Conversion Cost (€ 4.84): compared to M1 conversion costs went up by € 1.04, which is based on a revised production site split indicated by GO (SSMC 17%, KLF 47%, Flex HUN 19%, MAN 7%)
  Licenses (€ 0.33)
  CCQ:
  Service costs are calculated out of Return Rate of 5.5% and service costs per return of € 45.49.
  R&D:
  R&D budget includes € 1’7 direct project costs and € 1’7 indirect costs.
  Marcom:
  MarCom based on revised budget indication from S&M (€ 1.5 per unit sold plus 1% of T/O plus € 1’0 HQ budget).
Deviation Analysis M1 vs DS
Artemis
Notes: <number>
<footer>
<header>
<date/time>

## Slide 9: Measures for improving sell-through for Artemis
Identify root-cause for deviation between M1-planning and current forecast.
  RHQs were asked to comment situation (11.1.). RHQ asked countries. Answer is pending.
  Analyze situation (Hübler / Weber / Breen)
Push Artemis sell through
  Newsletter was sent again for getting more attention (12.1.)
  External training planned for A-Class including presentation of
    New A-Class Marketing-concept (Design / Easy-to-use)
    Focus on customer benefits vs. features
    Showing examples for value-selling
    Visit some RHQ planned for testing/discussing impact.

## Slide 10: Status RU Artemis (18.1.05)
Coverage RU-plan:
Jan: 37,7k orders vs. 71k planned  53%
  Orders / to be delivered in Jan:
  Bangladesh 1,5k
  Arabic 3k
  Greece 1,2k
  Turkey 9k
  Russia 20k
  White Russia 3k
  SUM 37,7k
Feb: 245 (ROF/DSB) vs. 300k planned  82%
RU-phase

## Slide 11: Updated LC-Planning

## Slide 12
Product Profile - Artemis Basic Community Phone
Consumer Highlights:
Offer a phone with ease of use, high quality and attractive price.
Value appearance through attractive design and color display
Finishing and material helps to satisfy the need for durability and reliable quality
Source: PDM/MM/BA
Against Competition:
Competitive bundle of actively used features (SMS, EMS, WAP…)
Low price point for price conscious target group
Valuable design for entry level
Color Display
Triband
Operator Benefits:
  Artemis offers a color display at a very attractive price point.
  SMS / EMS, WAP
Positioning / Brand:
Basic Community Phone / Simply Colorfull
Mission: Gain further market shares in low-end (saturated markets)
Differentiation within MP:
  To lower products: Color-display, WAP
  To higher products: No MMS, display…
  To Libra: More conservative design. Price.
Business:
  Volume: 3’2
  ASP: 50€
Notes: To be discussed with SM
Product-approach to be named

## Slide 13: Artemis and Libra
External reasoning:
128x128, 64k will be mainstream for successful low end colour (launch €65- €75)
Nokia 2600 to reach 55€ by Q3 FY05. Libra’s new design, the considerably smaller size and the tri band option should allow for a €5 mark-up even with the smaller screen
Internal reasoning:
Equilibrated positioning between A57 and Pegasus supports the launch price
Libra’s new designs should allow a 10-15% mark-up compared to Artemis
Libra has to achieve No 3-4 market position in order to realize ~800k volume
Planning: 1.000k (Q3)
Nokia 2600
Siemens Libra
Dummy
Sagem myX 3-2
Motorola V 150
101x80
4k CSTN
Tri band
Basic organizer
SMS/EMS
4 way navi.
16 poly
128x128,
65k
MMS
Exch. Cover
MMS
Integr. handsfree
Voice dial
Data cable
128x128
Spreadsheet
Dual band
No poly
Dual band
96x65
Dual band
No organizer
107.6x46x20.3
Q4 FY04,
€55
Price range
€65-€75
100x45x21
Q1 FY04
€58
82x43x20
Q1 FY04
€55
100x44x18
Q3 FY05
€58
Libra
Libra to Pegasus
+MMS
+IrDA
+data cable
+128x128
+64k
Internal positioning
Artemis to Libra
+new design
A57 to Libra
+4k CSTN
+101x80
+Tri band
+ new design
+ basic organ.
Expected competitor
positioning
2600
V150
MyX3-2
€17
€5
€11
Size
Launch
Exp.Q3
CRP
(€)
70
60
50
40
80

## Slide 14
MTA Artemis Status 19.1.05
Due to low complexity of project (only new color / smaller flash / no MMS, no Java) only M1, S3/DS and S4 will be declared.
Notes: <number>
<footer>
<header>
<date/time>