## Slide 1
A60 Ramp Down – M4-Declaration MD Product Status Review
Wed, 19th January, 2005
COM MD PBM Doris König / Thomas Teistler
– confidential –

## Slide 2
SCM
CCQ
Sales
AD
PM
KLF/MUC
Manaus/LAM
Flextronics
*no official Team member,
no participation to any
team meetings
LCM - life cycle manager
A60 Ramp Down – Team
LCM (Koeller)
MM (Abreu)
S OP BO (Cadeddu)
PP (Lewitzke)
GO6 (Umland)
BO (König)
PM (Bojko)
BA (KPM) (Teistler)
CCQ BA SCM (Wienen)
person* informed
GMM (Herrmann)
Brzuskova*

## Slide 3
Last production 03/05 in Manaus/Zala
Last deliveries 03/05
977k € for KLF/MAN/ZALA/GDL
TARGET
VARIANTS
VOLUME
E
O
L
A60 Ramp Down – Strategy Ramp down target 977k € (Set by PSR 19.01.2005)
Lifecycle volume planned for A60: 2’5 Mio units (M3)
Current planning: 4’4 Mio units
Ramp Down Volumes (11/04-03/05): 945k Units
Remaining deliveries (01/05-03/05) : 434k Units
53 variants have been built up
Two colours: stone, and the special colour silver for LAM

## Slide 4
A60 Ramp Down – Sales Volumes Committed M4 Volume EMEA and LAM
Status
Periode
Regions
K Units
A60 EMEA
11/04 till 03/05
659.100*
A60 LAM (Brazil/ Mercosur/ Merconorte)
11/04 till 03/05
285.900**
945.000
critical
monitor
fair
* Delivered since 1. November 433k; Orders (conf./unconf.) 187k Missing 39,1k (10,9k VHD)
** Delivered since 1. November 110,5k; Orders (conf./unconf.) 34k  Missing 141,4k

## Slide 5
CW49/04
WIP
Material
2,5
Team Estimation
in Mio
Euro
Current Risk CW02/05
Risk should be reduced to 977k € after negotiations
M5F Scrap risk after
negotiations
10%
Supplier Negotiation
1,8
Realized reduction since start
Planned
Committed
Add. Measures
Negotiation (GP and SD)
WIP
Material
Planned Risk reduction Measures
*material transfer from Mexico to Zala
*93k silver
*new orders
A60 Ramp Down – Scrap Risk Global Risk should be reduced to 977k € (PSR Decision 19.01.05)
1,0
Additional target set by PSR (50k €)
M5F/V target set by Management to 977k €
PSR 19.01.05
0,977
Notes: Material First column:
MAN: Some specific component common used with A50 shift to A50 ongoing
ROF Volumes: remaining Production EMEA 27K for 13K no orders.
Additional Production 1,4 Mio reduction SSMC 560K/ PAN 240K/ Man/ 600K
*60K Sky Blue (new colour never sold in EMEA) reduction of SSMC risk
*4,6K Chr-OR colour variant (international/Russia/Italy/South Africa)
 Reduction of risk in PAN
*95,5K (31,5K Units Chr-OR and 75,2K Units Chr-Blue)  Reduction of risk in MAN
Orders:
ROF: 13K w/o orders
VKL: 32K w/o orders
Add. Production: 160K (60K sky-blue, 95,5K LAM, 4,6K chrom-orange)

## Slide 6
Covered by orders, to be shipped
Not covered by orders, quantities > 0.5K
Not covered by orders, quantities < 0.5K
A60 Ramp Down - VKL Overview Stock w/o orders (4,4k) is covered by Sales commitment. Some position will be reworked.
VKL w/o orders is covered by Sales commitment
and rework
A60 VKL KLF

3,6k
w/o DCO, stock VHD
Status
14.01.05
7,6k
A60 VKL Man

Status
11.01.05
33k
0,8k

## Slide 7
Financials

## Slide 8
A60 Business Case Projected Profit 3’8 mio Euro lower than planned at M3
Shipments
Turnover
ASP
Gross Margin
% of T/O
Profit
% of T/O
04/05
YTD
0‘6
29‘9
53 €
1‘0
3%
-3’4*
-11%
M3
Total
2’5
181’2
73 €
17’4
10%
-4‘6
-3%
M Units/ M Euro
Actual
to date
3’8
265’7
70 €
27’7
10%
-8’1**
-3%
M4
Total
4’4
295’7
68 €
29‘8
10%
-8’4
-3%
03/04
Actual
3’2
235’8
73 €
26’7
11%
0’9*
0%
*Based on product P&L Statements (Oct 03 - Nov 04)
** incl. 5‘6 mio Euro in FY02/03
M1 data not available as product was redefined to A60 and C60 after M1
HK per unit 3,57 € lower than planned at M3.
(M3: 60,55, M4: 56,98)

## Slide 9
A60 Ramp Down – Scrap factor Comparison of Ramp Down projects

## Slide 10
The Segment recommends to make the following decision:
yes no Comment
The PSR agrees to the M4 Milestone
Preconditions:
LAM will produce 93k devices in silver and 65k devices in stone in Q2.
Reach the budget target 977k €.

PSR Decision 19.01.2005 Agree A60 M4 Milestone

## Slide 11
BACKUP
A60 Ramp Down - Backup

## Slide 12
A60
End of...
Ramp Down Factories Manaus/Zala
Production
Acquisition
Sales
GDL
Service
EMEA
EMEA
M4
M5S
M5F/V
M5F/V
A60 Ramp Down - Timing
LAM
LAM
ZALA
MAN

## Slide 13
Action
Item
Status
Date
Responsible
Description / Comment
GP
8
Close negotiation for global WiP risk at all suppliers
13.05.05
A60 Ramp Down - Action Items KLF Actions to achieve Milestone M5F/V
Ms. Cadeddu/
Mr. Lewitzke
4
Push delivery of stock of finished goods in VKL KLF
30.04.05
Mr. Lewitzke/
Ms. Cadeddu
6
Track stock of finished goods EMEA -> initiate rework if necessary
2
Scrap excess material on stock in KLF
30.04.05
31.03.05
Mr. Koeller
7
Prepare negotiations with suppliers, initiate preparation meeting
22.04.05
Mr. Koeller/
Ms. Wienen
3
Agree procedure of material transfer for service demands
30.04.05
Ms. Cadeddu
5
Get special variants orders to meet volume proposal
28.02.05
Mr. Koeller/
Mr. Herrmann
1
Support Material Transfer between KLF and Zala
15.03.05
Mr. Koeller
critical
monitor
fair

## Slide 14
A60 Ramp Down - Action Items Manaus Actions to achieve Milestone M5F/V
Mr. Herrmann
2
Support transfer of excess material from KLF to Manaus
28.02.05
Action
Item
Status
Date
Responsible
Description / Comment
Mr. Abreu/
Mr. Herrmann
1
Order risk materials from KLF
28.02.05
critical
monitor
fair
Ms. Assis/
Mr. Vargas
3
Push delivery of finished goods in stock
30.04.05
4
Get special variants orders to meet volume proposal
15.03.05
Ms. Assis/
Mr. Vargas
Mr. Abreu/
Mr. Herrmann
5
Coordinate production of agreed Ramp Down volume. Focus on reduction of material on hand.
31.03.05
Mr. Boldt
6
End scrapping process for remaining material after final production
30.04.05

## Slide 15
A60 Ramp Down - Action Items Zala Actions to achieve Milestone M5F/V
Mr. Herrmann
2
Support transfer of excess material from KLF/GDL to Zala
31.03.05
Action
Item
Status
Date
Responsible
Description / Comment
Mr. Herrmann
1
Order risk materials from KLF and GDL
28.02.05
critical
monitor
fair
Mr. Lewitzke
3
Coordinate production of agreed Ramp Down volume
31.03.05
4
Make sure that Zala takes over the risk material from other production sites
15.03.05
Mr. Köller/
Mr. Herrmann
Mr. Herrmann
5
End scrapping process for remaining material after final production in Zala
30.04.05

## Slide 16
A60 Ramp Down Signatures of team member
Doris

## Slide 17
A60 Ramp Down Volume Commitment LAM Signatures of team member