## Slide 1: Pegasus – Basic Organizer Phone Product Status Report, 23.2.05
– Confidential –
Copyright © Siemens AG 2005: Copying of this document and giving it to others and the use or communication of the contents thereof, are forbidden without express authority. Offenders are liable to the payment of damages. All rights reserved in the event of the grant of a patent or the registration of a utility model or design.
Vinzenz Greger, SPM / Diana Stähler, SPM BA / Kirsi Lehtonen, PM / Susan Tan, PL-T
Notes: Product-approach to be named

## Slide 2: Pegasus – Current Status
Status:
Pegasus S2 is planned for 28.2.
B1+-boards are being populated 22.3.. B1+ is the board planned for Type-Approval.
Original delay in January:  31 days
Actions for speeding-up:
Install qualification-run and shorten Pilot-Series  -5 days
Shorten environmental-test by assigning Pegasus to prio 1  -5 days
Further optimization of project-schedule…
Current delay:  18 days
Ongoing activities:
Optimize and closely monitor schedule.
Identification of potential risks we may face and definition of fallback-solutions.
Checking on further potential. There is still a slight chance to improve in certain areas however these are connected with small probability only.
Delivery-Start now on 17.6. instead of 24.5.
Confirmed June-volume: 100k
Link to explanation of reasons
Link to schedule
Link to action plan

## Slide 3: Current Status for S2 (top open issues)
SP, AD, ED declared S2.
HW-evaluation (and therefore approval of Flash / risk release) not yet finished because of SW-issues  24.2.
Depending on HW-declaration SCM will declare S2
MD will declare end of this week. No issues seen but results of environmental tests not available yet.
Complete System-Test  18.2.. Depending on results ST and SW will declare S2.
EMC / Antenna: no issues  25.2.
CCQ: No topics. Just waiting for team to sign.

## Slide 4: Comparison Business Case The Actual Business Case per 24.02.05 indicates 26’7 m EUR Profit
  Lifecycle and units:
  Delayed launch of 1 month leads to a
  LC shortage
  loss of 311k
  loss of € 1’900 Sales Margin
  Total units stabilized due to 850 variant
  ASP:
  Decrease of launch price from € 70,- to € 67,-;
  In Q1 drop from € 65,- to € 64,-
  HK:
  Significant BoM improvement mainly driven by second source for display
  CCQ:
  No changes
  R&D:
  Increase due to 850 variant
  Marcom:
  Decrease of push rate from € 3,50 / unit to € 3,- / unit
Deviation Analysis M1 vs. current Business Case
AX75
Pegasus

## Slide 5: END / BACKUP

## Slide 6: Reasons for the delay
Libra was chosen as lead-project for EGOLD-lite-platform.
B1-Pegasus was scheduled for 25.11. It was performed 22.12.
Severe problems during Libra B1-prototype-shop-phase:
  Test-SW did not work properly.
  Infineon‘s CRAM and AMD-Flash has HW-defects.
Search and fix took 4 weeks. Pegasus B1-prototype-shop was put on hold until Libra was stable (as these were platform-issues).
Because of the higher complexity Pegasus had some additional issues to work on – even after the successful prototype-shop of Libra (GSM1800-performance…).
The issues within Platform-SW made it necessary to work on these with highest priority. The work on Pegasus-SW had to be postponed until Libra / Pegasus issues have been solved.
Link back to status

## Slide 7: Comparison M1 vs. current schedule
5 weeks delay with B1
5 weeks delay with B1+
      Reduced down to 4 weeks for R&TTE
        Reduced down to 3 weeks for Delivery-Start
Link back to status

## Slide 8
Risks and Actions Pegasus
Link back to status
Notes: <number>
<footer>
<header>
<date/time>
Measures to be dicsuessed with Claus Ziegler (EGOLDlite)

## Slide 9
MTA Pegasus Status 21.2.05
Link back to status
Notes: <number>
<footer>
<header>
<date/time>