## Slide 1: ARIES “The powerful imaging aide“ Product Status Report at M1, Feb 11, 2005
Roland Aubauer
Byrne Wilson
Michael Schuster
Ralf Kern

## Slide 2: This document is review and agreed by the extended ARIES REA Team
__________________ __________________ __________________
SPM PLT SPM BA
__________________ __________________ __________________
Sales SCM QM
__________________
PDM
Signed, Roland Aubauer
Signed, Martin Krepcke
Signed, Fritz Schaumburger
Signed, Thomas Görig
Signed, Ralf Kern
Signed, Byrne Wilson
Due to the PSR decision as of Oct 27, 04 all extended core team members have to commit to the content of this presentation and “virtually” sign the presentation! Please send email to SPM.
Signed, Arnold Spitaler

## Slide 3: Quality Gate Rating Aries 1/2 Status M1
Sales Fit
Good design acceptance
Scenario based on non-VDF exclusivity
ASP: 92€; CRP: 99€ launch, 75€ EOL
Risk: Only 20% of forecasted 23% Market Share in EMEA 09-12/05 range (300k on risk) 1)
Risk: Only minimum price can be realized for non-VF customers 2)
Profitability
Current 4,3% (=16'1€) profit vs. target 7,5% (= 27'9€)
Price/Volume risk has impact of -17'2 EUR on profit 1) 2)
TTM risk has impact of -0‘9 EUR on profit
Strategy Fit
Aries is necessary to stay with high volume product in VF live! (as well in other key customer’s) portfolio and to strengthen our low-end C-class w/ state of the art product
Addressable market (LC): 52' units, market share: 8% (EMEA 09-12/05 market share = 23%)
Profitability
Project Quality
Sales Fit
Product Quality
Strategy
Fit
Time-to-Market
QG
Rating Meeting: Feb 14, 2005 PSO support: B. Pfeifer
Notes: <number>
<footer>
<header>
<date/time>

## Slide 4: Quality Gate Rating Aries 2/2 Status M1
Time-to-Market
Milestone DS: Aug 19, 2005
Risk: delayed DS by 4 weeks
Major risk due to comparably short cycle time of 6,25 months (M1 – DS)
Project Quality
Detailed planning incl. resources available with M1 quality
Product Quality
Major risk due to very short timeline and working not according to standard process (mechanics and testing).
Reduced milestone content requirements (shortened environmental test periods) to achieve timeline.
Risk on minor quality issues for ramp up quantities
Profitability
Project Quality
Sales Fit
Product Quality
Strategy
Fit
Time-to-Market
QG
Rating Meeting: Feb 14, 2005 PSO support: B. Pfeifer
Notes: <number>
<footer>
<header>
<date/time>

## Slide 5: Decisions Proposals in case of yellow Q-Gate
A.) Go ahead with project
Impacts on TTM, EBIT, Volumes, Quality is calculated and available
(see previous slides and backup)
B.) Stop the project:
  Impact : Loss of 4’05 volume in C-class
  Loss of confidence at Vodafone
PSR decision: continue
PSR decision: stop


## Slide 6: Measures, Responsible and Due Dates
Aries

## Slide 7
Backup

## Slide 8: Product Profile - ARIES Be connected in a colorful way
Positioning / Brand: Product Segment: C-Segment
Target Group: female / male: 50:50 age <17-50 yrs, low - mid income
Business: Life cycle: 08/2005 – 05/2006
Volume: 4’05
Price , ASP: 91,85 €
EBIT: 16‘1 €
Against Competition:
Above average feature set & performance for planned price point (TFT-Display, VGA camera, full video)
Fully VF live! Rel 6 compliancy (ultra low tier) without UI
Customization to operator demands
Consumer Highlights:
TFT with highest resolution in segment (132x176, 65536 color display)
Integrated VGA camera and video functionality - ready whenever you want it
Modern & valuable design, lightweight & small
Differentiation within MP:
Differentiation to Adonis: Form Factor
Differentiation to Pegasus: Camera
Differentiation to Wega: Form Factor and target group
Aries

## Slide 9
Aries
Comparison Business Case The M1 Business Case indicates +16’1 m EUR Profit
  VDF exclusivity not considered in M0 and M1 Business Case
  M0 LC BOM commitment 0,39 € below M0 Team commitment
  License fees decreased by 2,09€ to 3,07€ based on new IPR estimation
  Conversion cost decreased by 0,47€ to 6,40 based on updated SCM calculation
  Reduction of R&D costs by 1‘5 € based on M1 re-planning
Deviation Analysis
*w/o variant adder

## Slide 10
Schedule:
M0 21.01.2005 
S0 28.01.2005 
M1 11.02.2005 
S25 20.05.2005
M2 10.06.2005
S3 08.07.2005
PS 15.07.2005
DS 22.08.2005
S4 30.09.2005
M3 30.09.2005
MTA ARIES Status 17.02.05
Aries
Notes: <number>
<footer>
<header>
<date/time>

## Slide 11: Competition Competitor Overview (1/3)
 | Siemens Aries | SE K500i / F500i | Sagem My-V55 | Sharp GX-15 | Sagem My-V75
Network | Tri | Tri | Tri | Tri | Tri
Launch | 08/ 2005 | Q3 / 2004 | 06 / 2004 | 06 / 2004 | Q2 / 2004
Street Price [€] | * | 300 | 250 | 400 | 400
CRP [€] (FY Q4 05) | * | 121 | n.a. | 102 | n.a.
Dimension [mm] | 103x44x17 | 102x46x19 | 106x46x19 | 105x46x17,8 | 110x46x22
Weight [g] | 85 | 87 | 97 | 90 | 106
Display | 65k / 132x176 | 65k / 128x160 | 65k / 128x160 | 65k / 120x160 | 65k / 128x160
Camera / Flash | VGA / ext. | VGA / n.a. | VGA / - | VGA / - | VGA / -
Video play / record |  /  |  /  | - / - |  /  |  / 
MMS / Email |  /  |  /  |  / - |  / - |  / -
User Memory [MB] | 5 | 12 | n.a. | 1,8 | n.a.
MP3 / Radio | - / - |  /  | - / - | - / - | - / -
IrDa / BT |  / - |  / - |  / - |  /  |  / -
Standby Time [h] | 300 | 300 | 370 | 230 | 310
Talk Time [min] | 300 | 420 | 285 | 180 | 270
Battery [mAh] | 750 | n.a. | 920 | 780 | 1050
Extras | PTT | Video Streaming F500i excl Vodafone | Excl Vodafone | Excl Vodafone | Excl. Vodafone
* removed for confidentiality reasons

## Slide 12: Competition Competitor Overview (2/3)
 | Siemens Aries | Sagem My X-7 | Motorola C651 | Alcatel 565 | Nokia 3220
Network | Tri | Tri | Tri | Tri | Tri
Launch | 08/ 2005 | 06 / 2004 | Q4 / 2004 | Q4 / 2004 | Q3 / 2004
Street Price [€] | * | 300 | n.a. | n.a. | 250
CRP [€] (FY Q4 05) | * | 98 | n.a. | n.a. | n.a.
Dimension [mm] | 103x44x17 | 110x46x22 | 103x44x19,6 | 107.7x48.2x21.4 | 104,5x44x18,7
Weight [g] | 85 | 106 | 91 | 93 | 86
Display | 65k / 132x176 | 65k / 128x160 | 65k / 128x128 | 65k / 128x160 | 65k / 128x128
Camera / Flash | VGA / ext. | VGA/night mode | VGA / - | VGA / - | VGA / -
Video play / record |  /  |  /  |  / - |  / - |  / 
MMS / Email |  /  |  / - |  / - |  / - |  / -
User Memory [MB] | 5 | 4 | 1,7 | 2 | n.a.
MP3 / Radio | - / - | - / - | - / - | - / - | - / -
IrDa / BT |  / - |  / - | - / - |  / - | - / -
Standby Time [h] | 300 | 310 | 215 | 285 | 280
Talk Time [min] | 300 | 280 | 380 | 455 | 180
Battery [mAh] | 750 | 1050 | 750 | 800 | 760
Extras | PTT | Excl T-Mobile |  |  | Light effects
* removed for confidentiality reasons

## Slide 13: Competition Competitor Overview (3/3)
 | Siemens Aries | Panasonic X300 | Alcatel 756 | Samsung X 610 | 
Network | Tri | Tri | Tri | Dual | 
Launch | 08/ 2005 | Q4 / 2004 | Q2 / 2004 | Q3/ 2004 | 
Street Price [€] | * | 300 | 300 | 250 | 
CRP [€] (FY Q4 05) | * | n.a. | n.a. | n.a. | 
Dimension [mm] | 103x44x17 | 92x49x21 | 106x46x18,5 | 111x46x11,8 | 
Weight [g] | 85 | 87 | 92 | 75 | 
Display | 65k / 132x176 | 65k / 128x128 | 262k / 128x160 | 65k / 128x128 | 
Camera / Flash | VGA / ext. | VGA / n.a. | VGA /  | VGA /  | 
Video play / record |  /  |  /  |  /  |  /  | 
MMS / Email |  /  |  / - |  / - |  / - | 
User Memory [MB] | 5 | n.a. | 4 | 6,5 | 
MP3 / Radio | - / - | - / - | - / - | - / - | 
IrDa / BT |  / - | - / - |  / - |  / - | 
Standby Time [h] | 300 | 260 | 250 | 230 | 
Talk Time [min] | 300 | 660 | 480 | 180 | 
Battery [mAh] | 750 | 780 | 950 | 800 | 
Extras | PTT | Pop up display |  | Turnable camera | 
* removed for confidentiality reasons