## Slide 1
Generation 85 pre M0 Project Status PSR 24.02.2005
Com MD PBM PM
– For internal use only –
Copyright © Siemens AG 2004: Copying of this document and giving it to others and the use or communication of the contents thereof, are forbidden without express authority. Offenders are liable to the payment of damages. All rights reserved in the event of the grant of a patent or the registration of a utility model or design.

## Slide 2: Generation 85 pre-M0 Overview milestone planning - Status 24.02.2005
Fast track M0
Fast track M0 w/o M-Beta
14.03.05
05/06
Robin
01.04.05
02/06
Plover
TBC
02/06
Baya
23.03.05
01/06
Finch
14.03.05
05/06
Dodo
28.02.05
02/06
Polaris
04.03.05
11/05
Siskin
29.04.05
05/06
Ibis
30.03.05
03/06
Swift
25.02.05
01/06
Quail
TBC
06/06
Lark
M04/05
03/06
Pelicane
06/05
05/06
Macaw
M
M0
2 months
2 months
8 ~ 13 months 1)
Mß
2 months
1) Typical lead time for market launch depending on complexity of product
E02/05
05/06
Brambling
03/05
08/06
Hummingbird
03/05
08/06
Swan
03/05
09/06
Parrot
DS
LEGEND
14.03.05
02/06
Project
Target date next Milestone
Delivery Start
Project owner
= ODM
= in-house
Kick-off
M0
Mß
M
Kick-off

## Slide 3: Generation 85 pre-M0 Achievements, Issues and Next Steps (1)
Time to market
Product
Status
Positive trend, e.g. significant positive delta to last reported value
Negative trend, e.g. significant negative delta to last reported value
No significant change
Achievements
Next Steps
Issues
Financials
Target
Actual
02/ 05
25.02.05
01/ 06
01/ 06
Trend
Status
DS
M0
Trend
Status
Target
Actual
02/ 05
TBC
02/ 06
02/ 06
Target
Actual
M04/ 05
M04/ 05
03/ 06
03/ 06
Target
Actual
03/ 05
04.03.05
11/ 05
11/ 05
Siskin
Quail
Polaris
Pelicane
M0 workshop from Feb 28 to Mar 4
SP PPL is not available (escalated by PLT) Antenna clarification for M0 critical
M0 workshop this week (Feb 21 to Feb 25)
M0 Kick-off Feb 19
M0 workshop from Apr 11 to Apr 15
Lark (2nd ID Pelicane)
New M0 date will be communicated by end of this week (Feb 25)
Target
Actual
M04/ 05
TBC
06/ 06
06/ 06
Alignment between
Mechanics and Design still
not complete (currently being
addressed in Beijing)
M0 delayed due to SW situation in PD: SW team still not staffed. (escalated by PLT)
DS 02/06 still valid.
M0 declaration Feb 25
see Pelicane
Nano I/O still not confirmed by PD
Severe deviations
Deviations or risk
According to targets

## Slide 4: Generation 85 pre-M0 Achievements, Issues and Next Steps (2)
Time to market
Product
Status
Positive trend, e.g. significant positive delta to last reported value
Negative trend, e.g. significant negative delta to last reported value
No significant change
Achievements
Next Steps
Issues
Financials
Target
Actual
04/ 05
29.04. 05
05/ 06
05/ 06
Trend
Status
DS
M0
Trend
Status
Target
Actual
TBC
05/ 06
05/ 06
Target
Actual
03/ 05
23.03.05
01/ 06
01/ 06
Target
Actual
03/ 05
30.03.05
03/ 06
03/ 06
Principle Design Decision (Feb 17)
Principle Design Decision (Feb 18)
Finch
Plover
M0 workshop from Mar 21 to Mar 25
M0 workshop from Mar 28 to Apr 1
Ibis
Swift
Brambling
PPL’s missing, escalated by PLT.
Seriell data cable for EGL with Nano I/O still unclear
New QVGA 2,0” display needs to be evaluated (stack-up concept & design)
PPL’s (EMC, RF, SP, NPI2) missing, escalated by PLT
Target
Actual
04/ 05
01.04.05
02/ 06
02/ 06
Alternative generation and fine tune product profile (Mar 3)
see Swift
Available battery today:
520mAh not acceptable.
New offer from Sanyo for
700mAh on evaluation
Battery feedback until Feb.
25
M0 workshop on CW 11
M0 workshop on CW 15
New slim concept used for
Swift (17mm)
Severe deviations
Deviations or risk
According to targets

## Slide 5: Generation 85 pre-M0 Achievements, Issues and Next Steps (3)
PPM
Time to market
Product
Status
Positive trend, e.g. significant positive delta to last reported value
Negative trend, e.g. significant negative delta to last reported value
No significant change
Baya
Dodo
Robin
3G
see Baya
Macaw
Principle Design Decision (Feb 17)
Principle Design Decision (Feb 7)
Achievements
Next Steps
Issues
Missing feedback by supplier
Financials
Target
Actual
06/ 05
06/ 05
05/ 06
05/ 06
Trend
Status
DS
M0
Trend
Status
Target
Actual
TBC
05/ 06
05/ 06
Target
Actual
TBC
05/ 06
05/ 06
Target
Actual
TBC
02/ 06
02/ 06
New QVGA 2,0” display decided and therefore SG2 platform for product. Activities needs to be aligned, new milestone schedule to be generated until Feb 25.
Severe deviations
Deviations or risk
According to targets
see Robin Presentation by 3G
Activities to improve BC