## Slide 1: Dorado – The Basic Tool Product Status Report, 24 Feb 2005
– Strictly Confidential –
Copyright © Siemens AG 2005: Copying of this document and giving it to others and the use or communication of the contents thereof, are forbidden without express authority. Offenders are liable to the payment of damages. All rights reserved in the event of the grant of a patent or the registration of a utility model or design.
Michael Huebler, SPM / Juergen Jungbauer, SPM BA / Qi Zhao Hui (ZH), PM / Zhuang Xiao Qun (Raymond), PL-T
Notes: Product-approach to be named

## Slide 2: Dorado – Current Status
Status:
B1+ Tape Out is done.
B1+ Prototype Run planned for 08 Mar 2005. B1+ is the board planned for Type-Approval.
Delay vs. M1:  4 weeks
Actions already taken for speeding-up: Original delay from B1 run: 6 weeks
Re-arrange Prototype Runs scenario, re-use Libra  -2 weeks
4 weeks
Further Opportunities for improvements: Action Item:
Type Approval – could take less than 8 wks (slight chance) PL-T to follow-up & monitor – during Type Approval phase
Faster ramp-up (slight chance) Ramp-Up-Team to optimize – until e/o Mar 2005
Further Risks:
Prototype Shop (esp. Test Line) availability in SHA for the B1+ run
 a 2nd Test Line would reduce this risks, of course for all other BJ projects as well
Delivery-Start now on 16.6. instead of 19.5.
Targeted volume in June: 117k
Link to explanation of reasons
Link to schedule
Link to financials

## Slide 3: BACKUP

## Slide 4: Reasons for the delay
B1 run
  was scheduled for 03 Dec 2004
  but happened 18 Jan 2005
During the Libra B1 run, severe problems with testing & booting happened:
  Mobile SW & Test SW did not work properly
  HW defects in Infineon CRAM and AMD Flash
Search and fix took 4 weeks.
Dorado B1 run was put on hold
  until Libra was stable
  and 2 more weeks, until Pegasus B1 run was finished (switch from IFX -> Samsung and follow-up problems due to change)

## Slide 5: Comparison M1 vs. current schedule
6 weeks delay with B1
Reduced down to 4 weeks for Delivery-Start

## Slide 6
MTA
Notes: <number>
<footer>
<header>
<date/time>

## Slide 7: Financial Impact of 1 month delay Assumption: total loss of 3rd month volumes
M1 1-Month-Delay Delta
Units 11'532 10'562 - 0’970
Turn Over 407'068 370'606 - 36'462
Sales Margin 84'407 74'180 - 10'227
Gross Margin 52'522 45'051 - 7'471
DP 7'991 3'751 - 4'241
DP in% 1.96% 1.01% - 0.95%
->
->
->
->
->
->

## Slide 8: Mindmap