## Slide 1: Phoenix “Social Life Manager” Product Status Report
PSR, 30th March 2005 – Confidential
M. Mildenberger (SPM), Gregor Flüge (PLT), D. Culmbacher (SPM BA)
Notes: STRICTLY CONFIDENTIAL

## Slide 2: The industrial design and the colours
Sand Silver (second colour)
Titan Grey (launch colour)
Design
CX75
Velvet Black (Vodafone exclusive colour)
tbd. (I-Mode)
Notes: <number>
<footer>
<header>
<date/time>
STRICTLY CONFIDENTIAL

## Slide 3: Phoenix has been launched at CeBIT
CX75
Notes: <number>
<footer>
<header>
<date/time>
STRICTLY CONFIDENTIAL

## Slide 4: Press and end customer feedback
CX75
„The display convinced everybody. The first time Siemens managed to built in a competitive display“ (POS Trainer, 17.03.2005)
“Having played with what is destinated to be a mid-range handset by the time it arrives, I have to admit I took a quite a liking to the CX75. Sporting a light grey colour scheme, the handset is quite comparable to the S65 with its 1,3 Megapixel camera, Bluetooth support, triband GSM 900/1800/1900 MHz and GPRS Class.” (infoSync World, 10.03.2005)
„The keypad is great – everybody is in the position to use it“ (POS Trainer, 17.03.2005)
„Jede Menge Hightech hat Siemens auch ins CX75 gepackt.“ (xonio.com, 11.03.2005)
Notes: <number>
<footer>
<header>
<date/time>
STRICTLY CONFIDENTIAL

## Slide 5: Project schedule is now back on track
CX75
Source: latest PSO Primavera snapshot, 11th March 2005
Due to weekend work the project already caught up this delay and is now back on track (DS: June 10)
Early March the project team reported a delay of 5 working days due to belated arrival of samples at mechanical design department in Shanghai
Notes: <number>
<footer>
<header>
<date/time>
STRICTLY CONFIDENTIAL

## Slide 6: MTA
CX75
Notes: <number>
<footer>
<header>
<date/time>
STRICTLY CONFIDENTIAL

## Slide 7: Risks, current problems and counter measures
CX75
Problem/Risk | Action | Responsible | Due
Mechanics (Sub)-supplier of deco cap is not capable of mass producing the needed quality (yield ~10%) This was leading to a late change in surface appearance and additional risk regarding TTM. So far no written commitment that changed gloss level will solve the problem entirely. | Monitor closely the B2 delivery timeline and delivered quality | G. Flüge (PL-T) | B2
I-Mode/Doja 1.5 The agreed timeline for the I-Mode/Doja 1.5 variant is mid of July. However, the latest planning is showing an availability of the software end of August. | Provide a detailed planning which is showing the committed dates | F. Zabel (Platform PL-T) | April 6
Hardware The power supply chip “Mozart” has currently problems in lead free soldering process. Tests with new metallization have been performed. Result: Mozart ok now but lead free soldering process not stable for mass production yet. | Additional pilot run in Phoenix-Project Qualification of a second source started more early than planned | G. Flüge (PL-T) | Pilot run
Mechanics Navikey misplacement leads to bad visual appearance. | First evaluation of tolerance analyses was not showing the root cause. Ongoing evaluation of the root cause with a wider scope | G. Flüge (PL-T) | Pilot run
CRs, Operator customization and Approval Bug fixing, CR load and customization is not possible as planned with assigned resources | Increase of assigned resources for Phoenix/Sirius (see next slides for details!) | M. Topel (Head of SWP), K. Rudolph (Head of SWC) | 1st April 05
Notes: <number>
<footer>
<header>
<date/time>
STRICTLY CONFIDENTIAL

## Slide 8: Phoenix/Sirius has additional workload compared to the M1 contract
Due to SW Resource situation the following limitations are agreed between PM and PD
No more new SW CRs for Phoenix/Sirius otherwise even more additional resources are required.
Limitation of “bugs to be evaluated” to 300 (best guess from PM and RD).
Resource consuming or difficult 65-generation-bugs need to be discussed and agreed separately, as maybe further additional resources are needed.
 Increase of requirements will lead to additional lack of resources. Without countermeasures this will cause delay of DS.
CX75

## Slide 9
Due to insufficient resources in March, some tasks were shifted to April and May. If the missing resources will not be available as planned in April & May, these tasks need to be shifted. This endanger the approvals and the DS.
CX75
The software resource situation is showing a severe overload in the upcoming critical period before DS software freeze

## Slide 10
Source: latest PSO resource loads, 17th March 2005
The latest PSR resource load summary is confirming the team evaluation regarding software load
CX75
Notes: <number>
<footer>
<header>
<date/time>

## Slide 11: Additional resource problems are becoming more and more severe
CX75
Problem/Risk | Action | Responsible | Due
PPL Mechanical design The MD part project leader has resigned. Changing this key role in the project is adding tremendous risk to the project. Another experienced resource not available at the moment in Shanghai! | Mechanical Design Line Organization trying to make her stay in the company until end of pilot run. If not possible, Mechanical Design Line Management shall take PPL job. | D. Markardt, Mech. Design Line Manager Shanghai | 15th April
Beijing Software team Not so experienced team in SGold lite platform in Beijing leads to TTM risk | Continuing support from German experts necessary | M. Topel (Head of SWP), K. Rudolph (Head of SWC) | ongoing
Primavera Project Planning This role is currently staffed with a consultant. The contract will expire in April and is not yet extended. | Extend contract | PSO | 1st April
Notes: <number>
<footer>
<header>
<date/time>
STRICTLY CONFIDENTIAL

## Slide 12: Comparison Business Case
  Lifecycle:
  With delivery start in June’05 and phase out in February’06 lifecycle is 9 months.
  Units:
  Regional split of total quantity of 1,900k is: 87% EMEA, 10% APAC and 3% LAM.
  Tough time schedule in ramp-up phase leads to reduced quantity in first month by 50k.
  ASP:
  Launch price of € 165 and phase out price of € 135 leads to ASP of € 157 over LC.
  HK:
  BoM-improvement mainly through negotiation successes after M1.
  Conversion Cost (€ 8.09) based on production site split indicated by GO (KLF 87%, SSMC 10%, MAN 3%)
  Licenses (€ 6.17): Audio/Video Levies (€ 3.71) only considered for EMEA quantities. Activation of MP3-Player considered.
  Cogs:
  Service costs are calculated out of Return Rate of 13.4% and service costs per return of € 37.05.
  R&D:
  R&D budget includes € 9’5 direct project costs and € 10’2 indirect costs.
  Marcom:
  MarCom based on revised budget indication from S&M (€ 3.0 per unit sold plus 4% of T/O plus € 2’5 HQ budget). Slight decrease due to lower LC-quantity.
Deviation Analysis M1 vs. 30.03.05
CX75

## Slide 13: Business Case – Key Performance Indicators
General | Launch date | June 05 |  | COGS | Return rate | 13,4%
 | End of Life | Feb 06 |  |  | Cost per return | € 37,05
 | Positioning | Mid |  |  | Other COGS in % of T/O | 1,3%
 |  |  |  |  | SCM costs in % of T/O | 2,0%
T/O | Units | 1’900k |  | OH | Total R&D cost. | € 19.687.472
 | Launch price | € 165 |  |  | Therein indirect R&D cost | € 10.171.835
 | EOL price | € 135 |  |  | R&D in % of T/O | 6,6%
 | ASP | € 157 |  |  | Selling in % of T/O | 5,0%
 | Price decrease over life-cycle | -18,2% |  |  | Marketing cost | € 19.727.500
HK | Ø HK | € 103,62 |  |  | Marketing per unit sold | € 10,38
 | Ø Conversion cost | € 8,09 |  |  | Marketing in % of T/O | 6,6%
 | Ø BOM | € 87,61 |  |  | Admin in % of T/O | 1,2%
 | BOM price decrease over life-cycle | 11,4% |  | Profit | Profit in Mio | € 24,4m
 | Licences | € 6,17 |  |  | Profit per Unit | € 12,85
 | Ø Variant Adder | € 1,75 |  |  | Profit in % of T/O | 8,18%
CX75

## Slide 14: Business Case – Risks
  Time-to-Market
Business Case Risks
  Confidence Level: 80% for Launch date in June, 20% risk for 2 weeks delay (150k)
Description
Impact
   4’0 m EUR
  EBIT
  EBIT margin %
   0,7 %
  Price
  Latest market feedback as per CeBit o.k.: 10% price risk
   25’8 m EUR
   8,7 %
  Volume
  Latest market feedback as per CeBit o.k.: 16% volume risk due to current planning in I2 DM (300k)
   7’3 m EUR
   1,4 %
  0% HK risk, high confidence level in actual BoM
   0’0 m EUR
   0,0 %
  HK
CX75

## Slide 15: Backup
CX75
Notes: <number>
<footer>
<header>
<date/time>
STRICTLY CONFIDENTIAL

## Slide 16: Highlights
* Headset and RS-MultiMediaCard not bundled
Key Features
Design
Accessories
Technology
Applications
  1.3-megapixel camera
  Bluetooth®
  262K colour display, 132 x 176 pixels, 1.8 inch
  Video recording and playback
  MP3 / AAC / AAC+ player *
  RS MultiMediaCard slot
  PaT via side key
  Bar phone
  High-value colour and material finish
  Timeless design with an exclusive touch
  Clearly structured keypad
Key Features
  Car Kit Bluetooth® Portable
  Mobile Music Set
  Wide range of Headsets and Car Solutions
  Tri-band (900 / 1800 / 1900)
  GPRS Class 10
  WAP 2.0
  Bluetooth®, IrDA, RS MultiMediaCard slot
  Wireless Java MIDP 2.0
  MP3/AAC / AAC +
  3D games & multiplayer games
  Printer via Bluetooth®
  Blogging Client
  Photo Editor
  Download Assistant
  Instant messaging
CX75
Update: Music bundle w/ 128MB RS-MMC and headset for an attractive price available!
Notes: <number>
<footer>
<header>
<date/time>
STRICTLY CONFIDENTIAL

## Slide 17: Multimedia without Limits
Product Idea, Target Group
Product Idea
Surprising entertainment options and multimedia features combined with efficient life management components.
  Male: Female (50:50)
  Age focus 20 - 45 years
  Low to mid income
  Focus on use for personal purposes
  They concentrate on friends & family (community-centric people) and want to enjoy life
  They are leading a turbulent and multi-faceted life juggling many activities & appointments related to their professional & personal life
  Relaxation and finding a certain balance are key requirements
  Products they own have to be surprising and give away a 'human touch'
  Image & design also have a certain importance
  Decisions are based on a mixture of design, feature and cost considerations
Product Segment
Target Group Socio-demographic Data
Target Group Behavioural Aspects
Emotion class
CX75
Notes: <number>
<footer>
<header>
<date/time>
STRICTLY CONFIDENTIAL

## Slide 20: Quality Gate Phoenix 1/2 Status M1 (Oct 27, 2004)
Profitability
Project Quality
Sales Fit
Product Quality
Strategy
Fit
Time-to-Market
Sales Fit
I-mode currently no feature, but change request launched
Volume risk (10% overall) if i-mode is not implemented
150k volume risk (8% overall) due to lack of demand in summer
Sales: no price risk (BA disagrees because of experience of 65 generation)
Profitability
8.5% (current) vs. 7.5% (target)
Low confidence due to volume risk and challenging project time schedule
Strategy Fit
Life cycle between 6 to 9 months, Minos successor already in place
Dead-end platform: S-Gold lite not S-Gold 2
CX75
Notes: <number>
<footer>
<header>
<date/time>

## Slide 21: Quality Gate Phoenix 2/2 Status M1 (Oct 27, 2004)
Time-to-Market
Medium confidence because of tough schedule
M1: 25.10.04 (-26 days)
S3: 17.05.05 (-23 days)
PS: 30.05.05 (-22 days)
DS: 10.06.04 (-16 days)
S4: 06.07.05 (-23 days)
Project Quality
Activities without predecessors, however they are missing in external plans (SW components)
Project plan for Phoenix itself is green
No weekly update for some part projects
Product Quality
Not enough time for mechanical optimization/environment test between B2 and ramp up
Accessories will be available later than the latest layout; risk: support and functionality not guaranteed, changes in mobile difficult to implement in late stages
New technology (lead free process) in mass production
Profitability
Project Quality
Sales Fit
Product Quality
Strategy
Fit
Time-to-Market
CX75
Notes: <number>
<footer>
<header>
<date/time>

## Slide 22
Risks and Actions Status M1 (Oct 27, 2004), update March 14 marked in blue
CX75
Notes: <number>
<footer>
<header>
<date/time>

## Slide 23: Concept execution – ongoing -
CX75
DRAFT
only
M1: Phoenix planned as “Below the line”
Product  POS driven concept
Recent feedback from Regions:
CEE: no major role of product
AIP: no major role of product
RUS: full campaign required/highlight product
I: no major role of product
WE: print only/ highlight product
GER: print required
 adaptation of concept to changed
requirements of Regions ongoing
 discussion with Russia ongoing to
develop an additional TV campaign