## Slide 1: Adonis “My stylish socialiser” Product Status Report, 30.3.05
COM MD PBM PG75, Vinzenz Greger (SPM), Carlos Schmidt (SPM BA), Emily Zhao (PM)
– Confidential –
Copyright © Siemens AG 2005: Copying of this document and giving it to others and the use or communication of the contents thereof, are forbidden without express authority. Offenders are liable to the payment of damages. All rights reserved in the event of the grant of a patent or the registration of a utility model or design.

## Slide 2: Executive Summary Adonis 1/2 Status 14.03.05
Profitability
Project Quality
Sales Fit
Product Quality
Strategy
Fit
Time-to-Market
Sales Fit
Price risk to 100.- Euro launch price since key customers ask for special prices already
Good feedback from regions and high to moderate sales confidence level
Profitability
Current BC with 8,8% (40’5 Euro) profit above target
BUT: Risk indications for volume due to delay, for ASP due to special price requests and for HK
Therefore, moderate to low confidence that targets can be met
Strategy Fit
All key features according to position in roadmap and story line
Attractive price/performance ratio in a premium design allowing operator customization as differentiator
CF75
Adonis
Notes: <number>
<footer>
<header>
<date/time>

## Slide 3: Executive Summary Adonis 2/2 Status 14.03.05
Profitability
Project Quality
Sales Fit
Product Quality
Strategy
Fit
Time-to-Market
Time-to-Market
Medium confidence to reach TTM
S2: 29.03.05
S3: 30.05.05
DS: 11.07.05 (in line with M1 plan)
S4: 11.07.05
Same date for DS / S4 as pilot series start 6 weeks earlier
Project Quality
Staffing of Rea & PD team complete
Product Quality
Project on track
Cooperation with BYD is a pilot for a new approach (one-stop-shopping-concept), therefore risk remains for the phase of high volume production
CF75
Adonis
Notes: <number>
<footer>
<header>
<date/time>

## Slide 4
MTA Adonis Status 13.3.05
S2-Status
PD-team reached S2-status. Only signatures to be collected.
Confidence in declaring S2 this week
CCQ: Waiting for team to sign.
Notes: <number>
<footer>
<header>
<date/time>

## Slide 5: Critical Path, Measure to be taken, Decision to be taken
Critical Path:
B1+-prototype-run
B2-LC-module
Type-Approval
Measures & Decisions to be taken:
-
Implementation Controlling
Weekly tracking of scheduled actions by Rea / PD-Team (see top AIs).

## Slide 6: Comparison Business Case
  Lifecycle:
  - No changes; timeline confirmed
  Units:
  - No changes
  ASP:
  - No changes
  HK:
  - License fees increased due to new prevailing case law
  Cogs:
  - Service costs per unit increased slightly
  R&D:
  - Improved due to lower actual costs
  Marcom:
  - No changes
Deviation Analysis M1 vs. 29.03.05
CF75
Adonis

## Slide 7: Business Case – Key Performance Indicators
General | Launch date | July 05 |  | COGS | Return rate | 11,87%
 | End of Life | April 05 |  |  | Cost per return | € 42,91
 | Positioning | Mid / Class |  |  | Other COGS in % of T/O | 1,3%
 |  | Clam fashionable |  |  | SCM costs in % of T/O | 2,0%
T/O | Units | 3’537k |  | OH | Total R&D cost. | € 12’1m
 | Launch price | € 115 |  |  | Therein indirect R&D cost | € 5‘9m
 | EOL price | € 95 |  |  | R&D in % of T/O | 3,3%
 | ASP | € 102,23 |  |  | Selling in % of T/O | 5,0%
 | Price decrease over life-cycle | -17,4% |  |  | Marketing cost | € 26’8m
HK | Ø HK | € 74,28 |  |  | Marketing per unit sold | € 7,59
 | Ø Conversion cost | € 6,15 |  |  | Marketing in % of T/O | 7,4%
 | Ø BOM | € 62,96 |  |  | Admin in % of T/O | 1,2%
 | BOM price decrease over life-cycle | NA. |  | Profit | Profit in Mio | € 7‘6m
 | Licences | € 3,91 |  |  | Profit per Unit | € 2,15
 | Ø Variant Adder | € 1,26 |  |  | Profit in % of T/O | 2,1%
CF75
Adonis

## Slide 8: Technical and Business Case Risks - Adonis
  Mechanics:
Technical Risks
  Medium risk: No 2nd source for FPC due to missing resource. 2nd source for camera ongoing.
  Display-lens did not pass static-load-tests. Measures implemented but not confirmed.
Description and measures
Impact
  Higher yield / return rate
  Potential quality-issues
  Hardware:
  No major risks seen.
  Potential minor delay because of delayed prototype-shop
  <3d
  Software / System Test
  No major risks seen.
  -
  Others
  No major risks seen.
  -
  Time-to-Market
Business Case Risks
  20% probability that launch is delayed one month until August 2005
Description
Impact
   -2’7 m EUR
  EBIT
  EBIT margin %
   -0,7 %
  Price
  >50% probability that ASP is reduced 5% over Lifecycle (Launch Price 109 EUR, EoL Price 90 EUR and ASP 97 EUR)
   -15’6 m EUR
   -4,5 %
  Volume
  0%
   x’x m EUR
   x,x %
  0%
   x’x m EUR
   x,x %
  HK

## Slide 9
Product Status Adonis
Adonis
Adonis
(CF75)
Schedule/PV/Milestones:
M0 25.10.04  S15 30.12.04  S3 30.05.05
S0 01.11.04  S2 29.03.05 DS 11.07.05
M1 23.12.04  S25 27.04.05 S4 11.07.05
M3 08.08.05
Status current milestone:
S2 (29.03.04): PD team reached S2 status. Only signatures to be collected.
Major Risk
ESD failure during camera view finder, solution still not available new target is Apr. 1.
Static load failure due to adoption of die-cut lens, will improve this till B2, some improvement will be implemented B1+.
HW
FPC: HW tool samples test finished, result is OK.
LCDM: due to ESD problem, B2 LCDM is very likely be delayed (currently is around one week) and might have some impact on DS.
MD
Static load issue is under improving
3rd OT will be on time.
SW
S25 SW will be frozen for test on Apr. 1
APAC variant available
Power consumption issue basically solved, continuously improvement still ongoing.
Prototype run:
B1+: ongoing. Might have small delay because of PCB ready some days later than planned.

## Slide 10: Adonis 850
Adonis 850 was requested by LAM
A CR was handed in for adding Adonis 850 to roadmap
PD-team evaluated CR and reached M0-status (only 2 signatures and Q-Gate missing)
Team asks for permission to proceed with development until next PSR.
Action Items until next PSR:
According to Guy Spillabeen the volume-scenario provided by countries is too conservative  volume to be double-checked until next PSR.  Area Manager, Ricardo Ferraz
In next PSR M0 is to be confirmed.  Greger
Evaluation of impact on overall R&D-situation to be investigated.  Cron

## Slide 11: Business Case – Key Performance Indicators
General | Launch date | Oct 05 |  | COGS | Return rate | 9,1%
 | End of Life | May 06 |  |  | Cost per return | € 48,52
 | Positioning | Mid / Class |  |  | Other COGS in % of T/O | 1,3%
 |  | Clam fashionable |  |  | SCM costs in % of T/O | 2,0%
T/O | Units | 749k |  | OH | Total R&D cost. | € 1’5m
 | Launch price | € 99 |  |  | Therein indirect R&D cost | € 0‘7m
 | EOL price | € 90 |  |  | R&D in % of T/O | 2,0%
 | ASP | € 96 |  |  | Selling in % of T/O | 5,0%
 | Price decrease over life-cycle | -9% |  |  | Marketing cost | € 5’1m
HK | Ø HK | € 73,82 |  |  | Marketing per unit sold | € 6,85
 | Ø Conversion cost | € 7,72 |  |  | Marketing in % of T/O | 7,2%
 | Ø BOM | € 62,41 |  |  | Admin in % of T/O | 1,2%
 | BOM price decrease over life-cycle | n.a. |  | Profit | Profit in Mio. | € -2‘1m
 | Licences | € 2,44 |  |  | Profit per Unit | € -2,78
 | Ø Variant Adder | € 1,25 |  |  | Profit in % of T/O | -2,9%
Adonis 850

## Slide 12: Product Status Adonis 850 (LAM variant)
Adonis
(CF76)
Open point: Need official decision on LAM variant,
M0 18.03.05 (PD team is ready to declare M0)
M1 07.04.05
S15 04.21.05
S2 22.06.05
S25 07.29.05
S3 17.08.05
Pilot Series Start 10.08.05
Production Start 24.08.05
S4 17.11.05
Delivery Start 20.10.05
M3 15.12.05

## Slide 13: Price- / Volume-Scenario

## Slide 14: Backup / Risks & Actions as defined within M1

## Slide 15: Risks and actions, M1

## Slide 16: Risks and actions, PD-Team 1 of 2
done
done

## Slide 17: Risks and actions, PD-Team 2 of 2
6.No critical issue was found at B1, need further tracking until B1+
10.B1 didn’t pass the testing, ME provided solution for this,Need to be checked at B1+
13.FPC: No second source for FPC , due to resource limit, BYD FPC passed the bending test at B1.

## Slide 18: Quality Management update in M1
Critical risk: main supplier BYD, which is not qualified.
Risk of higher field return rate and unacceptable higher failure rate in mass production:
  BYD does not fulfil the requirements of a capable supplier. (76% for plastic / design part Class B, 71% for cameras Class C , required AB (>=80%)).
  BYD has a lot of deficiencies in their QM system and process.
  Increased risks for the supply with sample parts and constant quality for the mass production.
Risk of endangered TTM: supplied quality and the amount of delivery are not guaranteed for ramp-up and mass production. This could lead to a delayed „Time to Market“.
QM Actions update in M1:
  Task force to improve BYD quality: SCM QM, Henning Haase,
    corrective actions and coordinate continuous improvement of BYD on a full time basis
    Latest camera audit score is 71% (better than 37% in M0&S0) .
    Next follow up audit is planed around May
  Push PD team to have second supplier of FPC, Camera, Battery: SCM QM, PQA, PM, PL-T,PD
    Battery: Take Leopard battery as fallback solution;--done
    No second source for FPC, camera second supplier is on going
    LCD doesn’t have second supplier, which is accepted by MP board.
    --complete BYD feasibility analyse report based on BYD display and camera TTD, due date: Dec.31