## Slide 1
EGL Platform Status
Date: 2005-03-30
PPL: Claus Ziegler

## Slide 2: EGold-Lite Platform Status
Schedule/Milestones:
I0: 09.04.04 ( 09.04.04)  I2: 13.08.04 ( 13.08.04)  I4: 29.05.2005
I1: 08.06.04 ( 08.06.04)  I3: 08.04.05
I3 has been delayed to April 08, 2005 because of insufficient product SW stability (LL).
Major threats
Recently discovered HW-bug in B6E – both possible solutions of metal fix and layout change not in time for pilot series of lead product. Screening of parts at supplier side needs to be done.
SW
SW debugging for EGold-Lite generic SW is ongoing (with Libra B2)
Power consumption in”normal case” and “worst case” is higher than expected. Investigations are ongoing. Deadline for fixing this bug is April 8, 2005 (Libra SW S3)
S25 for lead project (Libra) will be declared on April 4, 2005
HW
EGold-Lite baseband chipset qualification is done
First risk releases for EGold-Lite in Libra, Dorado and Pegasus have been made
Investigations regarding effect of B6E bug on products and search for countermeasures are ongoing

## Slide 3: Number of defects for EGL Products which determine TTM Known Defects /w RPN>1000 on EGL Products as of 29.03.05
Bug fixing rate of appr. 20 bugs per week => not critical for DS