## Slide 1
X75/85 SGL Platform Status (excl. SW)
Date: 2005-03-30
PPL: Farouk Zabel

## Slide 2: X75/85 SGL Platform Status
Schedule/PV/Milestones:
M0: 01.03.05 ( 10.06.04)  S2: N/A  DS: N/A
S0: N/A  S25: 18.03.05 ( 18.03.04)  S4: 01.04.2006
M1: 01.03.05 ( 22.10.04)  S3: 15.12.05  M3: 01.06.2006
X75/85 SGL Platform planning has been finished and account has been opened
Milestones are only SW related. S25 has been declared
Major threats
Introduction of lead-free soldering – new problems in Phoenix/Sirius B1+ boards with Mozart ASIC
Stabilization period between SW S25 and first DS only 9 weeks
Lack of SW resources to tackle all bugs and CRs (including operator CRs) in time for the DS SW-freeze
HW
First risk release of SGL with G15 mask done.
All tests on SGL lead-free showed positive results, no problems expected in mass production.
B6E RF-solution implemented in Adonis and Aries – high power consumption in talk and standby mode believed to be related to B6E SW – currently under investigation.
New AAC/MP3-chip with integrated MMC-interface for SGL platform under development
Due to high unused stock of key components from R65 generation (SGL, Mozart), careful material management and component allocation to the new SGL products is required.

## Slide 3: SGoldLite G12 – Project Quantities and Stock