## Slide 1: Dorado – The Basic Tool Product Status Review 30 Mar 2005
– Strictly Confidential –
Copyright © Siemens AG 2005: Copying of this document and giving it to others and the use or communication of the contents thereof, are forbidden without express authority. Offenders are liable to the payment of damages. All rights reserved in the event of the grant of a patent or the registration of a utility model or design.
Michael Huebler, SPM / Juergen Jungbauer, SPM BA / Qi Zhao Hui (ZH), PM / Zhuang Xiao Qun (Raymond), PL-T
Notes: Product-approach to be named

## Slide 2: Executive Summary Dorado 1/2 Status 30.03.05
Profitability
Project Quality
Sales Fit
Product Quality
Strategy
Fit
Time-to-Market
Sales Fit
Customer requirements are met in terms of features, positive feedback on design
34€ launch price (38€ LAM), ASP 34€, heavily under pressure due to competition (e.g. Mot C117)
Volume reduced by 33% (7’7 vs. 11’5 at M1)
Profitability
Current BC below target with -4.83% (-12’7 Euro) profit.
Strategy Fit
Product addresses ultra-low market segment (<50US$) with high volume
Highly competitive segment

## Slide 3: Executive Summary Dorado 2/2 Status 30.03.05
Profitability
Project Quality
Sales Fit
Product Quality
Strategy
Fit
Time-to-Market
Time-to-Market
S2: 18.03.05
S3: 16.05.05
DS: 03.06.05 (11 days later than M1 plan)
S4: 16.06.05
Project Quality
Fast implementation of corporate planning tools in China require a close monitoring and coaching of Primavera planning
Product Quality
Components fulfill quality requirements
Low complexity of SW should lead to low return rates
Dependency on new platform (E-Gold Lite)

## Slide 4
Timeline MTA - Dorado
Dorado 900 (A70):
DS: 03 June 2005
Dorado 850 (A71):
DS: 28 July 2005

## Slide 5
Critical Path - Dorado

## Slide 6: Risks and Opportunities - Dorado
  Mechanics:
Technical Risks
  B2 housing failed in pre-drop test.
  -> Improve housing quality before B2 housing available
  B1+ keypad ESD test failed caused by ESD painting problem.
  -> Improve ESD painting for B2 UC
Description and measures
Impact
  Delay S3HW
  Re-measure SAR in B2
  Hardware:
  Late start of qualification to 32Mbit lead free flash -> Qualify a fallback lead free flash solution in advance
  No impact to DS, but will impact to delivery total lead free devices after Oct. 2005.
  Software / System Test
  For SW, same risks as Libra -> same measures as Libra
  ST: Slight HW difference between B1+ and B2 may cause FCC device selection difficulty based on B1+ SAR measurements. -> Study the feasibility to use B2 for both FCC & SAR.
  Bad SW maturity
  No impact to DS, but may delay FCC
Opportunities
Skip B2 Tape Out Re-use Libra B2 layout data Speed up B2 prototype run
Type Approval R&TTE could possible take 6 wks only (delta TA to Libra) PL-T to follow-up & monitor – during Type Approval phase
Faster ramp-up Ensure material availability for ramp-up at 20 May 2005 DS on 03 June 2005
Description and measures
Impact

## Slide 7: DTC Potential - Dorado
Two opportunities will be investigated and –if possible– introduced after launch:
Keypad
  Use all-silicone one-piece keypad with painting
  Similar option as in Aries
  Paint will rub off faster than with the current IMF caps.
  0.23~0.30 EUR savings
Conductive rubber contact below keypad
  Remove the conductive rubber, add rib to the part and use PVD process to apply conductive contact.
  Influence on ESD/EMC expected.
  0.10 EUR savings(?) tbc.
Attached: Cost Reduction Analysis by PT31 / C. Umland / 22.03.05 / with comments

## Slide 8: Ramp-Up: Demand vs. Plan

## Slide 9: Comparison Business Case The actual business case as of 30.03.05 indicates -12.7m EUR profit
  Lifecycle:
  With delivery start in June 2005 and phase out in March 2006 life cycle is 10 months. Due to the earlier launch of Canary the life cycle of Dorado has been cut by 3 months.
  Units:
  Volumes adjusted according to current DP (14.03.05). Regional split of total quantity of 7,662k is: 18% A-MEA (incl. CH), 30% WE/EE and 52% AM. Compared to M1 LC volumes declined due to a LC cut by 3 months and an overall lack of demand.
  ASP:
  Launch price of € 38 (LAM) and € 34 (RoW). Phase out price of € 35 (LAM) and € 31 (RoW). This leads to an ASP of € 34 over LC. Special price adjustments have been considered in connection with separate logistic and service concept.
  HK:
  Actual BoM based on GS Life cycle commitment minus DTC measurements of € 0.50 as these are reckoned to be secured.
  Conversion Cost (€ 3.72) based on production site split indicated by GO (SSMC 45%, Flex HUN 16%, MAN dom 31%, MAN exp 8%).
  Licenses based on input from K. Foitzik (15.03.05). Licenses include Tegic only (€ 0.12).
  CCQ:
  Service costs are calculated out of Return Rate of 5.0% and service costs per return of € 31.36. The significant price decline compared to M1 (€ 40) is based on a special service concept.
  R&D:
  R&D budget includes direct cost of € 4’4 and € 2’7 indirect costs.
  Marcom:
  MarCom based on revised budget indication from S&M (€ 1 per unit sold; 0% of T/O; € 0 HQ budget).
Deviation Analysis BC 30.03.05 vs. M1

## Slide 10: Business Case – Key Performance Indicators
General | Launch date | Jun 05 |  | COGS | Return rate | 5.0%
 | End of Life | Mar 06 |  |  | Cost per return | € 31.36
 | Positioning | Low |  |  | Other COGS in % of T/O | 1.30%
 |  |  |  |  | SCM costs in % of T/O | 2.00%
T/O | Units | 7,662k |  | OH | Total R&D cost. | € 6,517,460
 | Launch price * | € 34 |  |  | Therein indirect R&D cost | € 2,472,421
 | EOL price ** | € 31 |  |  | R&D in % of T/O | 2.48%
 | ASP | € 34 |  |  | Selling in % of T/O | 5.00%
 | Price decrease over life-cycle | -8.8% |  |  | Marketing cost | € 7,662,000
HK | Ø HK | € 29.70 |  |  | Marketing per unit sold | € 1.00
 | Ø Conversion cost | € 3.79 |  |  | Marketing in % of T/O | 0 %
 | Ø BOM | € 25.28 |  |  | Admin in % of T/O | 1.20%
 | BOM price decrease over life-cycle | -1.8% |  | Profit | Profit in M | - € 12.7 m
 | Licences | € 0.12 |  |  | Profit per Unit | - € 1.65
 | Ø Variant Adder | € 0.51 |  |  | Profit in % of T/O | - 4.83%
Note: * € 38 for LAM; € 35

## Slide 11: Business Case – Risks
  Time-to-Market
Business Case Risks
  Confidence Level: 90% for June Launch
Description
Impact
   -32’4 m EUR
  EBIT margin %
   -11.6 %
  Price
  10% price risk on ASP
   -27’6 m EUR
   -10.5 %
  Volume
  0% volume risk. Volume already significantly reduced due to life cycle cut by 3 months.
   - m EUR
   - %
  3% HK risk due to a changing split of production in Manaus and overall lower demand.
   -6’9 m EUR
   -2.6 %
  HK
  EBIT