## Slide 1: Libra – The Basic Community Phone Product Status Review 30 Mar 2005
– Strictly Confidential –
Copyright © Siemens AG 2005: Copying of this document and giving it to others and the use or communication of the contents thereof, are forbidden without express authority. Offenders are liable to the payment of damages. All rights reserved in the event of the grant of a patent or the registration of a utility model or design.
Michael Huebler, SPM / Marjolein de Vries, SPM BA / Qi Zhao Hui (ZH), PM / Liu Wei, PL-T
Notes: Product-approach to be named

## Slide 2: Executive Summary Libra 1/2 Status 30.03.05
Profitability
Project Quality
Sales Fit
Product Quality
Strategy
Fit
Time-to-Market
Sales Fit
Feature requirements met, positive feedback on design
Launch price 56€, expecting potential risk of price decrease, due to highly competitive segment
Volume reduced by 28.7% (4’377 vs. 6’140 at M1)
Profitability
Current BC below target with -1.96% (-4’4 Euro) profit.
Strategy Fit
Product addresses entry-level color segment (mid-range of A-Class) differentiating by ease of use and premium design
Highly competitive segment

## Slide 3: Executive Summary Libra 2/2 Status 30.03.05
Profitability
Project Quality
Sales Fit
Product Quality
Strategy
Fit
Time-to-Market
Product Quality
High quality perception due to premium design
Low complexity of SW should lead to low return rates
Lead project of new platform (E-Gold Lite, designed-to-cost)
Time-to-Market
S2: 25.02.05
S3: 22.04.05
DS: 20.05.05 (4 days later than M1 plan)
S4: 03.06.05
Project Quality
Fast implementation of corporate planning tools in China require a close monitoring and coaching of Primavera planning

## Slide 4
Timeline MTA - Libra
Libra 900 (A75):
DS: 20 May 2005
Libra 850 (A76):
DS: 22 July 2005

## Slide 5
Critical Path - Libra

## Slide 6: Risks and Opportunities - Libra
  Mechanics
Technical Risks
  Display static load test failed; Metal dome foil assembly needs to be improved;
  -> Increase the thickness of display lens w/o increasing the whole phone thickness (implementation was done);
  -> Improve the assembly process in the production line.
Description and measures
Impact
  Verify display static load test before Pilot run. No impact on DS.
  Hardware
  3 out of 100 times, the users has to press the ON button twice to switch on the phone. This error occurs with 5% of the B6E ICs.
  Software / System Test
  Power consumption in “normal case” and “worst case” is bigger than expected
  -> Need support from Comneon.
  -> Need multidisciplinary cooperation to solve this problem.
  Standby time and talking time of Libra in “normal case” and “worst case” will be decreased but still meet M1 document requirement.
Description
Impact
  B6E IC has HW bug;
  -> Ask supplier to redesign the B6E IC; Screening test on supplier
  test before they ship the IC to Siemens
Opportunities

## Slide 7: Ramp-Up: Demand vs. Plan

## Slide 8: Comparison Business Case The actual business case as of 30.03.05 indicates -4.4m EUR profit
  Lifecycle:
  With delivery start in May 2005 and phase out in June 2006 life cycle is 14 months.
  Units:
  Volumes adjusted according to current DP (14.03.05). Regional split of total quantity of 4,377k is: 15% A-MEA (incl. CH), 49% WE/EE and 36% AM. Volumes have been adjusted according to the current ramp up plan. Note: LAM demand is by far exceeding our assumptions at M1 whereas RoW demand is now expected to be way beyond.
  ASP:
  Launch price of € 56 and phase out price of € 45 leads to ASP of € 51 over LC. Price line for Q305 (from € 60 down to € 56) & Q405 (from € 54 up to € 56) have been adjusted according to the QPM (15.03.05)
  HK:
  Actual BoM based on GS Life cycle commitment. A BoM adder of 5% is included for LAM quantities due to Manaus production. Compared to M1 the BoM decreased by € 0.37
  Conversion Cost (€ 3.60) based on production site split indicated by GO (SSMC 60%, Flex HUN 32%, MAN 8%). Note: Due the current change in volume split production sites must be revised, especially with regard to Manaus production. Conversion costs will most likely increase.
  Licenses based on input from K. Foitzik (15.03.05). Note: Due to a new payable license fee for DRM license cost increased from € 0.32 up to € 0.68.
  CCQ:
  Service costs (based on CC BA input (04.03.05)) are calculated out of Return Rate of 5.5% (compared to M1 5.1%) and service costs per return of € 40.49 (at M1 € 36.97).
  R&D:
  R&D budget includes direct cost of € 4’8 - thereof € 0’6 for LAM 850 development - and € 4’7 indirect costs. To date € 2’1 direct cost have been spent.
  Marcom:
  MarCom based on revised budget indication from S&M (€ 1.5 per unit sold (€ 1.0 for last 3 months) plus 1% of T/O plus € 2’0 HQ budget).
Deviation Analysis BC 30.03.05 vs. M1

## Slide 9: Business Case – Key Performance Indicators
General | Launch date | May 05 |  | COGS | Return rate | 5.5%
 | End of Life | Jun 06 |  |  | Cost per return | € 40.49
 | Positioning | Low |  |  | Other COGS in % of T/O | 1.30%
 |  |  |  |  | SCM costs in % of T/O | 2.00%
T/O | Units | 4,377k |  | OH | Total R&D cost. | € 9,472,542
 | Launch price | € 56 |  |  | Therein indirect R&D cost | € 4,712,044
 | EOL price | € 45 |  |  | R&D in % of T/O | 4.44%
 | ASP | € 51 |  |  | Selling in % of T/O | 5.00%
 | Price decrease over life-cycle | -19.6% |  |  | Marketing cost | € 10,618,219
HK | Ø HK | € 40.11 |  |  | Marketing per unit sold | € 1.50
 | Ø Conversion cost | € 3.60 |  |  | Marketing in % of T/O | 1.00%
 | Ø BOM | € 35.13 |  |  | Admin in % of T/O | 1.20%
 | BOM price decrease over life-cycle | 6.0% |  | Profit | Profit in M | - € 4.4m
 | Licences | € 0.68 |  |  | Profit per Unit | - € 1.00
 | Ø Variant Adder | € 0.70 |  |  | Profit in % of T/O | - 1.96%

## Slide 10: Business Case – Risks
  Time-to-Market
Business Case Risks
  Confidence Level: 90% for May Launch.
Description
Impact
   -28’0 m EUR
  EBIT margin %
   -12.5 %
  Price
  10% price risk on ASP
   -22’1 m EUR
   -9.8 %
  Volume
  0% volume risk. Rather upside if A62 is taken out of the market in Q4/05
   - m EUR
   - %
  3% HK risk due to a changing split of production in Manaus and overall lower demand.
   -5’3 m EUR
   -2.4 %
  HK
  EBIT