## Slide 1: ARIES “The powerful imaging aide“ Product Status Report March 30, 2005
Roland Aubauer
Byrne Wilson
Michael Schuster
Ralf Kern

## Slide 2: Executive Summary 1/2 Status 30.03.05 – only minor but positive profitability deviations versus M1
Sales Fit
Good design acceptance
Scenario based on non-VDF exclusivity
ASP: 92€; CRP: 99€ launch, 75€ EOL
Risk: only 20% of forecasted 23% Market Share in EMEA 09-12/05 range (300k on risk) 1)
Risk: only minimum price can be realized for non-VF customers 2)
Profitability
Current 4,7% (=17‘5 €) profit vs. target 7,5% (= 27'9€)
Price/Volume risk has impact of -17’1m EUR on profit 1) 2)
TTM risk has impact of -1‘1m EUR on profit
Strategy Fit
Aries is necessary to stay with high volume product in VF live! (as well in other key customer’s) portfolio and to strengthen our low-end C-class w/ state of the art product
Addressable market (LC): 52' units, market share: 8% (EMEA 09-12/05 market share = 23%)
Profitability
Project Quality
Sales Fit
Product Quality
Strategy
Fit
Time-to-Market
QG
Notes: <number>
<footer>
<header>
<date/time>

## Slide 3: Executive Summary 2/2 Status 30.03.05 – no deviations versus M1
Time-to-Market
Milestone DS: Aug 19, 2005
Risk: delayed DS by 4 weeks
Major risk due to comparably short cycle time of 6,25 months (M1 – DS)
Project Quality
Detailed planning incl. resources available with M1 quality
Product Quality
Major risk due to very short timeline and working not according to standard process (mechanics and testing).
Reduced milestone content requirements (shortened environmental test periods) to achieve timeline.
Risk on minor quality issues for ramp up quantities
Profitability
Project Quality
Sales Fit
Product Quality
Strategy
Fit
Time-to-Market
QG
Notes: <number>
<footer>
<header>
<date/time>

## Slide 4: Milestone Trend Analysis Status 24.03.2005
Schedule:
M0 21.01.2005 
S0 28.01.2005 
M1 11.02.2005 
S15 04.03.2005 
S2 24.03.2005 
S25 20.05.2005
M2 10.06.2005
S3 08.07.2005
PS 15.07.2005
DS 19.08.2005
S4 30.09.2005
M3 30.09.2005
S2 declared 8 days in advance
Notes: <number>
<footer>
<header>
<date/time>
MTA shows that the project is on track
Anyhow, the dependency of the Ulysses platform SW caused a 2weeks shift of the delivery start
Nevertheless, the financial impact can be made up because of the high ROF with that the originally planned May volumes can be shifted completely to June

## Slide 5: Critical Path, Measure to be taken, Decision to be taken
Critical Path: Mechanics/EMC-Antenna >> TA approval & Product Quality at Launch
Expected delay:
best case -14 days (delivery to VF on 8.8.2005)
worst case +28 days (additional prototype run because of TA or major quality issues)
most likely 0 days
Measures & Decisions to be taken: when who
Implementation of HW tracking  Martin Krepcke
Rapid prototyping for early feedback loops B1.2 run  Ralf Kern
Fractional supplier deliveries until S3 Ralf Kern
Implementation Controlling
Weekly HW and SW tracking rounds Ralf Kern

## Slide 6: Comparison Business Case Compared to M1, the actual Business Case indicates +1’4 m EUR Profit
Lifecycle:
No change
Units:
No change
ASP:
No change
HK:
- BOM over LC decreased 0,19 € due to release button & user guide
- License Fees over LC increased 0,07 € due to ARM/3D Client
CCQ:
No change
R&D:
Reduction of 0’9 m € since M1 based on new R&D allocation forecast and P&L Report (PG85 EGK Factor still considered)
Marcom:
No change
Deviation Analysis
* w/o variant adder

## Slide 7: Business Case – Key Parameters Status as of 23rd March 2005
Launch date | August 05 |  | NRE | € 0
Positioning | C-Class |  | Return cost | € 44,44
Units | 4.050k |  | Return rate | 8,2% (12m)
Market share |  |  | Cost per unit sold | € 4,27
Launch price | € 97 |  | Other COGS in % of T/O | 3,3%
EOL price | € 73 |  | Marketing in % of T/O | 7,55%
ASP | € 92 |  | Marketing cost | € 28’1m
Price decrease over life-cycle | 25% |  | Marketing per unit sold | € 6,93
Ø HK | € 64,72 |  | Selling in % of T/O | 5,0%
Conversion cost | € 6,40 |  | R&D in % of T/O | 3,2%
Ø BOM | € 54,08 |  | Total R&D cost | € 11‘7 m
BOM price decrease over life-cycle | n.a. |  | Therein indirect R&D cost | € 5’2 m
UMTS license | n.a. |  | Admin in % of T/O | 1,2%
Other license/IPR/ patents (p.u.) | € 3,15 |  |  | 
Further Assumptions
BOM decrease over LC not applicable as BOM is only available as average value per FY
  Profit in Mio: € 17‘5
  Profit in % of T/O: 4,7%
  Profit per Unit: € 4,32
Profitability

## Slide 8: Business Case – Risks & Measures
  Time-to-Market
Business Case Risks
  Delayed launch due to short timeline (as reported M1)
Description
Impact
   1’1 m EUR
  EBIT
  EBIT margin %
   0,03 %
  Price
  Minimum price line realized over Lifecycle (as reported M1)
   13’1 m EUR
   3,50 %
  Volume
Target Market Share not realized in EMEA during Q1 FY05 leading to a reduction of 300ku (as reported M1)
Launch in China cancelled by region affects all other Chinese SW variants
Launch depending completely on VF approvals
   4’0 m EUR
   1,10 %
  Not applicable
  HK
Measures to secure BC
Get volume forecasts on country / customer level (Roland Aubauer) from Area Operation Managers until CW15
Close failure tracking in VF approval phase (Roland Aubauer)

## Slide 9: SGL2005 products ARIES status
Blue marked text is new, black is old, red will serve as indicator for the red traffic light
High/Low light
S2 declared – 1 week BEFORE M1-schedule
Decision on silver-copper EMI painting for metallization in upper case
Most critical issues from environmental tests: MDF foil broken, static load not passed, joystick centricity critical
Major threats
Phönix, Sirius, Adonis, Aries in short intervals on one SW data base (ZIDB)
HW
Body Worn SAR@0cm too high, BUT currently no blocking point with respect to legal issue >> Counter measure implemented and tested positive >> 1.97W/kg(10g)@0cm (1TX) >> OK >> 3.94W/kg(10g)@0cm (2TX) >> hint in user manual/ NEW SIEMENS guideline
SW
SGL2005 defect priorization & tracking finally started
z-IDB4 for DS SW stabilization will start on 18th of APRIL / Maintenance in BEJ (DS schedule: 1) Phönix/Sirius, 2) Adonis, 3) Aries)
Mechanics
Quality of vacuum metallization currently not sufficient >> Switch to silver-copper EMI painting decided; spec conformity of JIGs/metallization area to be confirmed
NOTE: Yellow traffic light, because B1 evaluation not finalized & B1+ must have TA maturity