## Slide 1: Pegasus – Basic Organizer Phone Product Status Report, 30.3.05
– Confidential –
Copyright © Siemens AG 2005: Copying of this document and giving it to others and the use or communication of the contents thereof, are forbidden without express authority. Offenders are liable to the payment of damages. All rights reserved in the event of the grant of a patent or the registration of a utility model or design.
Vinzenz Greger, SPM / Diana Stähler, SPM BA / Kirsi Lehtonen, PM / Susan Tan, PL-T .
Notes: Product-approach to be named

## Slide 2: Executive Summary Pegasus 1/2 Status 14.03.05
Profitability
Project Quality
Sales Fit
Product Quality
Strategy
Fit
Time-to-Market
Sales Fit
Feedback generally positive
Price pressure expected in this segment
Profitability
Current BC with 4,0% (12’1 Euro) profit above target
HK improvement by 4.- Euro very likely (~19’0 Euro positive profit impact)
ASP risk quantified with 2.- Euro
In total, reasonable confidence that target can be met.
Strategy Fit
Product addresses mass market segment in premium entry level (AX), also attracting low-end business users
Pegasus supports new positioning of A-Class segment (ease of use in premium design) as flagship product
AX75
Pegasus
Notes: <number>
<footer>
<header>
<date/time>

## Slide 3: Executive Summary Pegasus 2/2 Status 14.03.05
Profitability
Project Quality
Sales Fit
Product Quality
Strategy
Fit
Time-to-Market
Time-to-Market
Medium to high confidence that DS will be met
S2: 25.03.05
S3: 20.05.05
DS: 17.06.05 (18 days later than M1 plan)
S4: 15.07.05
Project Quality
Reasonable quality of Primavera planning
Product Quality
Moderate TTM-risk because of new platform (E-GOLD-lite)
AX75
Pegasus
Notes: <number>
<footer>
<header>
<date/time>

## Slide 4
MTA Pegasus Status 26.3.05
As presented in PSR 23.2.
S2-Status:
ST Not declared yet because of open issues with High power consumption (normal and worst case, platform-issue). One potential risk or problem found. Infineon will provide components to BJ BB for measurements until end of this week.
CCQ: Waiting for for team to sign.
Notes: <number>
<footer>
<header>
<date/time>

## Slide 5: Critical Path, Measure to be taken, Decision to be taken
Critical Path:
The environmental tests are in critical-path. Pegasus already has priority 1 and shortest cycle-time
Type-approval may even be finished earlier as expected.
Still issues with power-consumption (standby / talk-time). M1 target can be committed,
but new optimized power saving concept can only be implemented in 2nd SW-release.
IrDA-Feature is implemented and can be tested in Factory, but because of current testing in
normal mode,2-3 sec gap to target cycle time, line capacity is endangered.
Measures & Decisions to be taken:
-
Implementation Controlling
Weekly tracking of scheduled actions by Rea / PD-Team (see top AIs).

## Slide 6: Comparison Business Case
  Lifecycle and units:
  Delayed launch of 1 month leads to a
  LC shortage
  loss of 311k
  Loss of € 6’1 Sales Margin
  Total units stabilized due to 850 variant
  ASP:
  Decrease of launch price from € 70,- to € 67,-;
  In Q1 drop from € 65,- to € 64,-
  HK:
  Significant BoM improvement mainly driven by second source for display
  CCQ:
  No changes
  R&D:
  Increase due to 850 variant
  Marcom:
  Decrease of push rate from € 3,50 / unit to € 3,- / unit
Deviation Analysis M1 vs. 30.03.05
Pegasus

## Slide 7: Business Case – Key Performance Indicators
General | Launch date | June 05 |  | COGS | Return rate | 6,77%
 | End of Life | June 06 |  |  | Cost per return | € 40,14
 | Positioning | Low |  |  | Other COGS in % of T/O | 1,30%
 |  |  |  |  | SCM costs in % of T/O | 2,00%
T/O | Units | 5.130 k |  | OH | Total R&D cost. | € 10.760.770
 | Launch price | € 67 |  |  | Therein indirect R&D cost | € 3.877.260
 | EOL price | € 55 |  |  | R&D in % of T/O | 3,34%
 | ASP | € 62,77 |  |  | Selling in % of T/O | 5,00%
 | Price decrease over life-cycle | -18,0% |  |  | Marketing cost | € 20.799.501
HK | Ø HK | € 42,55 |  |  | Marketing per unit sold | € 4,05
 | Ø Conversion cost | € 4,98 |  |  | Marketing in % of T/O | 6,46%
 | Ø BOM | € 35,92 |  |  | Admin in % of T/O | 1,20%
 | BOM price decrease over life-cycle | -16,2% |  | Profit | Profit in Mio | €27,7m
 | Licences | € 0,93 |  |  | Profit per Unit | € 5,39
 | Ø Variant Adder | € 0,72 |  |  | Profit in % of T/O | 8,6%
Pegasus

## Slide 8: Technical and Business Case Risks - Pegasus
Pegasus
  Time-to-Market
Business Case Risks
  Confidence Level: 90% for June Launch, 10% for July Launch
Description
Impact
   3’9 m EUR
  EBIT
  EBIT margin %
   0,5 %
  Price
  Sales feedback as per latest Q-Gate: 65€ seen --> 3% price risk (current target 67€)
   5,7 m EUR
   1,6 %
  Volume
  Current ROF indicates that M1 volume-targets targets might not be fulfilled. Risk: Lose 30% of volume.
   12’1 m EUR
   1,7 %
  HK
  Latest HKs (S2-calculation 14.2.) are considered in current BC.
   0 m EUR
   0 %
  Mechanics:
Technical Risks
  Everything on track.
Description and measures
Impact
  No impact expected
  Hardware:
  IrDA-Test in production: Cycle-time not reached yet.
  IrDA is not fully implemented.
  Analogue-switch not released yet because of missing tests with IrDA.
  Higher conversion cost.
  Reworks/new layout. TTM-risk.
  Software / System Test
  IrDA-feature not fully implemented.
  Standby/Talk-time can not be confirmed with current HW/SW-version. 90% probability that this is connected to SW.
  TTM-risk
  Bad Std.by/Talk. performance
  Introduction of ‘Rel 2’ with better performance in Q4.
  Others
  -
  -

## Slide 9: EGL products Pegasus
Pegasus
Blue marked text is new, black is old, red will serve as indicator for the red traffic light
Schedule/PV/Milestones:
M0 23.07.04  S15 15.11.04  S3 20.05.05
S0 17.08.04  S2 25.03.05 DS 17.06.05
M1 28.09.04  S25 05.04.05 S4 15.07.05
M3 22.07.05
Status next milestone:
S2 (25.03.): Blocked due to high power consumption (ST, CCQ).
Major threats
big power consumption unclear if SW or HW. Some bugs such as 474E,55B0 (S25 relevant for ST), etc.. SW and COMNEON are investigate in parallel.
EMC/Antenna
B1+ new self interference and ESD problems (upper bar keypad area) found.
SW
See main threats
Irda current factory testing in normal mode,2-3 sec gap to target cycle time
ST
High Power consumption ST S2 blocking point.
Prototype run:
B6E B1+ and LAM B1 run finished!
AX75
Pegasus

## Slide 10: Status LAM 850-version
LAM variant
M0 23.07.04
S0 17.08.04
M1 28.09.04
S15 04.03.05
S2 26.04.05
S25 02.06.05
S3 05.08.05
Pilot Series Start 05.08.05
Production Start 19.08.05
S4 30.09.05
Delivery Start 02.09.05 vs. 16.6.05 (M1)

## Slide 11: Backup

## Slide 12: Status Ramp-Up / Demand vs. Capacity
Status RU:
RU-team started Beginning of March – fully staffed.
Initial forecast covers ~50% of capacity / M1-volume
Confidence given that forecast will imrove significantly after CeBIT-Update / delivery of Acquisition-samples.

## Slide 13
Risks and Actions Pegasus
Notes: <number>
<footer>
<header>
<date/time>
Measures to be dicsuessed with Claus Ziegler (EGOLDlite)