## Slide 1: SG2 products – Polaris -> Status Update
Polaris
Blue marked text is new, black is old, red will serve as indicator for the red traffic light
milestones, timeline, Prima Vera planning
M0 -> Q-Gate not passed:
Status reached (except SW relevant WP): MD; HW; LCM (NPI 2&3)
Status open: ST; SW; QA
S0:
Status reached (except SW relevant WP): MD
Status open: HW; LCM (NPI 2&3); ST; SW; QA
Prima-Vera Planning
Not completed due to missing links to platform
All HW relevant WP in time with “Target S15”: 29.07.05
technical aspects, next steps
Key Caps –Aluminium Caps not feasible -> going for stainless steel
A1: PCBA Build: 15.04.05; SLA Build: 06.06.05 ;WB TO: 18.04.05
major threats
TimeLine:
M0: 3.5 month delayed
S2: 1 month delayed (based on SW Platform DL C25 planning 09/05)
Time between M1 and AS app. 3month only (based on M1 08/05 PL-T assumption)
BC:
Target cost gap of app. 7,-EUR due to reduced ASP and additional PD Budget (1/6 of X75 platform cost to be covered by Polaris)

## Slide 2: SG2 products – Polaris -> Decisions
Blue marked text is new, black is old, red will serve as indicator for the red traffic light
Decisions Due:
Declaration of M0 Milestone
Release of Invest/ Budget till M0 (has been passed on to PBM Head as well)
  ->PD Budget till M0 (6/05) 1.7Mio EUR (including SCM Budget 135k EUR)
  ->Tooling due till M0 (6/05) 1.478Mio EUR
Proposal of Polaris Project Team:
Do not declare M0 Polaris due to missing input from platform, esp. missing timeline
Continue WP as planned with preliminary Time Schedule and release Budget/ Invest in order to minimize DS delay