## Slide 1: Status SG2 products - Swift/ Ibis
Swift/
Ibis
milestones, timeline, PrimaVera planning
Swift M0-HW status reached on 05.04.2005 (w/o SW, ST, QM)
Swift S0-HW status target 22.04.2005 (w/o SW, ST, QM)
Ibis M0-HW target end of April 2005 (w/o SW, ST, QM)
Swift rough planning done, alignment of detailed plans after B1 run w/o software input not possible
technical aspects
Swift S0-HW shifted by 1week, supplier selection process still ongoing >> no agreement between mechanics and procurement yet
Currently one layout but already two PCBs for Swift and Ibis, high risk that two layouts are necessary because of RF performance issues >> decision after Swift A1 evaluation
Platform display concept is a problem for Swift antenna performance because of flex length >> probability that two displays with different flex length are needed is higher than 50%
Resources of several lines shifted because of Kestrel, teams are now distributed on several sides >> changing team members, higher co-ordination effort and increased risk of communication gaps
major threats
Ibis M0-HW endangered because of blocked and shifted mechanics resources >> by Kestrel
Swift BOM target cannot be met >> currently 14€ below target; CRW workshop on April 18th.
Platform SW timeline missing >> detailed project planning not possible, no DS commitment

## Slide 2: Next project steps and needed decisions SG2 products - Swift/ Ibis
next project steps – short and mid term
Swift S0-HW milestone declaration
Swift A1 run E05.2005
Ibis M0-HW and S0-HW declaration
Needed decisions how to continue
Swift budget release 1‘050€ budget needed for Swift long runners in mechanics and hardware for time until E05.2005 (700k€ tool invest, 250k€ samples, 100k€ display NRE) >> Release budget for Swift to continue
Communication of Swift DS delay (and later also Ibis DS status)
  Given dates: M0-SW M06.2005
  needed of stable type approval software B12.2005
  Assumption: M1-SW M08.2005 (only 2 months after M0-SW)
  Results in only 3,5 months time between M1-SW and need for TA-SW
  >> PLT statement: DS for Swift not possible, shift of “several months” to be expected
Decision if project M1-HW and further S-Milestones need to be declared w/o SW
  No SW input regarding support of prototypes at the time of M1-HW (B05.2005)
  M1-HW declaration w/o SW will have too many exceptions
  No real M1 commitment possible
  >> PLT proposal: Team commits to performance description and waits for M1-SW
Swift/
Ibis