## Slide 1: Minos Status: Timeline until DS 15.09.05 critical
Project Status, Timeline, Milestones:
- DS (15.09.05) is only valid if preconditions are fulfilled
Preconditions for reaching DS on 15.09.05:
- B1+ evaluation must be finished (B1+ SW content required)
- B2-Tapeout not later than 04.05.05
- Stabilized IDB-SW (not R-IDB) available by end of CW19 (S25_TA_freeze)
- B2 HW is final version
- RF-parameters are final
- 100 reference devices are available on 27.05.05 for ST2
- Minos must have first priority in prototype shop (CW20 – CW23)
=> due to lack of production capacity [five products at the same time]
Minos