## Manual (hidden)
BJ-Projects in realization | [30 empty] | MD PM BA (BJ)
|  |  |  | Time to Market |  |  |  |  | Financials
| PG | Chip | Product | [5 empty] | Life Cycle | [6 empty] | Profit in FY05 |  |  |  | EBIT FY05 | Profit in FY06 |  |  |  | EBIT FY06 | Profit in FY07 |  |  |  | EBIT FY07
[6 empty] | Delivery | Status | Trend | Volume | S. Margin | S. Margin | Profit | Profit | Status | Trend | Q1 | Q2 | Q3 | Q4 | Total | Q1 | Q2 | Q3 | Q4 | Total | Q1 | Q2 | Q3 | Q4 | Total
[6 empty] | Start |  |  | (in mill. | (in mill. €) | (in %) | (in mill. €) | (in %) |  |  | (in | (in | (in | (in | (in | (in | (in | (in | (in | (in | (in | (in | (in | (in | (in
[9 empty] | units) | [6 empty] | mill. €) | mill. €) | mill. €) | mill. €) | mill. €) | mill. €) | mill. €) | mill. €) | mill. €) | mill. €) | mill. €) | mill. €) | mill. €) | mill. €) | mill. €)
| PG85 | EGL | Quail | Target | M-alpha (2C') | 2006-01-17 |  |  | 2.525 | 61.9635 | 36.09%
|  |  |  | Current | 2005-03-25 | 2006-02-06 |  |  | 3.365 | 30.7589 | 15.34% | -12.3148 | -6.143% |  |  |  | -0.2882 | -1.419 | -1.839 | -3.5462 | -2.25 | 0.77765 | 0.24667 | -4.199 | -5.4247 | -3.0379 | -0.30484 |  |  | -3.3428
|  |  | pre-M0 | Deviation | weeks | 2.8571 |  |  | 0.84 | -31.2046 | -20.75%
| PG85 | EGL | Flamingo | Target | M1 | 2005-10-24 |  |  | 2.95 | 91.7498 | 37% | 25.3945 | 10.24% |  |  | -0.28256 | -2.2475 | -2.6547 | -4.3239 | -9.5087 | 6.9992 | 12.1855 | 10.3044 | 3.17 | 32.659 | 2.2442 |  |  |  | 2.2442
|  |  |  | Current | 2005-03-15 | 2005-10-05 |  |  | 2.95 | 91.7498 | 37% | 25.3945 | 10.24% |  |  | -0.28256 | -2.2475 | -2.6547 | -4.3239 | -9.5087 | 6.9992 | 12.1855 | 10.3044 | 3.17 | 32.659 | 2.2442 |  |  |  | 2.2442
|  |  | M1 | Deviation | weeks | -2.7143 |  |  | 0 | 0 | 0% | 0 | 0% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| PG85 | EGL | Pelican | Target | M-alpha (2C') | 2006-03-15 |  |  | 2.15 | 62.4145 | 41.35%
|  |  |  | Current | 2005-03-15 | 2006-03-15 |  |  | 2.43 | 49.3337 | 29.55% | 10.4961 | 6.286%
|  |  | M-alpha | Deviation | weeks |  |  |  | -0.28 | 13.0808 | 0.11807
| PG75 | EG | Puma | Target | M1 | 2004-09-06 |  |  | 5.728 | 74.4044 | 18.96% | 10.6114 | 2.704% |  |  | 14.4437 | 1.6143 | -0.43787 | 1.0365 | 16.6566
|  |  |  | Current | 2005-04-19 | 2004-09-06 |  |  | 4.5144 | 50.4765 | 18.83% | -8.0068 | -2.986% |  |  | 10.4804 | -5.1373 | -1.4607 | -3.1125 | 0.77004
|  |  | launched | Deviation | weeks | 0 |  |  | -1.2136 | -23.928 | -0.1318% | -18.6182 | -5.69% |  |  | -3.9633 | -6.7515 | -1.0228 | -4.149 | -15.8866
| PG75 | EGL | Pegasus | Target | M1 | 2005-05-26 |  |  | 5.111 | 80.5855 | 24.72% | 5.5723 | 1.709% |  |  | -2.004 | -2.9916 | -0.88771 | 6.0067 | 0.12334 | 8.4863 | 0.78563 | -2.6346 |  | 6.6373
|  |  |  | Current | 2005-04-19 | 2005-06-17 |  |  | 0 | 0 | 0% | 0 | 0% |  |  | 0 | 0 | 4.2461e-08 | 4.2461e-08 | 8.4921e-08 | 0 | 0 | 0 |  | 0
|  |  | pre-M2 | Deviation | weeks | 3.1429 |  |  | -5.111 | -80.5855 | -24.72% | -5.5723 | -1.709% |  |  | 2.004 | 2.9916 | 0.88771 | -6.0067 | -0.12334 | -8.4863 | -0.78563 | 2.6346 |  | -6.6373
| PG65 | SGL | Leopard | Target | M1 | [14 empty] | 0 |  |  |  |  | 0
|  |  |  | Current | 2005-04-12 | [14 empty] | 0 |  |  |  |  | 0
|  |  |  | Deviation | weeks | 0 |  |  | 0 | 0 | 0% | 0 | 0% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Target | M1 | [14 empty] | 0 |  |  |  |  | 0
|  |  |  | Current | 2005-04-12 | [14 empty] | 0 |  |  |  |  | 0
|  |  |  | Deviation | weeks | 0 |  |  | 0 | 0 | 0% | 0 | 0% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Target | M1 | [14 empty] | 0 |  |  |  |  | 0
|  |  |  | Current | 2005-04-12 | [14 empty] | 0 |  |  |  |  | 0
|  |  |  | Deviation | weeks | 0 |  |  | 0 | 0 | 0% | 0 | 0% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Target: Basis is Scenario 2C-Strich; no detailed figures underneath Sales Margin as well as for break-down to quarters
|  | Ready to copy: |  |  |  | Traffic light - Time to market: |  |  |  |  | automatic fill-in |  |  | Traffic light - Time to market: |  |  |  |  | manual entry
[6 empty] | green | No delay or earlier than target | [6 empty] | green
[6 empty] | yellow | Delay to target is < 4 weeks | [6 empty] | yellow
[6 empty] | red | Delay to target is > 4 weeks | [6 empty] | red
-
[6 empty] | Trend - Time to market: |  |  |  |  | manual entry
|  |  |  | ü |  |  | Positive trend, e.g. signiificant positive delta to last reported value
No significant change
Negative trend, e.g. signiificant negative delta to last reported value

## Input
PHE Cockpit Chart 2G CW03 | [6 empty] | 2006-01-17
Products in realization (M0 - S4)
|  |  |  | Next | Time to Market |  |  |  |  | Financials (last Milestone) | [5 empty] | Return Rate |  |  |  |  | Status
|  |  |  | Mile- |  |  | Delivery | Status | Trend | R&D effort | BOM | Conversion | thereof | Status | Trend | RR | RR | RR | Status | Trend
|  | Chip | Product | stone |  |  | Start |  |  | (in mill. €) | (in p/u. €) | Cost | Licenses/Royalties |  |  | HW | SW | total |  |  | Achievements | Issues | Next Steps | Quantity(today) | Total costs + R&D effort | Deviation * Quantity +R&D effort
[12 empty] | (p/u. €) | (p/u. €) |  |  | (in %) | (in %) | (in %)
| PG85 | SG2 | Hydra | S3/DS | Target | at M1 | 2005-09-15 |  |  | 49.6 | 102.5 | 10.64 | 5.79 | -2.325% |  | 6 | 6 | 12 |  |  | SW approval from E-Plus, O2, Russia, Portugal, Switzerland (Sunrise), Middle East ,….. available / Prod. capacity starting from 02/06 improved (200K + 50K flex) / Limited DS 12.12.2005 | -SW quality / S3 basic software postponed to the 9th February - Blocked stock (T9 Bug) need to be rebooted but unfortunately only limited reboot capacity available Next reboot capacity in CW04 available - Epson display "contrast issue" - China production will be shifted from SSMC to Souzhou (China) | - New software SVN 16 with Orange and TMO bug fixes available - Approval from TMO with SVN 16 expected / Orange approval with SVN18 (26.01.06) expected | 973000 | 110085269.6 | -2558986.9
|  |  | SL75 | 2006-02-09 | Current | today | 2006-02-09 |  |  | 52.7 | 101.39 | 9.12 | 4.83 |  |  | 6 | 20 | 26
|  |  | TPM Mues-Hane |  | Deviation | weeks | 21 |  |  | 3.1 | -1.11 | -1.52 | -0.96 |  |  |  |  | 14
| PG85 | SG2 | Minos | S3/DS basic | Target | at M1 | 2005-09-15 |  |  | 57.5 | 80.04 | 8.3 | 5.15 | 3.803% |  | 6 | 6 | 12 |  |  | December 2005 production 60,2 k 34 k invoiced (31.12.2005); O2: unlimited approval of SVN13 | SW quality does not match DS requirements NCCPI ~137.000; Reboot scenario in CW02/04/05 (T9 Bug) to release blocked stock of 18 k | S3 basic / DS basic 09.02.2006 with an NCCPI <= 80.000 | 615000 | 54329157.5 | 2066398.3
|  |  | S75 | 2006-02-09 | Current | today | 2006-02-09 |  |  | 55.8 | 83.63 | 8.07 | 3.87 |  |  | 6 | 20 | 26
|  |  | TPM Hombeck |  | Deviation | weeks | 21 |  |  | -1.7 | 3.59 | -0.23 | -1.28 |  |  |  |  | 14
| PG75 | SG2 | Polaris | S3 HW | Target | at M1 | 2006-02-24 |  |  | 30.5 | 59.21 | 6.19 | 2.59 | -0.7339% |  | 7 | 4 | 11 |  |  | As Basic declared delta PTR done | - Pilot delayed 2weeks due to necessary ToolChange at ChiCheng (Front Cover) - S3HW delayed 2 weeks due to necessary mech. rework. But agreement given to start Pilot with limiuted amount - S3 SW delayed 2 weeks due to SW Platform | Perform B3 Run in order to proof mech. Rework, Pre-condition for S3HW | 1134000 | 74163630.5 | -544319.5
|  |  | S68 | 2006-01-27 | Current | . | 2006-02-24 |  |  | 31 | 58.9 | 6.02 | 2.47 |  |  |  |  | 0
|  |  | TPM T. Neumann |  | Deviation | . | 0 |  |  | 0.5 | -0.31 | -0.17 | -0.12 |  |  |  |  | -11
| PG75 | EGL | Leopard ref. |  | Target | M1 | 2005-02-04 |  | ü | 2.255 |  | 0.26589 | 0.26589 |  |  | M1 |  | 2005-02-04 |  | ü
[5 empty] | Current | 2005-10-25 | 2005-02-04 |  |  | 1.3811 |  | -8.6431 | -8.6431 |  |  | 2005-10-25 |  | 2005-02-04
[5 empty] | Deviation | weeks | 0 |  |  | -0.87395 |  | -8.909 | -8.909 |  |  | weeks |  | 0
| PG85 | SG2 | Swift | S25 | Target | at M1 | 2006-04-28 |  |  | 57.7 | 75 | 7.66 | 4.79 | 0% |  | 6 | 6 | 12 |  |  | - B2 PCB first shot done in CW2, soldering process stable now - First Perlos pre-assembled and tested B2 parts send out to KLF | - KHVatec change of painting fab before pilot - Quality of Perlos assembly - Stability of automatic tests at Perlos | - B2 first phone assembly - B2 drop tests - SCM, SW&ST S25 | 2024000 | 167303897.7 | 0
|  |  | EL71 | 2006-02-03 | Current | today | 2006-04-28 |  |  | 57.7 | 75 | 7.66 | 3.86 |  |  |  |  | 0
|  |  | TPM J. Kockmann |  | Deviation | weeks | 0 |  |  | 0 | 0 | 0 | -0.93 |  |  |  |  | -12
| PG85 | SG2 | Phillipe | S2/S25 | Target | at M1 | 2006-05-29 |  |  | 7.6 | 73.33 | 7.81 | 0.37 | -6.704% |  | 5.4 | 3.6 | 9 |  |  | - S15 declared on January 6th (as scheduled) - Delivery schedule for plastic parts confirmed to be on track by supplier Nolato | - B1 series: MMI modules not from right assembly tool. Quality risk - B1 series: MMC tray 1 week later than required. Alps pushed to improve. Quality risk | - Evaluation 1st out of tool parts (e.o. Jan) - B1 series (begin of Feb) - DS review 27.02.06 | 621000 | 50387947.6 | -3378239.2
|  |  | C81 | 2006-03-10 | Current | today | 2006-05-29 |  |  | 8.4 | 67.63 | 8.07 | 5.23 |  |  |  |  | 0
|  |  | TPM C. Dalmose |  | Deviation | weeks | 0 |  |  | 0.8 | -5.7 | 0.26 | 4.86 |  |  |  |  | -9
| PG75 | SG2 | Hawk | M0 | Target | < M0 | 2005-06-30 |  |  | n.a. | n.a. | n.a. | n.a. | #DIV/0! |  | 5.4 | 3.6 | 9 |  |  | - Team nearly complete. - Kickoff planned for this week | - new Orange Requir. under discussion
|  |  | ME85 | 2005-12-23 | Current | today | cancelled |  |  | n.a. | n.a. | n.a. | n.a. |  |  |  |  | 0
|  |  | TPM Dr. Röhrig |  | Deviation | weeks | #VALUE! | [10 empty] | -9
| PG85 | SG2 | Obsidian | S0 | Target | at M0 | 2006-08-30 |  |  | 16.3 | 61.22 | 9.97 | 4.77 | -2.107% |  | 5.4 | 3.6 | 9 |  |  | - MD Supplier Pre-selected - S0 declared by MD, SCM3 & PE | - S0 declarations missing from SQM due missing qualification of PVD process (SQM and CPM is traveling to China CW03 for verification) - M1 declaration delayed by one week due system breakdown in MD CAD system | - PVD process clearence in CW03 - Securing B1 prototype run in all skills - M1 declaration | 3793000 | 270023686.3 | -5689502.4
|  |  | SLxx | 2005-12-23 | Current | today | 2006-08-30 |  |  | 13.9 | 63.81 | 5.88 | 1.61 |  |  |  |  | 0
|  |  | TPM T. Stokholm |  | Deviation | weeks | 0 |  |  | -2.4 | 2.59 | -4.09 | -3.16 |  |  |  |  | -9
| PG85 | SG2 | Swan | S0 | Target | at M0 | 2006-09-30 |  |  | 8.7 | 58.5 | 5.1 | 5.66 | 20.66% |  | 5.4 | 3.6 | 9 |  |  | >> CPM-Decision for new design >> S0 delay = 2 weeks (27.01.) >> 1st M1 SW planning workshop held (results under evaluation by TTM SW team) | > S0&M1 will be delayed by 2 weeks due to decision to take new design > Aplix & Teleca contracts still NOT fixed (no commercial/technical aligned weekly status available) | > fix Aplix & teleca contract (again) > Preparation SW planning follow up > A1-TapeOut (decision if PCB or Wingboard pending) | 2835000 | 180306008.7 | 37251940
|  |  | C61(tbc) | 2006-01-13 | Current | today | 2006-10-10 |  |  | 48.7 | 70.44 | 6.3 | 5.66 |  |  |  |  | 0
|  |  | TPM R. Kern |  | Deviation | weeks | 1.4286 |  |  | 40 | 11.94 | 1.2 | 0 |  |  |  |  | -9
| PG75 | SG3 | Diamond | M0 | Target | at Ma | 2007-02-16 |  |  | n.a. | n.a. | n.a. | n.a. | #DIV/0! |  | tbd | tbd | tbd |  |  |  |  | * Ma-Alignment of Design and mech.concept * Ma-Alignment of required Feature * Ma Alignment of HW/SW concept * Ma planned for 19th Jan
|  |  | tbd | 2006-03-17 | Current | today | 2007-02-16 |  |  | n.a. | n.a. | n.a. | n.a. |  |  |  |  | 0
|  |  | TPM A. Betting |  | Deviation | weeks | 0
| PG85 | SG2 | Sandpiper | M0 | Target | at Ma | 2007-03-23 |  |  | n.a. | n.a. | n.a. | n.a. | #DIV/0! |  |  |  | 12
|  |  | SLxx | 2006-04-14 | Current | today | 2007-03-23 |  |  | n.a. | n.a. | n.a. | n.a. |  |  | 5 | 10 | 15
|  |  | TPM tbd. |  | Deviation | weeks | 0 | [10 empty] | 3
| PG85 | SG2 | Lolite | M0 | Target | at Ma | 2007-07-20 |  |  | n.a. | n.a. | n.a. | n.a. | #DIV/0! |  |  |  | 9
|  |  | Cxx | 2006-10-13 | Current | today | 2007-07-20 |  |  | n.a. | n.a. | n.a. | n.a. |  |  | 5 | 5.5 | 10.5
|  |  | TPM tbd. |  | Deviation | weeks | 0 | [10 empty] | 1.5
| PG75 | SGL | Emerald | M0 | Target | at M1 | 2007-07-20 |  |  | n.a. | n.a. | n.a. | n.a. | #DIV/0! |  |  |  | 4.5
|  |  | Axx | 2006-10-13 | Current | today | 2007-07-20 |  |  | n.a. | n.a. | n.a. | n.a. |  |  | 2 | 2 | 4
|  |  | TPM tbd. |  | Deviation | weeks | 0 | [10 empty] | -0.5
Products in Life Cycle (S4 - M4)
| PG85 | SG2 | Condor | S4 | Target | at M1 | 2005-11-25 |  |  | 9.9 | 56.3 | 6.47 | 3.53 | -8.73% |  | 5.4 | 3.6 | 9 |  |  | * Qualification of 2nd RF Solution (Hitachi) for Condor and Aries started in cw02 | * parting-line optimisation in realisation * 3rd Color for Condor still open - PM decision expected in cw04 (not S4 relevant) | * cw03: finish tests with opti. parting-line * 20.01.06: final S4 Declaration * cw05:SVN24(for last bugfixes on ZIDB4) * cw07 release 2nd RF solution (Hitachi) | 1302000 | 81726549.9 | -7134960.6
|  |  | ME75 | 2006-01-20 | Current | today | 2005-11-14 |  |  | 9.3 | 51.12 | 6.17 | 1.42 |  |  |  |  | n.a.
|  |  | C. Aschmoneit |  | Deviation | weeks | -1.5714 |  |  | -0.6 | -5.18 | -0.3 | -2.11 |  |  |  |  | #VALUE!
| PG75 | SGL | Cormorant | M4 | Target | at M1 | 2005-10-19 |  |  | 4.9 | 44.82 | 5.82 | 2.69 | -2.231% |  | 5.4 | 3.6 | 9 | [5 empty] | 2650000 | 134196004.9 | -2994501
|  |  | Axx | xx.xx.xxxx | Current | today | 2005-10-12 |  |  | 3.9 | 43.61 | 5.9 | 1.26 |  |  |  |  | n.a.
|  |  | Name of TPM |  | Deviation | weeks | -1 |  |  | -1 | -1.21 | 0.08 | -1.43
| PG75 | EGL | Leopard ref. |  | Target | M1 | 2005-02-04 |  | ü | 2.255 |  | 0.26589 | 0.26589 |  |  | M1 |  | 2005-02-04 |  | ü
[5 empty] | Current | 2005-10-25 | 2005-02-04 |  |  | 1.3811 |  | -8.6431 | -8.6431 |  |  | 2005-10-25 |  | 2005-02-04
[5 empty] | Deviation | weeks | 0 |  |  | -0.87395 |  | -8.909 | -8.909 |  |  | weeks |  | 0
| PG85 | n.a. | Wega | M4 | Target | at M1 | 2006-02-24 |  |  | n.a. | n.a. | n.a. | n.a. | #DIV/0! |  |  |  | 12 |  |  | - comments | - comments | - comments
|  |  | CL75 | xx.xx.xxxx | Current | today | 2006-02-24 |  |  | n.a. | n.a | n.a | n.a |  |  | 5 | 10 | 15
|  |  | Name of TPM |  | Deviation | weeks | 0 | [10 empty] | 3
| PG85 | n.a. | Aries | M4 | Target | at M1 | 2006-04-28 |  |  | 12.6 | 54.27 | 6.4 | 3.07 | 1.403e-06% |  | 5.4 | 3.6 | 9 | [5 empty] | 3525000 | 213861762.6 | 3
|  |  | Cxx | xx.xx.xxxx | Current | today | 2006-04-28 |  |  | 15.6 | 54.27 | 6.4 | 1.27 |  |  |  |  | 0.8
|  |  | Name of TPM |  | Deviation | weeks | 0 |  |  | 3 | 0 | 0 | -1.8 |  |  |  |  | -8.2
EOL (M4 - M5)
| PG85 | SG2 | Phoenix | Mx | Target | at M1 | 2006-04-28 |  |  | 20 | 88.79 | 8.05 | 5.98 | 0.01033% |  | 5.4 | 3.6 | 9 | [5 empty] | 664000 | 64301780 | 6644.2
|  |  | CX75 | xx.xx.xxxx | Current | today | 2006-04-28 |  |  | 24.2 | 88.8 | 8.05 | 1.95 |  |  |  |  | 2.3
|  |  | Name of TPM |  | Deviation | weeks | 0 |  |  | 4.2 | 0.01 | 0 | -4.03 |  |  |  |  | -6.7
| PG75 | SGL | Sirius | Mx | Target | at M1 | 2005-08-19 |  |  | 16.9 | 94.49 | 8.11 | 7.53 | 10.65% |  | 5.4 | 3.6 | 9 | [6 empty] | 16.9 | 1.8
|  |  | M75 | xx.xx.xxxx | Current | today | 2005-08-04 |  |  | 18.7 | 94.5 | 8.11 | 4.02 |  |  |  |  | 3.1
|  |  | Name of TPM |  | Deviation | weeks | -2.1429 |  |  | 1.8 | 0.01 | 0 | -3.51 |  |  |  |  | -5.9
| PG75 | EGL | Leopard ref. |  | Target | M1 | 2005-02-04 |  | ü | 2.255 |  | 0.26589 | 0.26589 |  |  | M1 |  | 2005-02-04 |  | ü
[5 empty] | Current | 2005-10-25 | 2005-02-04 |  |  | 1.3811 |  | -8.6431 | -8.6431 |  |  | 2005-10-25 |  | 2005-02-04
[5 empty] | Deviation | weeks | 0 |  |  | -0.87395 |  | -8.909 | -8.909 |  |  | weeks |  | 0
| PG85 | n.a. | Electra | Mx | Target | at M1 | 2006-02-24 |  |  | n.a. | n.a. | n.a. | n.a. | 300% |  | 6 | 6 | 12 |  |  | - comments | - comments | - comments |  | #VALUE! | 0
|  |  | SF65 | xx.xx.xxxx | Current | today | 2006-02-24 |  |  | n.a. | n.a | n.a | n.a |  |  |  |  | n.a.
|  |  | Name of TPM |  | Deviation | weeks | 0
| PG85 | n.a. | Mars | Mx | Target | at M1 | 2006-04-28 |  |  | n.a. | n.a. | n.a. | n.a. | 300% |  | 5.4 | 3.6 | 9 | [6 empty] | #VALUE! | 0
|  |  | CC75 | xx.xx.xxxx | Current | today | cancelled |  |  | n.a. | n.a | n.a | n.a |  |  |  |  | n.a.
|  |  | Name of TPM |  | Deviation | weeks | #VALUE!
[5 empty] | Traffic light - Time to market |  |  |  |  | Traffic light - Financials | [6 empty] | Traffic light - Return Rate
[5 empty] | green | No delay or earlier than target |  |  |  | green | On track or above target | [5 empty] | green |  | On track or below target
[5 empty] | yellow | Delay to target is < 4 weeks |  |  |  | yellow | Below target (deviation max. 10% of target) | [5 empty] | yellow |  | Above target (deviation max. 20% of target)
[5 empty] | red | Delay to target is > 4 weeks |  |  |  | red | Below target (deviation >10% of target) | [5 empty] | red |  | Above target (deviation >20% of target)
Trend - Financials
|  |  |  | ü |  | Positive trend, e.g. significant positive delta to last reported value
No significant change
Negative trend, e.g. significant negative delta to last reported value
Note on R9: Keld Christiansen: Based on SVN13

## Input (2) (hidden)
BJ-Projects in realization | [32 empty] | MD PM BA (BJ)
|  |  |  | Time to Market |  |  |  |  | Financials
| PG | Chip | Product | [5 empty] | Life Cycle | [8 empty] | Profit in FY05 |  |  |  | EBIT FY05 | Profit in FY06 |  |  |  | EBIT FY06 | Profit in FY07 |  |  |  | EBIT FY07
[6 empty] | Delivery | Status | Trend | Volume | Sales | S.-Margin | S. Margin | Gross | Profit | Profit | Status | Trend | Q1 | Q2 | Q3 | Q4 | Total | Q1 | Q2 | Q3 | Q4 | Total | Q1 | Q2 | Q3 | Q4 | Total
|  |  | MS-status |  |  | Start |  |  | (in mill. | (in mill. €) | (in mill. €) | (in %) | Margin | (in mill. €) | (in %) |  |  | (in | (in | (in | (in | (in | (in | (in | (in | (in | (in | (in | (in | (in | (in | (in
[9 empty] | units) |  |  |  | (in %) |  |  |  |  | mill. €) | mill. €) | mill. €) | mill. €) | mill. €) | mill. €) | mill. €) | mill. €) | mill. €) | mill. €) | mill. €) | mill. €) | mill. €) | mill. €) | mill. €)
| PG75 | EG | Puma | Target | M1 | 2004-09-06 |  |  | 0.721 | 38.468 | 13.4219 | 34.89% | 28.06% | -9.8324 | -25.56% |  |  |  |  | -0.73827 | -2.5564 | -3.2947 | -3.1616 | -3.8475 | -0.11917 | 0.91068 | -6.2176 | 0.23762 | -0.55767 |  |  | -0.32005
|  |  |  | Current | 2005-06-27 | 2006-04-28 |  |  | 0.721 | 38.468 | 13.4219 | 34.89% | 28.06% | -9.8324 | -25.56% |  |  |  |  | -0.73827 | -2.5564 | -3.2947 | -3.1616 | -3.8475 | -0.11917 | 0.91068 | -6.2176 | 0.23762 | -0.55767 |  |  | -0.32005
|  |  | M3 | Deviation | weeks | 85.5714 |  |  | 0 | 0 | 0 | 0% | 0% | 0 | 0% |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
| PG85 | SG2 | Brambling | Target | M-alpha | 2006-05-26 |  |  | 1.915 | 231.8 | 69.56 | 30% | 23.4% | 1.884 | 0.81% | [6 empty] | -3.5229 |  |  |  |  | 5.4074
|  |  |  | Current | 2005-07-29 | 2006-06-26 |  |  | 2.1913 | 268.4 | 71.7 | 26.7% | 20.7% | -17.3 | -6.4% |  |  |  |  | -7.4422 | -4.5589 | -12.0011 | -4.6275 | -5.1991 | -3.8552 | 2.7049 | -10.9769 | 6.3148 | 0.13242 | -0.7421 |  | 5.7051
|  |  | pre-M0 | Deviation | weeks | 4.4286 |  |  | 0.27627 | 36.6 | 2.14 | -3.3% | -2.7% | -19.184 | -7.21% |  |  |  |  | -7.4422 | -4.5589 | -8.4782 | -4.6275 | -5.1991 | -3.8552 | 2.7049 | -16.3843 | 6.3148 | 0.13242 | -0.7421 |  | 5.7051
| PG85 | EGL | Quail | Target | M1 | 2006-01-24 |  |  | 1.7882 | 108.4 | 29.7825 | 27.48% | 21.5% | 2.3621 | 2.18% |  |  | 0 | -0.24951 | -1.3033 | -1.9769 | -3.5297 | -3.3304 | 0.26347 | 3.2437 | 2.5946 | 2.7714 | 2.6251 | 0.49527 |  |  | 3.1204
|  |  |  | Current | 2005-07-29 | 2006-01-24 |  |  | 1.7882 | 108.4 | 29.7825 | 27.48% | 21.5% | 2.3621 | 2.18% |  |  | 0 | -0.24951 | -1.3033 | -1.9769 | -3.5297 | -3.3304 | 0.26347 | 3.2437 | 2.5946 | 2.7714 | 2.6251 | 0.49527 |  |  | 3.1204
|  |  | M1 | Deviation | weeks | 0 |  |  | 0 | 0 | 0 | 0% | 0% | 0 | 0% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
| PG85 | EGL | Finch | Target | M1 | 2006-01-26 |  |  | 3.3276 | 148.2236 | 33.2953 | 22.46% | 15.47% | -3.4771 | -2.4% |  |  | 0 | -0.24752 | -1.0186 | -1.971 | -3.2371 | -2.8106 | 1.4615 | 2.2465 | -0.14274 | 0.75461 | -0.99466 |  |  |  | -0.99466
|  |  |  | Current | 2005-07-30 | 2006-01-26 |  |  | 3.3276 | 148.2236 | 33.2953 | 22.46% | 15.47% | -3.4771 | -2.4% |  |  | 0 | -0.24752 | -1.0186 | -1.971 | -3.2371 | -2.8106 | 1.4615 | 2.2465 | -0.14274 | 0.75461 | -0.99466 |  |  |  | -0.99466
|  |  | M1 | Deviation | weeks | 0 |  |  | 0 | 0 | 0 | 0% | 0% | 0 | 0% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| PG85 | SGL | Plover | Target | M0 | 2006-04-28 |  |  | 1.95 | 152.8 | 40.9527 | 26.8% | 20.1% | -15.6228 | -10.22% |  |  |  | -5.4674 | -3.1016 | -4.5392 | -13.1081 | -4.5804 | -5.0349 | 0.74272 | 2.8911 | -5.9815 | 2.2379 | 0.95549 | 0.27339 |  | 3.4668
|  |  |  | Current | 2005-08-30 | 2006-05-17 |  |  | 1.95 | 146.2 | 34.4 | 23.5% | 16.7% | -21.5 | -14.7% |  |  |  | -5.4674 | -3.1016 | -4.5392 | -13.1081 | -4.5804 | -5.0349 | 0.74272 | 2.3468 | -6.5258 | 0.61018 | -1.4987 | -1.0078 |  | -1.8963
|  |  | M0 | Deviation | weeks | 2.7143 |  |  | 0 | -6.6 | -6.5527 | -3.297% | -3.4% | -5.8772 | -4.477% |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -0.54433 | -0.54433 | -1.6277 | -2.4542 | -1.2812 |  | -5.3631
| PG85 | EGL | Flamingo | Target | M1 | 2005-10-24 |  |  | 2.95 |  | 91.7498 | 37% |  | 25.3945 | 10.24% |  |  | -0.28256 | -2.2475 | -2.6547 | -4.3239 | -9.5087 | 6.9992 | 12.1855 | 10.3044 | 3.17 | 32.659 | 2.2442 |  |  |  | 2.2442
|  |  |  | Current | 2005-07-26 | 2005-10-24 |  |  | 1.937 |  | 57.6576 | 37.49% |  | 11.5031 | 7.48% |  |  | -0.38786 | -1.0102 | -2.2328 | -4.671 | -8.3018 | 4.8144 | 8.9258 | 4.7278 | 1.4307 | 19.8987 | -0.093788 |  |  |  | -0.093788
|  |  | M1 | Deviation | weeks | 0 |  |  | -1.013 | 0 | -34.0922 | 0.4989% | 0% | -13.8914 | -2.759% |  |  | -0.1053 | 1.2373 | 0.42198 | -0.34708 | 1.2069 | -2.1848 | -3.2598 | -5.5766 | -1.7393 | -12.7603 | -2.338 |  |  |  | -2.338
| PG85 | EGL | Pelican | Target | M1 | 2006-03-20 |  |  | 1.4469 | 106.2 | 35.0321 | 33% | 26.8% | 10.236 | 9.641% |  |  |  |  | -0.32863 | -1.3589 | -1.6875 | -2.2635 | -1.9855 | 7.5107 | 5.9896 | 9.2513 | 2.6889 | -0.011098 | -0.0055488 |  | 2.6722
|  |  |  | Current | 2005-08-31 | 2006-03-20 |  |  | 1.4469 | 106.2 | 35.0321 | 33% | 26.8% | 10.236 | 9.641% |  |  |  |  | -0.32863 | -1.3589 | -1.6875 | -2.2635 | -1.9855 | 7.5107 | 5.9896 | 9.2513 | 2.6889 | -0.011098 | -0.0055488 |  | 2.6722
|  |  | M1 | Deviation | weeks | 0 |  |  | 0 | 0 | 0 | 0 | 0% | 0 | 0% |  |  |  |  | 0 | 0 | 0
| PG75 | EG | Puma | Target | M1 | 2004-09-06 |  | ü | 5.728 |  | 74.4044 | 18.96% |  | 10.6114 | 2.704% |  |  | 14.4437 | 1.6143 | -0.43787 | 1.0365 | 16.6566 | 0 |  |  |  | 0
|  |  |  | Current | 2005-07-26 | 2004-09-06 |  |  | 4.0741 |  | 39.7807 | 16.2% |  | -14.5046 | -5.907% |  |  | 9.9847 | -6.6019 | -3.8156 | -2.8651 | -3.298 | -2.43 |  |  |  | -2.43
|  |  | M3 | Deviation | weeks | 0 |  |  | -1.6539 | 0 | -34.6238 | -2.758% | 0% | -25.116 | -8.61% |  |  | -4.459 | -8.2162 | -3.3778 | -3.9016 | -19.9546 | -2.43 |  |  |  | -2.43
| PG75 | EG | Artemis | Target | M1 | 2005-01-07 |  | ü | 4.251 |  | 52.2165 | 23.9% |  | 7.8867 | 3.6% |  |  | -1.6638 | 1.6239 | 1.0243 | 2.6942 | 3.6785 | 3.0139 | 0.9981 | 0.19818 |  | 4.2102
|  |  |  | Current | 2005-07-26 | 2005-01-14 |  |  | 0.70357 |  | 7.6926 | 20.02% |  | -1.1946 | -3.807% |  |  | -0.64867 | 0.35327 | -0.75262 | -0.40289 | -1.4509 | -0.012278 |  |  |  | -0.012278
|  |  | pre-M3 | Deviation | weeks | 1 |  |  | -3.5474 | 0 | -44.524 | -3.888% | 0% | -9.0813 | -7.407% |  |  | 1.0152 | -1.2706 | -1.7769 | -3.0971 | -5.1294 | -3.0262 |  |  |  | -4.2225
| PG75 | EG | Libra | Target | M1 | 2005-05-09 |  | ü | 6.14 |  | 74.5469 | 23.46% |  | 7.2008 | 2.266% |  |  | -2.1889 | -3.7108 | -0.48376 | 7.5289 | 1.1455 | 8.1185 | 0.069853 | -1.1202 |  | 7.0681
|  |  |  | Current | 2005-07-26 | 2005-05-24 |  |  | 2.564 |  | 21.2408 | 16.73% |  | -13.4864 | -10.62% |  |  | -2.1969 | -3.6805 | -5.5201 | 0.44042 | -10.9571 | 0.35386 | -0.83555 | -1.0347 |  | -1.5164
|  |  | DS | Deviation | weeks | 2.1429 |  |  | -3.576 | 0 | -53.3061 | -6.73% | 0% | -20.6872 | -12.89% |  |  | -0.0080675 | 0.030241 | -5.0363 | -7.0885 | -12.1027 | -7.7646 | -0.90541 | 0.08548 |  | -8.5845
| PG75 | EGL | Dorado | Target | M1 | 2005-05-19 |  | ü | 11.532 |  | 84.4067 | 20.74% |  | 7.9916 | 1.963% |  |  | -1.6735 | -2.9824 | -0.83512 | 4.466 | -1.0251 | 8.7452 | 3.3302 | -2.9822 |  | 9.0933
|  |  |  | Current | 2005-07-28 | 2005-06-07 |  |  | 5.8223 |  | 22.9388 | 11.74% |  | -19.3293 | -9.89% |  |  | -2.1106 | -2.8306 | -0.76589 | -4.5349 | -10.242 | -5.9904 | -3.0496 | -0.0029082 |  | -9.0429
|  |  | DS | Deviation | weeks | 2.7143 |  |  | -5.7097 | 0 | -61.4679 | -8.999% | 0% | -27.3208 | -11.85% |  |  | -0.43711 | 0.15185 | 0.069228 | -9.0009 | -9.2169 | -14.7356 | -6.3798 | 2.9793 |  | -18.1361
| PG75 | SGL | Sirius | Target | M1 | 2005-06-28 |  | ü | 1.35 |  | 94.1447 | 38.37% |  | 24.7312 | 10.08% |  |  | -4.4331 | -5.5005 | -1.7756 | 14.713 | 3.0038 | 18.7561 | 5.6929 | 0.17863 |  | 24.6276
|  |  |  | Current | 2005-06-27 | 2005-06-27 |  |  | 0.55401 |  | 28.8964 | 31.23% |  | -9.2569 | -10% |  |  | -3.9799 | -4.5422 | -3.8348 | 2.418 | -9.9389 | 2.7388 | 0.45719 | 0.38618 |  | 3.5822
|  |  | DS | Deviation | weeks | -0.14286 |  |  | -0.79599 | 0 | -65.2483 | -7.143% | 0% | -33.9881 | -20.08% |  |  | 0.45324 | 0.95832 | -2.0592 | -12.295 | -12.9427 | -16.0173 | -5.2357 | 0.20755 |  | -21.0454
| PG75 | EGL | Pegasus | Target | M1 | 2005-05-26 |  | ü | 5.111 | 328 | 80.5855 | 24.72% | 17.3% | 5.5723 | 1.709% |  |  | -2.004 | -2.9916 | -0.88771 | 6.0067 | 0.12334 | 8.4863 | 0.78563 | -2.6346 |  | 6.6373
|  |  |  | Current | 2005-06-30 | 2005-06-17 |  |  | 2.5655 | 62.9 | 20.4 | 32.4% | 26.1% | -8.136 | -5.942% |  |  | -2.621 | -3.2344 | -3.196 | 1.0602 | -7.9913 | 1.5889 | -0.010382 | -1.0699 |  | 0.50861
|  |  | DS | Deviation | weeks | 3.1429 |  |  | -2.5455 | -265.1 | -60.1855 | 7.678% | 8.8% | -13.7082 | -7.652% |  |  | -0.61699 | -0.24276 | -2.3083 | -4.9466 | -8.1146 | -6.8974 | -0.79601 | 1.5647 |  | -6.1287
| PG75 | SGL | Phoenix | Target | M1 | 2005-06-10 |  | ü | 1.95 |  | 102.7868 | 33.51% |  | 23.7527 | 7.743% |  |  | -4.7798 | -6.0456 | 0.62009 | 20.9189 | 10.7136 | 15.976 | 2.0229 |  |  | 17.9989
|  |  |  | Current | 2005-07-26 | 2005-06-27 |  |  | 1.562 |  | 64.9686 | 28.54% |  | -2.1399 | -0.94% |  |  | -4.5309 | -6.5662 | -5.0135 | 7.6192 | -8.4913 | 10.1052 | 1.2062 |  |  | 11.3114
|  |  | DS | Deviation | weeks | 2.4286 |  |  | -0.388 | 0 | -37.8182 | -4.971% | 0% | -25.8926 | -8.683% |  |  | 0.24894 | -0.52066 | -5.6335 | -13.2997 | -19.2049 | -5.8708 | -0.81673 |  |  | -6.6876
| PG75 | SGL | Adonis | Target | M1 | 2005-07-11 |  | ü | 3.537 |  | 100.8147 | 27.88% |  | 8.2761 | 2.289% |  |  | -1.9818 | -3.5789 | -4.4205 | 10.1699 | 0.18862 | 6.9033 | 1.3168 | 0.16377 |  | 8.3839
|  |  |  | Current | 2005-06-03 | 2005-07-11 |  |  | 2.6086 |  | 65.9669 | 26.18% |  | -5.1788 | -2.055% |  |  | -2.1476 | -2.8109 | -4.903 | 0.22948 | -9.632 | 6.4986 | 0.89933 | -2.6236 | -0.024765 | 4.7496
|  |  | pre-DS | Deviation | weeks | 0 |  |  | -0.92843 | 0 | -34.8478 | -1.7% | 0% | -13.4549 | -4.344% |  |  | -0.16574 | 0.76807 | -0.4825 | -9.9404 | -9.8206 | -0.40475 | -0.41745 | -2.7873 |  | -3.6343
| PG75 | EGL | Leopard ref. | Target | M1 | 2005-02-04 |  | ü | 2.255 |  | 30.8785 | 19.36% |  | 0.26589 | 0.1667% |  |  |  | -0.0143 | 3.4543 | -3.1741 | 0.26589
|  |  |  | Current | 2005-07-26 | 2005-02-04 |  |  | 1.4858 |  | 15.1857 | 14.52% |  | -3.9466 | -3.773% |  |  |  | 1.3193 | -0.29949 | -2.1462 | -1.1265 | -2.8201 |  |  |  | -2.8201
|  |  | M3 | Deviation | weeks | 0 |  |  | -0.76918 | 0 | -15.6928 | -4.844% | 0% | -4.2125 | -3.94% |  |  |  | 1.3336 | -3.7538 | 1.0279 | -1.3923 | -2.8201 |  |  |  | -2.8201
| PG65 | SGL | Leopard | Target | M1 | [16 empty] | 0 |  |  |  |  | 0
|  |  |  | Current | 2005-04-12 | [16 empty] | 0 |  |  |  |  | 0
|  |  |  | Deviation | weeks | 0 |  |  | 0 |  | 0 | 0% |  | 0 | 0% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Target | M1 | [16 empty] | 0 |  |  |  |  | 0
|  |  |  | Current | 2005-04-12 | [16 empty] | 0 |  |  |  |  | 0
|  |  |  | Deviation | weeks | 0 |  |  | 0 |  | 0 | 0% |  | 0 | 0% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Target | M1 | [16 empty] | 0 |  |  |  |  | 0
|  |  |  | Current | 2005-04-12 | [16 empty] | 0 |  |  |  |  | 0
|  |  |  | Deviation | weeks | 0 |  |  | 0 |  | 0 | 0% |  | 0 | 0% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Target: Basis is Scenario 2C-Strich; no detailed figures underneath Sales Margin as well as for break-down to quarters
|  | Ready to copy: |  |  |  | Traffic light - Time to market: | [5 empty] | automatic fill-in |  |  |  | Traffic light - Time to market: |  |  |  |  | manual entry
[6 empty] | green | No delay or earlier than target | [8 empty] | green
[6 empty] | yellow | Delay to target is < 4 weeks | [8 empty] | yellow
[6 empty] | red | Delay to target is > 4 weeks | [8 empty] | red
-
[6 empty] | Trend - Time to market: | [5 empty] | manual entry
|  |  |  | ü |  |  | Positive trend, e.g. significant positive delta to last reported value
No significant change
Negative trend, e.g. significant negative delta to last reported value