## Manual (hidden)
BJ-Projects in realization | [30 empty] | MD PM BA (BJ)
|  |  |  | Time to Market |  |  |  |  | Financials
| PG | Chip | Product | [5 empty] | Life Cycle | [6 empty] | Profit in FY05 |  |  |  | EBIT FY05 | Profit in FY06 |  |  |  | EBIT FY06 | Profit in FY07 |  |  |  | EBIT FY07
[6 empty] | Delivery | Status | Trend | Volume | S. Margin | S. Margin | Profit | Profit | Status | Trend | Q1 | Q2 | Q3 | Q4 | Total | Q1 | Q2 | Q3 | Q4 | Total | Q1 | Q2 | Q3 | Q4 | Total
[6 empty] | Start |  |  | (in mill. | (in mill. €) | (in %) | (in mill. €) | (in %) |  |  | (in | (in | (in | (in | (in | (in | (in | (in | (in | (in | (in | (in | (in | (in | (in
[9 empty] | units) | [6 empty] | mill. €) | mill. €) | mill. €) | mill. €) | mill. €) | mill. €) | mill. €) | mill. €) | mill. €) | mill. €) | mill. €) | mill. €) | mill. €) | mill. €) | mill. €)
| PG85 | EGL | Quail | Target | M-alpha (2C') | 2006-01-17 |  |  | 2.525 | 61.9635 | 36.09%
|  |  |  | Current | 2005-03-25 | 2006-02-06 |  |  | 3.365 | 30.7589 | 15.34% | -12.3148 | -6.143% |  |  |  | -0.2882 | -1.419 | -1.839 | -3.5462 | -2.25 | 0.77765 | 0.24667 | -4.199 | -5.4247 | -3.0379 | -0.30484 |  |  | -3.3428
|  |  | pre-M0 | Deviation | weeks | 2.8571 |  |  | 0.84 | -31.2046 | -20.75%
| PG85 | EGL | Flamingo | Target | M1 | 2005-10-24 |  |  | 2.95 | 91.7498 | 37% | 25.3945 | 10.24% |  |  | -0.28256 | -2.2475 | -2.6547 | -4.3239 | -9.5087 | 6.9992 | 12.1855 | 10.3044 | 3.17 | 32.659 | 2.2442 |  |  |  | 2.2442
|  |  |  | Current | 2005-03-15 | 2005-10-05 |  |  | 2.95 | 91.7498 | 37% | 25.3945 | 10.24% |  |  | -0.28256 | -2.2475 | -2.6547 | -4.3239 | -9.5087 | 6.9992 | 12.1855 | 10.3044 | 3.17 | 32.659 | 2.2442 |  |  |  | 2.2442
|  |  | M1 | Deviation | weeks | -2.7143 |  |  | 0 | 0 | 0% | 0 | 0% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| PG85 | EGL | Pelican | Target | M-alpha (2C') | 2006-03-15 |  |  | 2.15 | 62.4145 | 41.35%
|  |  |  | Current | 2005-03-15 | 2006-03-15 |  |  | 2.43 | 49.3337 | 29.55% | 10.4961 | 6.286%
|  |  | M-alpha | Deviation | weeks |  |  |  | -0.28 | 13.0808 | 0.11807
| PG75 | EG | Puma | Target | M1 | 2004-09-06 |  |  | 5.728 | 74.4044 | 18.96% | 10.6114 | 2.704% |  |  | 14.4437 | 1.6143 | -0.43787 | 1.0365 | 16.6566
|  |  |  | Current | 2005-04-19 | 2004-09-06 |  |  | 4.5144 | 50.4765 | 18.83% | -8.0068 | -2.986% |  |  | 10.4804 | -5.1373 | -1.4607 | -3.1125 | 0.77004
|  |  | launched | Deviation | weeks | 0 |  |  | -1.2136 | -23.928 | -0.1318% | -18.6182 | -5.69% |  |  | -3.9633 | -6.7515 | -1.0228 | -4.149 | -15.8866
| PG75 | EGL | Pegasus | Target | M1 | 2005-05-26 |  |  | 5.111 | 80.5855 | 24.72% | 5.5723 | 1.709% |  |  | -2.004 | -2.9916 | -0.88771 | 6.0067 | 0.12334 | 8.4863 | 0.78563 | -2.6346 |  | 6.6373
|  |  |  | Current | 2005-04-19 | 2005-06-17 |  |  | 0 | 0 | 0% | 0 | 0% |  |  | 0 | 0 | 4.2461e-08 | 4.2461e-08 | 8.4921e-08 | 0 | 0 | 0 |  | 0
|  |  | pre-M2 | Deviation | weeks | 3.1429 |  |  | -5.111 | -80.5855 | -24.72% | -5.5723 | -1.709% |  |  | 2.004 | 2.9916 | 0.88771 | -6.0067 | -0.12334 | -8.4863 | -0.78563 | 2.6346 |  | -6.6373
| PG65 | SGL | Leopard | Target | M1 | [14 empty] | 0 |  |  |  |  | 0
|  |  |  | Current | 2005-04-12 | [14 empty] | 0 |  |  |  |  | 0
|  |  |  | Deviation | weeks | 0 |  |  | 0 | 0 | 0% | 0 | 0% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Target | M1 | [14 empty] | 0 |  |  |  |  | 0
|  |  |  | Current | 2005-04-12 | [14 empty] | 0 |  |  |  |  | 0
|  |  |  | Deviation | weeks | 0 |  |  | 0 | 0 | 0% | 0 | 0% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Target | M1 | [14 empty] | 0 |  |  |  |  | 0
|  |  |  | Current | 2005-04-12 | [14 empty] | 0 |  |  |  |  | 0
|  |  |  | Deviation | weeks | 0 |  |  | 0 | 0 | 0% | 0 | 0% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Target: Basis is Scenario 2C-Strich; no detailed figures underneath Sales Margin as well as for break-down to quarters
|  | Ready to copy: |  |  |  | Traffic light - Time to market: |  |  |  |  | automatic fill-in |  |  | Traffic light - Time to market: |  |  |  |  | manual entry
[6 empty] | green | No delay or earlier than target | [6 empty] | green
[6 empty] | yellow | Delay to target is < 4 weeks | [6 empty] | yellow
[6 empty] | red | Delay to target is > 4 weeks | [6 empty] | red
-
[6 empty] | Trend - Time to market: |  |  |  |  | manual entry
|  |  |  | ü |  |  | Positive trend, e.g. signiificant positive delta to last reported value
No significant change
Negative trend, e.g. signiificant negative delta to last reported value

## Input
PHE Cockpit Chart 2G |  |  |  | CW 22 |  |  | 2006-05-30
Products in realization (M0 - S4)
|  |  |  | Next | Time to Market |  |  |  |  | Financials | [6 empty] | Return Rate |  |  |  |  | Update-Status |  | Status
|  |  |  | Mile- |  |  | Delivery | Status | Trend | Volumes | R&D effort* | BOM | Conversion | thereof | Status | Trend | RR | RR | RR | Status | Trend
|  | Chip | Product | stone |  |  | Start |  |  |  | (in mill. €) | (in p/u. €) | Costs** | Licenses/Royalties |  |  | HW | SW | total |  |  |  |  | Achievements | Issues | Next Steps | Total costs + R&D effort | Deviation * Quantity +R&D effort
[13 empty] | (p/u. €) | (p/u. €) |  |  | (in %) | (in %) | (in %)
| PG75 | SG2 | Hydra | S4 | Target | at M1 | 2005-09-22 |  |  | 1010000 | 17.69 | 102.5 | 16.43 | 5.79 | -6.796% |  | 6 | 6 | 12 |  |  | TPM | X | - First 10k material for GOLD confirmed - S4 HW declared - SL78 cancelled because of negative market feed-back - SL75 only use SG2 from ALTIS. | - Huge deviation of reported LC figures (Forecast, Close of gab and ROF). Nearly 500k. LC shows 1.1mill and ROF shows <700k) - All activities for CMCC stopped, no more market for China. | - S4 from SW and ST. | 151367320 | -10286720
|  |  | SL75 | 2006-05-26 | Current | today | 2006-02-17 |  |  | 1124000 | 16.71 | 99.18 | 11.47 | 2.4 |  |  | 6 | 5.5 | 11.5
Add. CR Impact
|  |  | SPM Mues-Hane |  | Deviation | weeks | 21.1429 |  |  | 114000 | -0.98 | -3.32 | -4.96 | -3.39 |  |  |  |  | -0.5 |  |  | TPM BA
| PG75 | SG2 | Minos | S4 | Target | at M1 | 2005-09-22 |  |  | 3475000 | 21.609 | 87.73 | 13.45 | 5.15 | -4.368% |  | 6 | 6 | 12 |  |  | TPM |  | Vodafone unlimited approval for SW31 | lifecycyle volume decreased dramatically (3,7 Mio => 500k); further lifecycle volumen decrease 100k under evaluation adjusted M1 value |  | 72199000 | -3154000
|  |  | S75 | 2006-05-26 | Current | today | 2006-02-17 |  |  | 500000 | 19.325 | 85.43 | 14.01 | 3.38 |  |  | 5 | 9 | 14
Add. CR Impact
|  |  | SPM Hombeck |  | Deviation | weeks | 21.1429 |  |  | -2975000 | -2.284 | -2.3 | 0.56 | -1.77 |  |  |  |  | 2 |  |  | TPM BA
| PG75 | SG2 | Polaris | S4 | Target | at M1 | 2006-02-24 |  |  | 1220500 | 10.417 | 58.69 | 8.78 | 2.59 | 4.72% |  | 8 | 4 | 12 |  |  | TPM | x | DS declared All SW Approvals Available SW Quality reached S4 Target nCCPI 35k (Estimated RR 4,7% to 5,2%) Most recent Frontcovers with optimal bonding parameter fullfill all requirements to 100% | Bad tactile feeling of Navi Keyof app. 5% -> 100% manual inspection | - S4 (31-May-06) endangered due to 100% manual inspection at factory (Tactile Feeling of Navi Key) | 94929922 | 4480950
|  |  | S68 | 2006-05-31 | Current | . | 2006-02-23 |  |  | 1252600 | 10.827 | 62.07 | 8.65 | 2.54 |  |  | 6 | 5 | 11
Add. CR Impact
|  |  | TPM T. Neumann |  | Deviation | . | -0.14286 |  |  | 32100 | 0.41 | 3.38 | -0.13 | -0.05 |  |  |  |  | -1 |  |  | TPM BA
| PG75 | EGL | Leopard ref. |  | Target | M1 | 2005-02-04 |  | ü |  | 2.255 |  | 0.26589 | 0.26589 |  |  | M1 |  | 2005-02-04 |  | ü
[5 empty] | Current | 2005-10-25 | 2005-02-04 |  |  |  | 1.3811 |  | -8.6431 | -8.6431 |  |  | 2005-10-25 |  | 2005-02-04
[5 empty] | Deviation | weeks | 0 |  |  |  | -0.87395 |  | -8.909 | -8.909 |  |  | weeks |  | 0
| PG85 | SG2 | Swift | DS | Target | at M1 | 2006-04-28 |  |  | 2024100 | 16.63 | 76.04 | 10.53 | 3.17 | 12.69% |  | 5.4 | 3.6 | 9 |  |  | TPM |  | - DS declared on 03.05.2006 - SW releases of E-Plus, TMO D, Orange Amena and several other retailer - Second Source qualification of KHVatec parts started with BYD and Diabel | - Ramp Up volume reduced due to material shortage; May volume has to be reduced to 53k (loss of 1.9 Mio Sales Margin) | - SW step 2 DS shifted by 4 weeks to 07.07.2006; timeline is not accepted by CPM; escalation on management level - Close tracking of Härter, KHVatec and Perlos to secure Volumes in June and later | 211436912.74 | 26822174.46
|  |  | EL71 | 2006-05-05 | Current | today | 2006-05-03 |  |  | 2250282 | 14.131 | 89.61 | 9.99 | 2.75 |  |  | 5.4 |  | 5.4
Add. CR Impact
|  |  | TPM J. Kockmann |  | Deviation | weeks | 0.71429 |  |  | 226182 | -2.499 | 13.57 | -0.54 | -0.42 |  |  |  |  | -3.6 |  |  | TPM BA
| PG85 | SG2 | Phillipe | S3 | Target | at M1 | 2006-05-29 |  |  | 665000 | 4.7 | 75.13 | 11.77 | 4.43 | 7.749% |  | 5.4 | 3.6 | 9 |  |  | TPM |  | - Pilot series with NO-ID phones performed in factory with success. - Opportunity for early delivery of phones with SW SVN37 to countries (Czech, Ukraine) that does not need GCF approval. (Full GCF compliance not fulfilled until SVN38) | - Verification of mechanical changes not finalised until after start of ramp-up. Assesment for risk release of parts will be done. - S3 delayed due to failure in butter test (Quality test) (expected 15.05.06) - Correction for butter test failure implemented as running change. Q-department assess an added return rate of 2% until solution is implemented. | - S3 declaration (MD and PQA) - DS declaration - Finalisation of type approval - Release of SW SVN38 for DS - Project transfer to other sites after sales of Aalborg | 32334200 | 2505600
|  |  | C81 | 2006-04-26 | Current | today | 2006-05-29 |  |  | 318000 | 4.28 | 86.31 | 9.79 | 1.69 |  |  |  |  | 0
Add. CR Impact
|  |  | TPM C. Dalmose |  | Deviation | weeks | 0 |  |  | -347000 | -0.42 | 11.18 | -1.98 | -2.74 |  |  |  |  | -9 |  |  | TPM BA
| PG75 | SG2 | Hawk | S2/S25 | Target | at M1 | 2006-08-11 |  |  | 702100 | 3.042 | 72.55 | 8.25 | 1.47 | -0.03335% |  | 5.4 | 3.6 | 9 |  |  | TPM |  |  | - Delay of 1 week (6 working days) by tool maker due to technical problems in the preparations of the tools for the upper case. Expected to be ready 15.06.06. Potential risk on DS due to the tight time schedule. Assesment to be done when quality of the first molded parts is known. | - Start of B1+ prototype run in CW21 (previous schedule: CW19) - Rescheduling due to tool delay. - Project transfer to other sites after sales of Aalborg
|  |  | M81 | 2006-06-12 | Current | today | 2006-08-11 |  |  | 702100 | 3.042 | 72.55 | 8.25 | 1.47 |  |  |  |  | 0
|  |  | TPM C. Dalmose |  | Deviation | weeks | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | -9 |  |  | TPM BA
| PG85 | SG2 | Obsidian | S2 | Target | at M1 | 2006-09-08 |  |  | 2204600 | 6.765 | 64.87 | 7.15 | 0.77 | 0.1332% |  | 5.4 | 3.6 | 9 |  |  | TPM |  | - B1+ Mechanical data shipped 11th May according to schedule B1+ PCB data ready for shipment 17th May according to schedule SW expect to be able to declare S25 ahead of schedule |  | - Obsidian, signing S2 18th May | 165540292 | 220460
|  |  | E71 | 2006-05-18 | Current | today | 2006-09-08 |  |  | 2204600 | 6.765 | 64.87 | 7.25 | 0.87 |  |  |  |  | 0
Add. CR Impact
|  |  | TPM T. Stokholm |  | Deviation | weeks | 0 |  |  | 0 | 0 | 0 | 0.1 | 0.1 |  |  |  |  | -9 |  |  | TPM BA
| PG85 | SG2 | Obsidian LAM-Variante | M1 | Target | at M1 | 2006-10-20 |  |  | 183000 | 0.596 | 63.42 | 6.47 | 0.87 | 0% | [6 empty] | TPM |  |  | - Obsidian LAM 850, M1 target date 10th May missed due SCM (missing confirmation from suppliers ) and ST (missing operator requirements) – New target date is 18th May |  | 13385870 | 0
|  |  | E71 | 2006-05-18 | Current | today | 2006-10-20 |  |  | 183000 | 0.596 | 63.42 | 6.47 | 0.87
Add. CR Impact
|  |  | TPM T. Stokholm |  | Deviation | weeks | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | TPM BA
| PG85 | SG2 | Chameleon | M1 | Target | at S0 | 2006-11-10 |  |  | 1915000 | 6.187 | 82.43 | 7.41 | 0.8 | 4.863% |  | 5.4 | 3.6 | 9 |  |  | TPM |  | Team M1 declared on 19.04.2006 B1- Run started on 19.04.06, two days earlier as planed | Unsecure KHVatec quality and timelines may endanger the project, Backup-solution Nolato & DynaCast will be available for B1+ and ongoing. Decreasing LifeCycle volume from M0 (2,4Mio) over 1,.9 Mio. down to 1.3 Mio. at M1. - S0 BOM values based on Swan (2.2.2006) Project is still on track | B1 Evaluation of mechanics (both supplier), Micro SD Card reader and FM radio | 122979000 | 5981000
|  |  | CL61 | 19.04.206 | Current | today | 2006-11-10 |  |  | 1300000 | 6.5 | 85.6 | 8.6 | 1.1 |  |  |  |  | 0
Add. CR Impact
|  |  | TPM A.Zimmer |  | Deviation | weeks | 0 |  |  | -615000 | 0.313 | 3.17 | 1.19 | 0.3 |  |  |  |  | -9 |  |  | TPM BA
| PG95 | SG2 | Diamond | S0 | Target | at M0 | 2007-04-20 |  |  | 855850 | 12.156 | 92 | 22.03 | 6.75 | -0.0156% |  | 6 | 6 | 12 |  |  | TPM |  |  | * Design decision critical to reach in time due to not agreed solution for release button of slider mechanism (all proposals to solve this issue not accepted by CPM) * SW planning / Documentation still under evaluation. | * Design / mechanical Concept needs to be finalized for S0-Mileistone (MOST CRITICAL) * SW feasibility study ongoing for S0-SW Milestone * SW planning to reach S0/M1 Documentations in preparation * Supplier decisions in preparation | 109748575.5 | -17117
|  |  | tbd | 2006-05-19 | Current | today | 2007-04-20 |  |  | 855850 | 12.156 | 91.98 | 22.03 | 6.75 |  |  |  |  | 0
Add. CR Impact
|  |  | TPM A. Betting |  | Deviation | weeks | 0 |  |  | 0 | 0 | -0.02 | 0 | 0 | [7 empty] | TPM BA
Products in Life Cycle (S4 - M4)
| PG85 | SG2 | Condor | M4 | Target | at M1 | 2005-11-25 |  |  | 972600 | 2.651 | 55.77 | 10 | 3.53 | -2.295% |  | 5.4 | 3.6 | 9 |  |  | TPM |  | * 2nd RF FEM (Hitachi) Solution qualified and ready for production |  |  | 71312643.82 | -1636879.88
|  |  | ME75 | 2006-01-20 | Current | today | 2005-11-14 |  |  | 1043966 | 2.246 | 56.08 | 8.51 | 0.66 |  |  |  |  | n.a.
Add. CR Impact
|  |  | C. Aschmoneit |  | Deviation | weeks | -1.5714 |  |  | 71366 | -0.405 | 0.31 | -1.49 | -2.87 |  |  |  |  | #VALUE! |  |  | TPM BA
| PG75 | SGL | Cormorant | M4 | Target | at M1 | 2005-10-19 |  |  | 1890000 | 2.318 | 44.82 | 6.63 | 0.81 | -1.913% |  | 5.4 | 3.6 | 9 |  |  | TPM |  |  |  |  | 142947211.1 | -2733989.42
|  |  | C72 | xx.xx.xxxx | Current | today | 2005-10-12 |  |  | 2733318 | 1.47 | 43.58 | 7.18 | 1.29 |  |  |  |  | n.a.
Add. CR Impact
|  |  | Name of TPM |  | Deviation | weeks | -1 |  |  | 843318 | -0.848 | -1.24 | 0.55 | 0.48 | [7 empty] | TPM BA
| PG75 | EGL | Leopard ref. |  | Target | M1 | 2005-02-04 |  | ü |  | 2.255 |  | 0.26589 | 0.26589 |  |  | M1 |  | 2005-02-04 |  | ü
[5 empty] | Current | 2005-10-25 | 2005-02-04 |  |  |  | 1.3811 |  | -8.6431 | -8.6431 |  |  | 2005-10-25 |  | 2005-02-04
[5 empty] | Deviation | weeks | 0 |  |  |  | -0.87395 |  | -8.909 | -8.909 |  |  | weeks |  | 0
| PG85 | n.a. | Wega | M4 | Target | at M1 | 2006-02-24 |  |  | 1055000 | 1.45 | 95.41 | 0.18 | 0.18 | 0.8603% |  |  |  | 12 |  |  | TPM |  | - comments | based on FX rate change (1,225 --> 1,20166) | - comments | 82701500 | 711500
|  |  | CL75 | xx.xx.xxxx | Current | today | 2006-02-24 |  |  | 850000 | 2.425 | 94.94 | 0.34 | 0.34 |  |  | 5 | 10 | 15
Add. CR Impact
|  |  | Name of TPM |  | Deviation | weeks | 0 |  |  | -205000 | 0.975 | -0.47 | 0.16 | 0.16 |  |  |  |  | 3 |  |  | TPM BA
| PG85 | n.a. | Aries | M4 | Target | at M1 | 2006-04-28 |  |  | 4050000 | 6.23 | 54.27 | 9.48 | 3.07 | 6.982% |  | 5.4 | 3.6 | 9 |  |  | TPM |  |  |  |  | 196168025 | 13696566.8
|  |  | C75 | xx.xx.xxxx | Current | today | 2006-04-28 |  |  | 2979420 | 6.4 | 59.15 | 9.14 | 0.4 |  |  |  |  | 0.8
Add. CR Impact
|  |  | Name of TPM |  | Deviation | weeks | 0 |  |  | -1070580 | 0.17 | 4.88 | -0.34 | -2.67 |  |  |  |  | -8.2 |  |  | TPM BA
EOL (M4 - M5)
| PG85 | SG2 | Phoenix | Mx | Target | at M1 | 2006-04-28 |  |  | 1950000 | 20 | 88.79 | 8.05 | 5.98 | 7.692% |  | 5.4 | 3.6 | 9 |  |  | TPM |  |  | 1) current BoM-Value consists of IST+FC and thereby includes Variant Adder, FX Risk etc 2) former Licences were not divides between "HK relevant" and "Sales relevant" |  | 92827166.24 | 7140460.76
|  |  | CX75 | xx.xx.xxxx | Current | today | 2006-04-28 |  |  | 752036 | 24.2 | 92.9 | 7.85 | 1.26 |  |  |  |  | 2.3
Add. CR Impact
|  |  | Name of TPM |  | Deviation | weeks | 0 |  |  | -1197964 | 4.2 | 4.11 | -0.2 | -4.72 |  |  |  |  | -6.7 |  |  | TPM BA
| PG75 | SGL | Sirius | Mx | Target | at M1 | 2005-08-19 |  |  | 1350000 | 16.9 | 94.49 | 8.11 | 7.53 | 12.45% |  | 5.4 | 3.6 | 9 |  |  | TPM |  |  | 1 )current BoM-Value consists of IST+FC and thereby includes Variant Adder, FX Risk etc 2) former Licences were not divides between "HK relevant" and "Sales relevant" |  | 40237190.8 | 5009432.38
|  |  | M75 | xx.xx.xxxx | Current | today | 2005-08-04 |  |  | 227458 | 18.7 | 109.5 | 7.21 | 2.07 |  |  |  |  | 3.1
Add. CR Impact
|  |  | Name of TPM |  | Deviation | weeks | -2.1429 |  |  | -1122542 | 1.8 | 15.01 | -0.9 | -5.46 |  |  |  |  | -5.9 |  |  | TPM BA
| PG75 | EGL | Leopard ref. |  | Target | M1 | 2005-02-04 |  | ü |  | 2.255 |  | 0.26589 | 0.26589 |  |  | M1 |  | 2005-02-04 |  | ü
[5 empty] | Current | 2005-10-25 | 2005-02-04 |  |  |  | 1.3811 |  | -8.6431 | -8.6431 |  |  | 2005-10-25 |  | 2005-02-04
[5 empty] | Deviation | weeks | 0 |  |  |  | -0.87395 |  | -8.909 | -8.909 |  |  | weeks |  | 0
| PG85 | n.a. | Electra | Mx | Target | at M1 | 2006-02-24 |  |  | n.a. | n.a. | n.a. | n.a. | n.a. |  |  | 6 | 6 | 12 |  |  | TPM |  | - comments | - comments | - comments | #VALUE! | #VALUE!
|  |  | SF65 | xx.xx.xxxx | Current | today | 2006-02-24 |  |  | n..a. | n.a. | n.a | n.a | n.a |  |  |  |  | n.a.
Add. CR Impact
|  |  | Name of TPM |  | Deviation | weeks | 0 | [14 empty] | TPM BA
| PG85 | n.a. | Mars | Mx | Target | at M1 | 2006-04-28 |  |  | n.a. | n.a. | n.a. | n.a. | n.a. |  |  | 5.4 | 3.6 | 9 |  |  | TPM |  |  |  |  | #VALUE! | #VALUE!
|  |  | CC75 | xx.xx.xxxx | Current | today | cancelled |  |  | n.a. | n.a. | n.a | n.a | n.a |  |  |  |  | n.a.
Add. CR Impact
|  |  | Name of TPM |  | Deviation | weeks | #VALUE! | [14 empty] | TPM BA
[5 empty] | Traffic light - Time to market | [5 empty] | Traffic light - Financials | [6 empty] | Traffic light - Return Rate
[5 empty] | green | No delay or earlier than target |  |  |  |  | green | On track or above target | [5 empty] | green |  | On track or below target
[5 empty] | yellow | Delay to target is < 4 weeks |  |  |  |  | yellow | Below target (deviation max. 10% of target) | [5 empty] | yellow |  | Above target (deviation max. 20% of target)
[5 empty] | red | Delay to target is > 4 weeks |  |  |  |  | red | Below target (deviation >10% of target) | [5 empty] | red |  | Above target (deviation >20% of target)
[5 empty] | Trend - Financials | [10 empty] | * R&D effort: direct R&D efforts
** Conversions Costs: Value Add + HK relevant licences
|  |  |  | ü |  | Positive trend, e.g. significant positive delta to last reported value
No significant change
Negative trend, e.g. significant negative delta to last reported value
Note on S9: Keld Christiansen: Based on SVN37

## Input (2) (hidden)
BJ-Projects in realization | [32 empty] | MD PM BA (BJ)
|  |  |  | Time to Market |  |  |  |  | Financials
| PG | Chip | Product | [5 empty] | Life Cycle | [8 empty] | Profit in FY05 |  |  |  | EBIT FY05 | Profit in FY06 |  |  |  | EBIT FY06 | Profit in FY07 |  |  |  | EBIT FY07
[6 empty] | Delivery | Status | Trend | Volume | Sales | S.-Margin | S. Margin | Gross | Profit | Profit | Status | Trend | Q1 | Q2 | Q3 | Q4 | Total | Q1 | Q2 | Q3 | Q4 | Total | Q1 | Q2 | Q3 | Q4 | Total
|  |  | MS-status |  |  | Start |  |  | (in mill. | (in mill. €) | (in mill. €) | (in %) | Margin | (in mill. €) | (in %) |  |  | (in | (in | (in | (in | (in | (in | (in | (in | (in | (in | (in | (in | (in | (in | (in
[9 empty] | units) |  |  |  | (in %) |  |  |  |  | mill. €) | mill. €) | mill. €) | mill. €) | mill. €) | mill. €) | mill. €) | mill. €) | mill. €) | mill. €) | mill. €) | mill. €) | mill. €) | mill. €) | mill. €)
| PG75 | EG | Puma | Target | M1 | 2004-09-06 |  |  | 0.721 | 38.468 | 13.4219 | 34.89% | 28.06% | -9.8324 | -25.56% |  |  |  |  | -0.73827 | -2.5564 | -3.2947 | -3.1616 | -3.8475 | -0.11917 | 0.91068 | -6.2176 | 0.23762 | -0.55767 |  |  | -0.32005
|  |  |  | Current | 2005-06-27 | 2006-04-28 |  |  | 0.721 | 38.468 | 13.4219 | 34.89% | 28.06% | -9.8324 | -25.56% |  |  |  |  | -0.73827 | -2.5564 | -3.2947 | -3.1616 | -3.8475 | -0.11917 | 0.91068 | -6.2176 | 0.23762 | -0.55767 |  |  | -0.32005
|  |  | M3 | Deviation | weeks | 85.5714 |  |  | 0 | 0 | 0 | 0% | 0% | 0 | 0% |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
| PG85 | SG2 | Brambling | Target | M-alpha | 2006-05-26 |  |  | 1.915 | 231.8 | 69.56 | 30% | 23.4% | 1.884 | 0.81% | [6 empty] | -3.5229 |  |  |  |  | 5.4074
|  |  |  | Current | 2005-07-29 | 2006-06-26 |  |  | 2.1913 | 268.4 | 71.7 | 26.7% | 20.7% | -17.3 | -6.4% |  |  |  |  | -7.4422 | -4.5589 | -12.0011 | -4.6275 | -5.1991 | -3.8552 | 2.7049 | -10.9769 | 6.3148 | 0.13242 | -0.7421 |  | 5.7051
|  |  | pre-M0 | Deviation | weeks | 4.4286 |  |  | 0.27627 | 36.6 | 2.14 | -3.3% | -2.7% | -19.184 | -7.21% |  |  |  |  | -7.4422 | -4.5589 | -8.4782 | -4.6275 | -5.1991 | -3.8552 | 2.7049 | -16.3843 | 6.3148 | 0.13242 | -0.7421 |  | 5.7051
| PG85 | EGL | Quail | Target | M1 | 2006-01-24 |  |  | 1.7882 | 108.4 | 29.7825 | 27.48% | 21.5% | 2.3621 | 2.18% |  |  | 0 | -0.24951 | -1.3033 | -1.9769 | -3.5297 | -3.3304 | 0.26347 | 3.2437 | 2.5946 | 2.7714 | 2.6251 | 0.49527 |  |  | 3.1204
|  |  |  | Current | 2005-07-29 | 2006-01-24 |  |  | 1.7882 | 108.4 | 29.7825 | 27.48% | 21.5% | 2.3621 | 2.18% |  |  | 0 | -0.24951 | -1.3033 | -1.9769 | -3.5297 | -3.3304 | 0.26347 | 3.2437 | 2.5946 | 2.7714 | 2.6251 | 0.49527 |  |  | 3.1204
|  |  | M1 | Deviation | weeks | 0 |  |  | 0 | 0 | 0 | 0% | 0% | 0 | 0% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
| PG85 | EGL | Finch | Target | M1 | 2006-01-26 |  |  | 3.3276 | 148.2236 | 33.2953 | 22.46% | 15.47% | -3.4771 | -2.4% |  |  | 0 | -0.24752 | -1.0186 | -1.971 | -3.2371 | -2.8106 | 1.4615 | 2.2465 | -0.14274 | 0.75461 | -0.99466 |  |  |  | -0.99466
|  |  |  | Current | 2005-07-30 | 2006-01-26 |  |  | 3.3276 | 148.2236 | 33.2953 | 22.46% | 15.47% | -3.4771 | -2.4% |  |  | 0 | -0.24752 | -1.0186 | -1.971 | -3.2371 | -2.8106 | 1.4615 | 2.2465 | -0.14274 | 0.75461 | -0.99466 |  |  |  | -0.99466
|  |  | M1 | Deviation | weeks | 0 |  |  | 0 | 0 | 0 | 0% | 0% | 0 | 0% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| PG85 | SGL | Plover | Target | M0 | 2006-04-28 |  |  | 1.95 | 152.8 | 40.9527 | 26.8% | 20.1% | -15.6228 | -10.22% |  |  |  | -5.4674 | -3.1016 | -4.5392 | -13.1081 | -4.5804 | -5.0349 | 0.74272 | 2.8911 | -5.9815 | 2.2379 | 0.95549 | 0.27339 |  | 3.4668
|  |  |  | Current | 2005-08-30 | 2006-05-17 |  |  | 1.95 | 146.2 | 34.4 | 23.5% | 16.7% | -21.5 | -14.7% |  |  |  | -5.4674 | -3.1016 | -4.5392 | -13.1081 | -4.5804 | -5.0349 | 0.74272 | 2.3468 | -6.5258 | 0.61018 | -1.4987 | -1.0078 |  | -1.8963
|  |  | M0 | Deviation | weeks | 2.7143 |  |  | 0 | -6.6 | -6.5527 | -3.297% | -3.4% | -5.8772 | -4.477% |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -0.54433 | -0.54433 | -1.6277 | -2.4542 | -1.2812 |  | -5.3631
| PG85 | EGL | Flamingo | Target | M1 | 2005-10-24 |  |  | 2.95 |  | 91.7498 | 37% |  | 25.3945 | 10.24% |  |  | -0.28256 | -2.2475 | -2.6547 | -4.3239 | -9.5087 | 6.9992 | 12.1855 | 10.3044 | 3.17 | 32.659 | 2.2442 |  |  |  | 2.2442
|  |  |  | Current | 2005-07-26 | 2005-10-24 |  |  | 1.937 |  | 57.6576 | 37.49% |  | 11.5031 | 7.48% |  |  | -0.38786 | -1.0102 | -2.2328 | -4.671 | -8.3018 | 4.8144 | 8.9258 | 4.7278 | 1.4307 | 19.8987 | -0.093788 |  |  |  | -0.093788
|  |  | M1 | Deviation | weeks | 0 |  |  | -1.013 | 0 | -34.0922 | 0.4989% | 0% | -13.8914 | -2.759% |  |  | -0.1053 | 1.2373 | 0.42198 | -0.34708 | 1.2069 | -2.1848 | -3.2598 | -5.5766 | -1.7393 | -12.7603 | -2.338 |  |  |  | -2.338
| PG85 | EGL | Pelican | Target | M1 | 2006-03-20 |  |  | 1.4469 | 106.2 | 35.0321 | 33% | 26.8% | 10.236 | 9.641% |  |  |  |  | -0.32863 | -1.3589 | -1.6875 | -2.2635 | -1.9855 | 7.5107 | 5.9896 | 9.2513 | 2.6889 | -0.011098 | -0.0055488 |  | 2.6722
|  |  |  | Current | 2005-08-31 | 2006-03-20 |  |  | 1.4469 | 106.2 | 35.0321 | 33% | 26.8% | 10.236 | 9.641% |  |  |  |  | -0.32863 | -1.3589 | -1.6875 | -2.2635 | -1.9855 | 7.5107 | 5.9896 | 9.2513 | 2.6889 | -0.011098 | -0.0055488 |  | 2.6722
|  |  | M1 | Deviation | weeks | 0 |  |  | 0 | 0 | 0 | 0 | 0% | 0 | 0% |  |  |  |  | 0 | 0 | 0
| PG75 | EG | Puma | Target | M1 | 2004-09-06 |  | ü | 5.728 |  | 74.4044 | 18.96% |  | 10.6114 | 2.704% |  |  | 14.4437 | 1.6143 | -0.43787 | 1.0365 | 16.6566 | 0 |  |  |  | 0
|  |  |  | Current | 2005-07-26 | 2004-09-06 |  |  | 4.0741 |  | 39.7807 | 16.2% |  | -14.5046 | -5.907% |  |  | 9.9847 | -6.6019 | -3.8156 | -2.8651 | -3.298 | -2.43 |  |  |  | -2.43
|  |  | M3 | Deviation | weeks | 0 |  |  | -1.6539 | 0 | -34.6238 | -2.758% | 0% | -25.116 | -8.61% |  |  | -4.459 | -8.2162 | -3.3778 | -3.9016 | -19.9546 | -2.43 |  |  |  | -2.43
| PG75 | EG | Artemis | Target | M1 | 2005-01-07 |  | ü | 4.251 |  | 52.2165 | 23.9% |  | 7.8867 | 3.6% |  |  | -1.6638 | 1.6239 | 1.0243 | 2.6942 | 3.6785 | 3.0139 | 0.9981 | 0.19818 |  | 4.2102
|  |  |  | Current | 2005-07-26 | 2005-01-14 |  |  | 0.70357 |  | 7.6926 | 20.02% |  | -1.1946 | -3.807% |  |  | -0.64867 | 0.35327 | -0.75262 | -0.40289 | -1.4509 | -0.012278 |  |  |  | -0.012278
|  |  | pre-M3 | Deviation | weeks | 1 |  |  | -3.5474 | 0 | -44.524 | -3.888% | 0% | -9.0813 | -7.407% |  |  | 1.0152 | -1.2706 | -1.7769 | -3.0971 | -5.1294 | -3.0262 |  |  |  | -4.2225
| PG75 | EG | Libra | Target | M1 | 2005-05-09 |  | ü | 6.14 |  | 74.5469 | 23.46% |  | 7.2008 | 2.266% |  |  | -2.1889 | -3.7108 | -0.48376 | 7.5289 | 1.1455 | 8.1185 | 0.069853 | -1.1202 |  | 7.0681
|  |  |  | Current | 2005-07-26 | 2005-05-24 |  |  | 2.564 |  | 21.2408 | 16.73% |  | -13.4864 | -10.62% |  |  | -2.1969 | -3.6805 | -5.5201 | 0.44042 | -10.9571 | 0.35386 | -0.83555 | -1.0347 |  | -1.5164
|  |  | DS | Deviation | weeks | 2.1429 |  |  | -3.576 | 0 | -53.3061 | -6.73% | 0% | -20.6872 | -12.89% |  |  | -0.0080675 | 0.030241 | -5.0363 | -7.0885 | -12.1027 | -7.7646 | -0.90541 | 0.08548 |  | -8.5845
| PG75 | EGL | Dorado | Target | M1 | 2005-05-19 |  | ü | 11.532 |  | 84.4067 | 20.74% |  | 7.9916 | 1.963% |  |  | -1.6735 | -2.9824 | -0.83512 | 4.466 | -1.0251 | 8.7452 | 3.3302 | -2.9822 |  | 9.0933
|  |  |  | Current | 2005-07-28 | 2005-06-07 |  |  | 5.8223 |  | 22.9388 | 11.74% |  | -19.3293 | -9.89% |  |  | -2.1106 | -2.8306 | -0.76589 | -4.5349 | -10.242 | -5.9904 | -3.0496 | -0.0029082 |  | -9.0429
|  |  | DS | Deviation | weeks | 2.7143 |  |  | -5.7097 | 0 | -61.4679 | -8.999% | 0% | -27.3208 | -11.85% |  |  | -0.43711 | 0.15185 | 0.069228 | -9.0009 | -9.2169 | -14.7356 | -6.3798 | 2.9793 |  | -18.1361
| PG75 | SGL | Sirius | Target | M1 | 2005-06-28 |  | ü | 1.35 |  | 94.1447 | 38.37% |  | 24.7312 | 10.08% |  |  | -4.4331 | -5.5005 | -1.7756 | 14.713 | 3.0038 | 18.7561 | 5.6929 | 0.17863 |  | 24.6276
|  |  |  | Current | 2005-06-27 | 2005-06-27 |  |  | 0.55401 |  | 28.8964 | 31.23% |  | -9.2569 | -10% |  |  | -3.9799 | -4.5422 | -3.8348 | 2.418 | -9.9389 | 2.7388 | 0.45719 | 0.38618 |  | 3.5822
|  |  | DS | Deviation | weeks | -0.14286 |  |  | -0.79599 | 0 | -65.2483 | -7.143% | 0% | -33.9881 | -20.08% |  |  | 0.45324 | 0.95832 | -2.0592 | -12.295 | -12.9427 | -16.0173 | -5.2357 | 0.20755 |  | -21.0454
| PG75 | EGL | Pegasus | Target | M1 | 2005-05-26 |  | ü | 5.111 | 328 | 80.5855 | 24.72% | 17.3% | 5.5723 | 1.709% |  |  | -2.004 | -2.9916 | -0.88771 | 6.0067 | 0.12334 | 8.4863 | 0.78563 | -2.6346 |  | 6.6373
|  |  |  | Current | 2005-06-30 | 2005-06-17 |  |  | 2.5655 | 62.9 | 20.4 | 32.4% | 26.1% | -8.136 | -5.942% |  |  | -2.621 | -3.2344 | -3.196 | 1.0602 | -7.9913 | 1.5889 | -0.010382 | -1.0699 |  | 0.50861
|  |  | DS | Deviation | weeks | 3.1429 |  |  | -2.5455 | -265.1 | -60.1855 | 7.678% | 8.8% | -13.7082 | -7.652% |  |  | -0.61699 | -0.24276 | -2.3083 | -4.9466 | -8.1146 | -6.8974 | -0.79601 | 1.5647 |  | -6.1287
| PG75 | SGL | Phoenix | Target | M1 | 2005-06-10 |  | ü | 1.95 |  | 102.7868 | 33.51% |  | 23.7527 | 7.743% |  |  | -4.7798 | -6.0456 | 0.62009 | 20.9189 | 10.7136 | 15.976 | 2.0229 |  |  | 17.9989
|  |  |  | Current | 2005-07-26 | 2005-06-27 |  |  | 1.562 |  | 64.9686 | 28.54% |  | -2.1399 | -0.94% |  |  | -4.5309 | -6.5662 | -5.0135 | 7.6192 | -8.4913 | 10.1052 | 1.2062 |  |  | 11.3114
|  |  | DS | Deviation | weeks | 2.4286 |  |  | -0.388 | 0 | -37.8182 | -4.971% | 0% | -25.8926 | -8.683% |  |  | 0.24894 | -0.52066 | -5.6335 | -13.2997 | -19.2049 | -5.8708 | -0.81673 |  |  | -6.6876
| PG75 | SGL | Adonis | Target | M1 | 2005-07-11 |  | ü | 3.537 |  | 100.8147 | 27.88% |  | 8.2761 | 2.289% |  |  | -1.9818 | -3.5789 | -4.4205 | 10.1699 | 0.18862 | 6.9033 | 1.3168 | 0.16377 |  | 8.3839
|  |  |  | Current | 2005-06-03 | 2005-07-11 |  |  | 2.6086 |  | 65.9669 | 26.18% |  | -5.1788 | -2.055% |  |  | -2.1476 | -2.8109 | -4.903 | 0.22948 | -9.632 | 6.4986 | 0.89933 | -2.6236 | -0.024765 | 4.7496
|  |  | pre-DS | Deviation | weeks | 0 |  |  | -0.92843 | 0 | -34.8478 | -1.7% | 0% | -13.4549 | -4.344% |  |  | -0.16574 | 0.76807 | -0.4825 | -9.9404 | -9.8206 | -0.40475 | -0.41745 | -2.7873 |  | -3.6343
| PG75 | EGL | Leopard ref. | Target | M1 | 2005-02-04 |  | ü | 2.255 |  | 30.8785 | 19.36% |  | 0.26589 | 0.1667% |  |  |  | -0.0143 | 3.4543 | -3.1741 | 0.26589
|  |  |  | Current | 2005-07-26 | 2005-02-04 |  |  | 1.4858 |  | 15.1857 | 14.52% |  | -3.9466 | -3.773% |  |  |  | 1.3193 | -0.29949 | -2.1462 | -1.1265 | -2.8201 |  |  |  | -2.8201
|  |  | M3 | Deviation | weeks | 0 |  |  | -0.76918 | 0 | -15.6928 | -4.844% | 0% | -4.2125 | -3.94% |  |  |  | 1.3336 | -3.7538 | 1.0279 | -1.3923 | -2.8201 |  |  |  | -2.8201
| PG65 | SGL | Leopard | Target | M1 | [16 empty] | 0 |  |  |  |  | 0
|  |  |  | Current | 2005-04-12 | [16 empty] | 0 |  |  |  |  | 0
|  |  |  | Deviation | weeks | 0 |  |  | 0 |  | 0 | 0% |  | 0 | 0% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Target | M1 | [16 empty] | 0 |  |  |  |  | 0
|  |  |  | Current | 2005-04-12 | [16 empty] | 0 |  |  |  |  | 0
|  |  |  | Deviation | weeks | 0 |  |  | 0 |  | 0 | 0% |  | 0 | 0% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Target | M1 | [16 empty] | 0 |  |  |  |  | 0
|  |  |  | Current | 2005-04-12 | [16 empty] | 0 |  |  |  |  | 0
|  |  |  | Deviation | weeks | 0 |  |  | 0 |  | 0 | 0% |  | 0 | 0% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Target: Basis is Scenario 2C-Strich; no detailed figures underneath Sales Margin as well as for break-down to quarters
|  | Ready to copy: |  |  |  | Traffic light - Time to market: | [5 empty] | automatic fill-in |  |  |  | Traffic light - Time to market: |  |  |  |  | manual entry
[6 empty] | green | No delay or earlier than target | [8 empty] | green
[6 empty] | yellow | Delay to target is < 4 weeks | [8 empty] | yellow
[6 empty] | red | Delay to target is > 4 weeks | [8 empty] | red
-
[6 empty] | Trend - Time to market: | [5 empty] | manual entry
|  |  |  | ü |  |  | Positive trend, e.g. significant positive delta to last reported value
No significant change
Negative trend, e.g. significant negative delta to last reported value