## Manual (hidden)
BJ-Projects in realization | [30 empty] | MD PM BA (BJ)
|  |  |  | Time to Market |  |  |  |  | Financials
| PG | Chip | Product | [5 empty] | Life Cycle | [6 empty] | Profit in FY05 |  |  |  | EBIT FY05 | Profit in FY06 |  |  |  | EBIT FY06 | Profit in FY07 |  |  |  | EBIT FY07
[6 empty] | Delivery | Status | Trend | Volume | S. Margin | S. Margin | Profit | Profit | Status | Trend | Q1 | Q2 | Q3 | Q4 | Total | Q1 | Q2 | Q3 | Q4 | Total | Q1 | Q2 | Q3 | Q4 | Total
[6 empty] | Start |  |  | (in mill. | (in mill. €) | (in %) | (in mill. €) | (in %) |  |  | (in | (in | (in | (in | (in | (in | (in | (in | (in | (in | (in | (in | (in | (in | (in
[9 empty] | units) | [6 empty] | mill. €) | mill. €) | mill. €) | mill. €) | mill. €) | mill. €) | mill. €) | mill. €) | mill. €) | mill. €) | mill. €) | mill. €) | mill. €) | mill. €) | mill. €)
| PG85 | EGL | Quail | Target | M-alpha (2C') | 2006-01-17 |  |  | 2.525 | 61.9635 | 36.09%
|  |  |  | Current | 2005-03-25 | 2006-02-06 |  |  | 3.365 | 30.7589 | 15.34% | -12.3148 | -6.143% |  |  |  | -0.2882 | -1.419 | -1.839 | -3.5462 | -2.25 | 0.77765 | 0.24667 | -4.199 | -5.4247 | -3.0379 | -0.30484 |  |  | -3.3428
|  |  | pre-M0 | Deviation | weeks | 2.8571 |  |  | 0.84 | -31.2046 | -20.75%
| PG85 | EGL | Flamingo | Target | M1 | 2005-10-24 |  |  | 2.95 | 91.7498 | 37% | 25.3945 | 10.24% |  |  | -0.28256 | -2.2475 | -2.6547 | -4.3239 | -9.5087 | 6.9992 | 12.1855 | 10.3044 | 3.17 | 32.659 | 2.2442 |  |  |  | 2.2442
|  |  |  | Current | 2005-03-15 | 2005-10-05 |  |  | 2.95 | 91.7498 | 37% | 25.3945 | 10.24% |  |  | -0.28256 | -2.2475 | -2.6547 | -4.3239 | -9.5087 | 6.9992 | 12.1855 | 10.3044 | 3.17 | 32.659 | 2.2442 |  |  |  | 2.2442
|  |  | M1 | Deviation | weeks | -2.7143 |  |  | 0 | 0 | 0% | 0 | 0% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| PG85 | EGL | Pelican | Target | M-alpha (2C') | 2006-03-15 |  |  | 2.15 | 62.4145 | 41.35%
|  |  |  | Current | 2005-03-15 | 2006-03-15 |  |  | 2.43 | 49.3337 | 29.55% | 10.4961 | 6.286%
|  |  | M-alpha | Deviation | weeks |  |  |  | -0.28 | 13.0808 | 0.11807
| PG75 | EG | Puma | Target | M1 | 2004-09-06 |  |  | 5.728 | 74.4044 | 18.96% | 10.6114 | 2.704% |  |  | 14.4437 | 1.6143 | -0.43787 | 1.0365 | 16.6566
|  |  |  | Current | 2005-04-19 | 2004-09-06 |  |  | 4.5144 | 50.4765 | 18.83% | -8.0068 | -2.986% |  |  | 10.4804 | -5.1373 | -1.4607 | -3.1125 | 0.77004
|  |  | launched | Deviation | weeks | 0 |  |  | -1.2136 | -23.928 | -0.1318% | -18.6182 | -5.69% |  |  | -3.9633 | -6.7515 | -1.0228 | -4.149 | -15.8866
| PG75 | EGL | Pegasus | Target | M1 | 2005-05-26 |  |  | 5.111 | 80.5855 | 24.72% | 5.5723 | 1.709% |  |  | -2.004 | -2.9916 | -0.88771 | 6.0067 | 0.12334 | 8.4863 | 0.78563 | -2.6346 |  | 6.6373
|  |  |  | Current | 2005-04-19 | 2005-06-17 |  |  | 0 | 0 | 0% | 0 | 0% |  |  | 0 | 0 | 4.2461e-08 | 4.2461e-08 | 8.4921e-08 | 0 | 0 | 0 |  | 0
|  |  | pre-M2 | Deviation | weeks | 3.1429 |  |  | -5.111 | -80.5855 | -24.72% | -5.5723 | -1.709% |  |  | 2.004 | 2.9916 | 0.88771 | -6.0067 | -0.12334 | -8.4863 | -0.78563 | 2.6346 |  | -6.6373
| PG65 | SGL | Leopard | Target | M1 | [14 empty] | 0 |  |  |  |  | 0
|  |  |  | Current | 2005-04-12 | [14 empty] | 0 |  |  |  |  | 0
|  |  |  | Deviation | weeks | 0 |  |  | 0 | 0 | 0% | 0 | 0% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Target | M1 | [14 empty] | 0 |  |  |  |  | 0
|  |  |  | Current | 2005-04-12 | [14 empty] | 0 |  |  |  |  | 0
|  |  |  | Deviation | weeks | 0 |  |  | 0 | 0 | 0% | 0 | 0% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Target | M1 | [14 empty] | 0 |  |  |  |  | 0
|  |  |  | Current | 2005-04-12 | [14 empty] | 0 |  |  |  |  | 0
|  |  |  | Deviation | weeks | 0 |  |  | 0 | 0 | 0% | 0 | 0% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Target: Basis is Scenario 2C-Strich; no detailed figures underneath Sales Margin as well as for break-down to quarters
|  | Ready to copy: |  |  |  | Traffic light - Time to market: |  |  |  |  | automatic fill-in |  |  | Traffic light - Time to market: |  |  |  |  | manual entry
[6 empty] | green | No delay or earlier than target | [6 empty] | green
[6 empty] | yellow | Delay to target is < 4 weeks | [6 empty] | yellow
[6 empty] | red | Delay to target is > 4 weeks | [6 empty] | red
-
[6 empty] | Trend - Time to market: |  |  |  |  | manual entry
|  |  |  | ü |  |  | Positive trend, e.g. signiificant positive delta to last reported value
No significant change
Negative trend, e.g. signiificant negative delta to last reported value

## Input
PHE Cockpit Chart 3G |  |  |  | CW 22 |  |  | 2006-05-30
Products in realization (M0 - S4)
|  |  |  | Next | Time to Market |  |  |  |  | Financials (last Milestone) | [6 empty] | Return Rate |  |  |  |  | Update-Status |  | Status
|  |  |  | Mile- |  |  | Delivery | Status | Trend | Volumes | R&D effort* | BOM | Conversion | thereof | Status | Trend | RR | RR | RR | Status | Trend
|  | Chip | Product | stone |  |  | Start |  |  |  | (in mill. €) | (in € p/u) | Cost** | Licenses/Royalties |  |  | HW | SW | total |  |  |  |  | Achievements | Issues | Next Steps | Total costs + R&D effort | Deviation * Quantity +R&D effort
[13 empty] | (in € p/u) | (in mill. €) |  |  | (in %) | (in %) | (in %)
| PG85 | 6250A | Kestrel | S4 | Target | at M1 | 2006-03-03 |  |  | 1600000 | 20.538 | 125.11 | 22.7 | 10.59 | 5.779% |  | 6 | 8 | 14 |  |  | TPM |  | - DS (retail) achieved at 7th april 2006 - 60K phones delivered to VKL - approx. 15K phones delivered to costumers | - Communication towards costumers to be improved - nCCPI trend goes in wrong direction (increasing) - VF indicates a limited approval for spain, france and netherlands | - Invite costumer interfaces from marketing to bidaily TTM meeting - Continue SW bug fixing according to TTV priorisation | 258312852.12 | 14927634.72
|  |  | EF81 | 2006-06-29 | Current | today | 2006-04-07 |  |  | 1608652 | 18.8 | 143.24 | 14.93 | 5.3 |  |  | 8.7 | 9.5 | 18.2
|  |  | Holger Petersen |  | Deviation | weeks | 5 |  |  | 8652 | -1.738 | 18.13 | -7.77 | -5.29 |  |  |  |  | 4.2 |  |  | TPM BA
N.N.
| PG95 | 6250A | Onyx | S2 | Target | M1 | 2006-10-20 |  |  | 950000 | 13.054 | 132.4 | 18.1 | 5 | -0.008156% |  |  |  | 13 |  |  | TPM |  | - B1-Run successfully finished and delivered - LC volume increased to 1'29 (via CR) | - GCF 3.22 approval period ends on 24.10. - still critical path - QCT stopped premium support for 6250A platform, Onyx will only get OEM support, will becomes critical related to Type Approval. - Time-line of accessory which will be bundled need to re-worked to ensure DS time-line and Ramp-up according to the phone time-line | - declaration of S2 (08.06.06) - B1-Run phone evaluation ongoing - B1+ Phone tape-out | 207199000 | -16900
|  |  |  | 2006-06-08 | Current | today | 2006-10-20 |  |  | 1290000 | 13.05 | 132.35 | 18.14 | 5.02 |  |  | 7 | 6 | 13
|  |  | Markus Feldhoff |  | Deviation | weeks | 0 |  |  | 340000 | -0.004 | -0.05 | 0.04 | 0.02 |  |  |  |  | 0 |  |  | TPM BA
Thomas Alkaemper
| PG75 | EGL | Leopard ref. |  | Target | M1 | 2005-02-04 |  | ü |  | 2.255 |  | 0.26589 | 0.26589 |  |  | M1 |  | 2005-02-04 |  | ü | TPM BA
[5 empty] | Current | 2005-10-25 | 2005-02-04 |  |  |  | 1.3811 |  | -8.6431 | -8.6431 |  |  | 2005-10-25 |  | 2005-02-04
[5 empty] | Deviation | weeks | 0 |  |  |  | -0.87395 |  | -8.909 | -8.909 |  |  | weeks |  | 0 |  |  | TPM
| PG95 | 6280 | Ruby | S0 | Target | at M0 | 2007-02-28 |  |  | 505000 | 14.905 | 194.38 | 20 | 5.84 | 0% |  |  |  | n.a |  |  | TPM |  | - S0 maturity for all HW related topics achieved by April 12th - Interim contract with HDD supplier Seagate ready to sign - General agreement on DRM scenario found during workshop in San Diego in week 19 | - operator requirements still unclear - Not all feasibility studies completed yet (memory requirements, Java, Chinese support, HDD power saving) - A feasible scenario for Microsoft DRM may not be ready within week 20, therefore the S0 might be delayed till end of May. - Delay of M1 until end June expected - to be confirmed at S0 - S25 has to be shifted by 6 weeks in order to achieve a feasible DRM scenario for both OMA DRM and Microsoft DRM. Shift of delivery start to end of March expected! | - Clarify feasibility of DRM scenario for Ruby in detail - Agreement with category mangement on "minimum" set of operator requirements needed to achieve Ruby timeline - Comitment of R&D management for SW resources for Ruby required - Find procedure regarding tools invest for the next weeks before M1 | 123166900 | 0
|  |  |  | 2006-04-28 | Current | today | 2007-03-29 |  |  | 505000 | 14.905 | 194.38 | 20 | 5.84 |  |  | n.a | n.a | n.a
|  |  | Detlef Wiesing |  | Deviation | weeks | 4.1429 |  |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | n.a |  |  | TPM BA
Manfred Schwarz
| PG95 | 6280 | Koala | M0 | Target | at Mα | 2007-04-28 |  |  | n.a. | n.a. | n.a. | n.a. | n.a. |  |  |  |  | n.a |  |  | TPM | x | - Koala on short list of VF - M0 declarations received by all parties, SW pending. Overall project M0 still in time feasible. - Major Koala delta features to Ruby verified and feasibility available - S0 preperation started | - SW support improved but still fully satisfactory | - Getting SW discipline up to speed. - Setting up SW top down planning till CW21. - first architekes will start working week 21 | #VALUE! | #VALUE!
|  |  |  | 2006-05-31 | Current | today | 2007-04-28 |  |  | n.a. | n.a. | n.a. | n.a. | n.a. |  |  | n.a | n.a | n.a
|  |  | Jörn Watzke |  | Deviation | weeks | 0 | [11 empty] | n.a |  |  | TPM BA
Th. Engelhardt
| PG95 | 6280 | Mallow | M0 | Target | at Mα | 2007-04-28 |  |  | n.a. | n.a. | n.a. | n.a. | n.a. |  |  |  |  | n.a |  |  | TPM |  | Mallow stopped due to lack of resources and shortage in R&D budget |  |  | #VALUE! | #VALUE!
|  |  | stopped |  | Current | today | 2007-04-28 |  |  | n.a. | n.a. | n.a. | n.a. | n.a. |  |  | n.a | n.a | n.a
|  |  | Thomas Neumann |  | Deviation | weeks | 0 | [11 empty] | n.a |  |  | TPM BA
Andreas Lang
| PG85 |  |  | Mx | Target | at M1 | 2006-02-24 |  |  |  | 100 | 100 | 100 | 100 |  |  |  |  | 12 |  |  |  |  | - comments | - comments | - comments
|  |  |  | xx.xx.xxxx | Current | today | 2006-02-24 |  |  |  | 70 | 80 | 80 | 80 |  |  | 5 | 10 | 15
|  |  | Name of CPM |  | Deviation | weeks | 0 |  |  |  | -30 | -20 | -20 | -20 |  |  |  |  | 3
| PG85 |  |  | Mx | Target | at M1 | 2006-04-28 |  |  |  | 100 | 100 | 100 | 100 |  |  |  |  | 9
|  |  |  | xx.xx.xxxx | Current | today | 2006-04-28 |  |  |  | 105 | 105 | 105 | 105 |  |  | 5 | 5.5 | 10.5 |  |  | TPM
|  |  | Name of CPM |  | Deviation | weeks | 0 |  |  |  | 5 | 5 | 5 | 5 |  |  |  |  | 1.5
| PG75 |  |  | Mx | Target | at M1 | 2005-08-19 |  | ü |  | 100 | 100 | 100 | 100 |  |  |  |  | 4.5 |  |  | TPM BA
|  |  |  | xx.xx.xxxx | Current | #REF! | 2005-08-04 |  |  |  | 115 | 115 | 115 | 115 |  |  | 2 | 2 | 4
[5 empty] | Deviation | weeks | -2.1429 |  |  |  | 15 | 15 | 15 | 15 |  |  |  |  | -0.5 |  |  | TPM
| PG85 |  |  | Mx | Target | at M1 | 2006-02-24 |  |  |  | 100 | 100 | 100 | 100 |  |  |  |  | 12 |  |  |  |  | - comments | - comments | - comments
|  |  |  | xx.xx.xxxx | Current | today | 2006-02-24 |  |  |  | 70 | 80 | 80 | 80 |  |  | 5 | 10 | 15 |  |  | TPM BA
|  |  | Name of CPM |  | Deviation | weeks | 0 |  |  |  | -30 | -20 | -20 | -20 |  |  |  |  | 3
TPM
| PG85 |  |  | Mx | Target | at M1 | 2006-04-28 |  |  |  | 100 | 100 | 100 | 100 |  |  |  |  | 9
|  |  |  | xx.xx.xxxx | Current | today | 2006-04-28 |  |  |  | 105 | 105 | 105 | 105 |  |  | 5 | 5.5 | 10.5
|  |  | Name of CPM |  | Deviation | weeks | 0 |  |  |  | 5 | 5 | 5 | 5 |  |  |  |  | 1.5 |  |  | TPM BA
| PG75 |  |  | Mx | Target | at M1 | 2005-08-19 |  | ü |  | 100 | 100 | 100 | 100 |  |  |  |  | 4.5 |  |  | TPM
|  |  | Axx | xx.xx.xxxx | Current | #REF! | 2005-08-04 |  |  |  | 115 | 115 | 115 | 115 |  |  | 2 | 2 | 4
|  |  | Name of CPM |  | Deviation | weeks | -2.1429 |  |  |  | 15 | 15 | 15 | 15 |  |  |  |  | -0.5
TPM BA
| PG95 | 6250A | PHE/PHA | n/a | Target | n/a |  |  |  | n.a. | n.a. | n.a. | n.a. | n.a. |  |  |  |  | n.a. |  |  | TPM |  | - Merge of Kestrel IP10.0.1 SW and AMSS 6.2.93.21 modem part on Windows based platform database done. - Related SW build delivered as official MSM6250A SW version IP1.0.4 to PHA. | - Project transfer (responsibility) from TPM to RD organization decided. Next steps under definition. - Security concept for Merlin (due to memory technology change) and Caesar (due to H3G requirements) under discussion. - PHA statement: Necessary data transfer of production relevant information between BACH and SAP system will be supported by R&D Bijing. - PHA statement: Required components for remaining prototype runs, pilot and ram up will be ordered by BQY and shipped afterwards to BMS. -> Currently it is not clarified, in which way several tasks will be handled to assure mass production in BMS (e.g. component release process, CR process, PICS linking). | - Integration of official Qualcomm AMSS 6.2.93.21 SW version into PF DB ongoing. - Integration of full AMSS version scheduled for cw19. - Afterwards back porting to Unix data base and merge with current Onyx SW branch planned. Target for finalization is begin of June 2006. | #VALUE! | #VALUE!
|  |  | Migration |  | Current | n/a |  |  |  | n.a. | n.a. | n.a. | n.a. | n.a. |  |  | n.a | n.a | n.a.
|  |  | Michael Crutziger |  | Deviation | weeks | 0 | [11 empty] | n.a. |  |  | TPM BA
Products in Life Cycle (S4 - M4)
| PG85 | 6250 | Wolf 5 | M3 | Target | at M1 | 2005-09-21 |  |  | 851000 | 36.941 | 135 | 26.94 | 13.03 | 1.558% |  |  |  | 16 |  |  | TPM | x | - SFR approval available - first 3k delivered week 20 - maps for turkey available. Sales is planed in CW22 - final SW SVN26 availabe for slovenia and norway - navigation for easter europe available - Bug fix for russian variant integrated | no issues | - no actions planed anymore | 46009640 | 716760
|  |  | SXG 75 | 2006-03-31 | Current | today | 2005-12-29 |  |  | 56000 | 35.77 | 162.06 | 33.59 | 16.82 |  |  | 5 | 11 | 16
|  |  | Th. Engelhardt |  | Deviation | weeks | 14.1429 |  |  | -795000 | -1.171 | 27.06 | 6.65 | 3.79 |  |  |  |  | 0 |  |  | TPM BA
Jörn Watzke
| PG75 |  |  | Mx | Target | at M1 | 2005-08-19 |  | ü |  | 100 | 100 | 100 | 100 |  |  |  |  | 4.5
|  |  | Axx | xx.xx.xxxx | Current | #REF! | 2005-08-04 |  |  |  | 115 | 115 | 115 | 115 |  |  | 2 | 2 | 4
|  |  | Name of CPM |  | Deviation | weeks | -2.1429 |  |  |  | 15 | 15 | 15 | 15 |  |  |  |  | -0.5
TPM
| PG75 |  | Leopard ref. |  | Target | M1 | 2005-02-04 |  | ü |  | 2.255 |  | 0.26589 | 0.26589 |  |  | M1 |  | 2005-02-04 |  | ü
[5 empty] | Current | 2005-10-25 | 2005-02-04 |  |  |  | 1.3811 |  | -8.6431 | -8.6431 |  |  | 2005-10-25 |  | 2005-02-04
[5 empty] | Deviation | weeks | 0 |  |  |  | -0.87395 |  | -8.909 | -8.909 |  |  | weeks |  | 0 |  |  | TPM BA
| PG85 |  |  | Mx | Target | at M1 | 2006-02-24 |  |  |  | 100 | 100 | 100 | 100 |  |  |  |  | 12 |  |  | TPM |  | - comments | - comments | - comments
|  |  | SLxx | xx.xx.xxxx | Current | today | 2006-02-24 |  |  |  | 70 | 80 | 80 | 80 |  |  | 5 | 10 | 15
|  |  | Name of CPM |  | Deviation | weeks | 0 |  |  |  | -30 | -20 | -20 | -20 |  |  |  |  | 3
TPM BA
| PG85 |  |  | Mx | Target | at M1 | 2006-04-28 |  |  |  | 100 | 100 | 100 | 100 |  |  |  |  | 9
|  |  | Cxx | xx.xx.xxxx | Current | today | 2006-04-28 |  |  |  | 105 | 105 | 105 | 105 |  |  | 5 | 5.5 | 10.5
|  |  | Name of CPM |  | Deviation | weeks | 0 |  |  |  | 5 | 5 | 5 | 5 |  |  |  |  | 1.5
EOL (M4 - M5)
| PG85 | 6250 | Wolf 4 | Mx | Target | at M1 | 2006-11-04 |  |  |  | 37.3 | 117 | 12.8 | n.a. |  |  |  |  | n.a |  |  | TPM |  |  | Scrap Estiamtion 8,4 Mio (without all componenets which can be used in Wolf 5 |  | 58068000 | -1724000
|  |  | SG 75 | xx.xx.xxxx | Current | today | cancelled |  |  | 160000 | 33 | 126.56 | 19.34 | n.a. |  |  | n.a | n.a | n.a
|  |  | Jörn Watzke |  | Deviation | weeks |  |  |  |  | -4.3 | 9.56 | 6.54 | [5 empty] | n.a |  |  | TPM BA
| PG75 |  |  | Mx | Target | at M1 | 2005-08-19 |  | ü |  | 100 | 100 | 100 | 100 |  |  |  |  | 4.5 |  |  | TPM BA
|  |  | M75 | xx.xx.xxxx | Current | #REF! | 2005-08-04 |  |  |  | 115 | 115 | 115 | 115 |  |  | 2 | 2 | 4
|  |  | Name of CPM |  | Deviation | weeks | -2.1429 |  |  |  | 15 | 15 | 15 | 15 |  |  |  |  | -0.5
| PG75 |  | Leopard ref. |  | Target | M1 | 2005-02-04 |  | ü |  | 2.255 |  | 0.26589 | 0.26589 |  |  | M1 |  | 2005-02-04 |  | ü
[5 empty] | Current | 2005-10-25 | 2005-02-04 |  |  |  | 1.3811 |  | -8.6431 | -8.6431 |  |  | 2005-10-25 |  | 2005-02-04
[5 empty] | Deviation | weeks | 0 |  |  |  | -0.87395 |  | -8.909 | -8.909 |  |  | weeks |  | 0
TPM
| PG85 |  |  | Mx | Target | at M1 | 2006-02-24 |  |  |  | 100 | 100 | 100 | 100 |  |  |  |  | 12 |  |  |  |  | - comments | - comments | - comments
|  |  | SLxx | xx.xx.xxxx | Current | today | 2006-02-24 |  |  |  | 70 | 80 | 80 | 80 |  |  | 5 | 10 | 15
|  |  | Name of CPM |  | Deviation | weeks | 0 |  |  |  | -30 | -20 | -20 | -20 |  |  |  |  | 3 |  |  | TPM BA
| PG85 |  |  | Mx | Target | at M1 | 2006-04-28 |  |  |  | 100 | 100 | 100 | 100 |  |  |  |  | 9 |  |  | TPM
|  |  | Cxx | xx.xx.xxxx | Current | today | 2006-04-28 |  |  |  | 105 | 105 | 105 | 105 |  |  | 5 | 5.5 | 10.5
|  |  | Name of CPM |  | Deviation | weeks | 0 |  |  |  | 5 | 5 | 5 | 5 |  |  |  |  | 1.5
TPM BA
[5 empty] | Traffic light - Time to market | [5 empty] | Traffic light - Financials | [6 empty] | Traffic light - Return Rate
[5 empty] | green | No delay or earlier than target |  |  |  |  | green | On track or above target | [5 empty] | green |  | On track or below target
[5 empty] | yellow | Delay to target is < 4 weeks |  |  |  |  | yellow | Below target (deviation max. 10% of target) | [5 empty] | yellow |  | Above target (deviation max. 20% of target)
[5 empty] | red | Delay to target is > 4 weeks |  |  |  |  | red | Below target (deviation >10% of target) | [5 empty] | red |  | Above target (deviation >20% of target)
[5 empty] | Trend - Financials | [12 empty] | * R&D effort: direct R&D efforts
** Conversions Costs: Value Add + HK relevant licences
|  |  |  | ü |  | Positive trend, e.g. significant positive delta to last reported value
No significant change
Negative trend, e.g. significant negative delta to last reported value
Note on M13: Fascher/Feldhoff: has to be adapted (increase by approx. 50cent) in case of ordering tool for 30% upside potential (650k€) caused by CR to increase volume to 1'29

## Input (2) (hidden)
BJ-Projects in realization | [32 empty] | MD PM BA (BJ)
|  |  |  | Time to Market |  |  |  |  | Financials
| PG | Chip | Product | [5 empty] | Life Cycle | [8 empty] | Profit in FY05 |  |  |  | EBIT FY05 | Profit in FY06 |  |  |  | EBIT FY06 | Profit in FY07 |  |  |  | EBIT FY07
[6 empty] | Delivery | Status | Trend | Volume | Sales | S.-Margin | S. Margin | Gross | Profit | Profit | Status | Trend | Q1 | Q2 | Q3 | Q4 | Total | Q1 | Q2 | Q3 | Q4 | Total | Q1 | Q2 | Q3 | Q4 | Total
|  |  | MS-status |  |  | Start |  |  | (in mill. | (in mill. €) | (in mill. €) | (in %) | Margin | (in mill. €) | (in %) |  |  | (in | (in | (in | (in | (in | (in | (in | (in | (in | (in | (in | (in | (in | (in | (in
[9 empty] | units) |  |  |  | (in %) |  |  |  |  | mill. €) | mill. €) | mill. €) | mill. €) | mill. €) | mill. €) | mill. €) | mill. €) | mill. €) | mill. €) | mill. €) | mill. €) | mill. €) | mill. €) | mill. €)
| PG75 | EG | Puma | Target | M1 | 2004-09-06 |  |  | 0.721 | 38.468 | 13.4219 | 34.89% | 28.06% | -9.8324 | -25.56% |  |  |  |  | -0.73827 | -2.5564 | -3.2947 | -3.1616 | -3.8475 | -0.11917 | 0.91068 | -6.2176 | 0.23762 | -0.55767 |  |  | -0.32005
|  |  |  | Current | 2005-06-27 | 2006-04-28 |  |  | 0.721 | 38.468 | 13.4219 | 34.89% | 28.06% | -9.8324 | -25.56% |  |  |  |  | -0.73827 | -2.5564 | -3.2947 | -3.1616 | -3.8475 | -0.11917 | 0.91068 | -6.2176 | 0.23762 | -0.55767 |  |  | -0.32005
|  |  | M3 | Deviation | weeks | 85.5714 |  |  | 0 | 0 | 0 | 0% | 0% | 0 | 0% |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
| PG85 | SG2 | Brambling | Target | M-alpha | 2006-05-26 |  |  | 1.915 | 231.8 | 69.56 | 30% | 23.4% | 1.884 | 0.81% | [6 empty] | -3.5229 |  |  |  |  | 5.4074
|  |  |  | Current | 2005-07-29 | 2006-06-26 |  |  | 2.1913 | 268.4 | 71.7 | 26.7% | 20.7% | -17.3 | -6.4% |  |  |  |  | -7.4422 | -4.5589 | -12.0011 | -4.6275 | -5.1991 | -3.8552 | 2.7049 | -10.9769 | 6.3148 | 0.13242 | -0.7421 |  | 5.7051
|  |  | pre-M0 | Deviation | weeks | 4.4286 |  |  | 0.27627 | 36.6 | 2.14 | -3.3% | -2.7% | -19.184 | -7.21% |  |  |  |  | -7.4422 | -4.5589 | -8.4782 | -4.6275 | -5.1991 | -3.8552 | 2.7049 | -16.3843 | 6.3148 | 0.13242 | -0.7421 |  | 5.7051
| PG85 | EGL | Quail | Target | M1 | 2006-01-24 |  |  | 1.7882 | 108.4 | 29.7825 | 27.48% | 21.5% | 2.3621 | 2.18% |  |  | 0 | -0.24951 | -1.3033 | -1.9769 | -3.5297 | -3.3304 | 0.26347 | 3.2437 | 2.5946 | 2.7714 | 2.6251 | 0.49527 |  |  | 3.1204
|  |  |  | Current | 2005-07-29 | 2006-01-24 |  |  | 1.7882 | 108.4 | 29.7825 | 27.48% | 21.5% | 2.3621 | 2.18% |  |  | 0 | -0.24951 | -1.3033 | -1.9769 | -3.5297 | -3.3304 | 0.26347 | 3.2437 | 2.5946 | 2.7714 | 2.6251 | 0.49527 |  |  | 3.1204
|  |  | M1 | Deviation | weeks | 0 |  |  | 0 | 0 | 0 | 0% | 0% | 0 | 0% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
| PG85 | EGL | Finch | Target | M1 | 2006-01-26 |  |  | 3.3276 | 148.2236 | 33.2953 | 22.46% | 15.47% | -3.4771 | -2.4% |  |  | 0 | -0.24752 | -1.0186 | -1.971 | -3.2371 | -2.8106 | 1.4615 | 2.2465 | -0.14274 | 0.75461 | -0.99466 |  |  |  | -0.99466
|  |  |  | Current | 2005-07-30 | 2006-01-26 |  |  | 3.3276 | 148.2236 | 33.2953 | 22.46% | 15.47% | -3.4771 | -2.4% |  |  | 0 | -0.24752 | -1.0186 | -1.971 | -3.2371 | -2.8106 | 1.4615 | 2.2465 | -0.14274 | 0.75461 | -0.99466 |  |  |  | -0.99466
|  |  | M1 | Deviation | weeks | 0 |  |  | 0 | 0 | 0 | 0% | 0% | 0 | 0% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| PG85 | SGL | Plover | Target | M0 | 2006-04-28 |  |  | 1.95 | 152.8 | 40.9527 | 26.8% | 20.1% | -15.6228 | -10.22% |  |  |  | -5.4674 | -3.1016 | -4.5392 | -13.1081 | -4.5804 | -5.0349 | 0.74272 | 2.8911 | -5.9815 | 2.2379 | 0.95549 | 0.27339 |  | 3.4668
|  |  |  | Current | 2005-08-30 | 2006-05-17 |  |  | 1.95 | 146.2 | 34.4 | 23.5% | 16.7% | -21.5 | -14.7% |  |  |  | -5.4674 | -3.1016 | -4.5392 | -13.1081 | -4.5804 | -5.0349 | 0.74272 | 2.3468 | -6.5258 | 0.61018 | -1.4987 | -1.0078 |  | -1.8963
|  |  | M0 | Deviation | weeks | 2.7143 |  |  | 0 | -6.6 | -6.5527 | -3.297% | -3.4% | -5.8772 | -4.477% |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -0.54433 | -0.54433 | -1.6277 | -2.4542 | -1.2812 |  | -5.3631
| PG85 | EGL | Flamingo | Target | M1 | 2005-10-24 |  |  | 2.95 |  | 91.7498 | 37% |  | 25.3945 | 10.24% |  |  | -0.28256 | -2.2475 | -2.6547 | -4.3239 | -9.5087 | 6.9992 | 12.1855 | 10.3044 | 3.17 | 32.659 | 2.2442 |  |  |  | 2.2442
|  |  |  | Current | 2005-07-26 | 2005-10-24 |  |  | 1.937 |  | 57.6576 | 37.49% |  | 11.5031 | 7.48% |  |  | -0.38786 | -1.0102 | -2.2328 | -4.671 | -8.3018 | 4.8144 | 8.9258 | 4.7278 | 1.4307 | 19.8987 | -0.093788 |  |  |  | -0.093788
|  |  | M1 | Deviation | weeks | 0 |  |  | -1.013 | 0 | -34.0922 | 0.4989% | 0% | -13.8914 | -2.759% |  |  | -0.1053 | 1.2373 | 0.42198 | -0.34708 | 1.2069 | -2.1848 | -3.2598 | -5.5766 | -1.7393 | -12.7603 | -2.338 |  |  |  | -2.338
| PG85 | EGL | Pelican | Target | M1 | 2006-03-20 |  |  | 1.4469 | 106.2 | 35.0321 | 33% | 26.8% | 10.236 | 9.641% |  |  |  |  | -0.32863 | -1.3589 | -1.6875 | -2.2635 | -1.9855 | 7.5107 | 5.9896 | 9.2513 | 2.6889 | -0.011098 | -0.0055488 |  | 2.6722
|  |  |  | Current | 2005-08-31 | 2006-03-20 |  |  | 1.4469 | 106.2 | 35.0321 | 33% | 26.8% | 10.236 | 9.641% |  |  |  |  | -0.32863 | -1.3589 | -1.6875 | -2.2635 | -1.9855 | 7.5107 | 5.9896 | 9.2513 | 2.6889 | -0.011098 | -0.0055488 |  | 2.6722
|  |  | M1 | Deviation | weeks | 0 |  |  | 0 | 0 | 0 | 0 | 0% | 0 | 0% |  |  |  |  | 0 | 0 | 0
| PG75 | EG | Puma | Target | M1 | 2004-09-06 |  | ü | 5.728 |  | 74.4044 | 18.96% |  | 10.6114 | 2.704% |  |  | 14.4437 | 1.6143 | -0.43787 | 1.0365 | 16.6566 | 0 |  |  |  | 0
|  |  |  | Current | 2005-07-26 | 2004-09-06 |  |  | 4.0741 |  | 39.7807 | 16.2% |  | -14.5046 | -5.907% |  |  | 9.9847 | -6.6019 | -3.8156 | -2.8651 | -3.298 | -2.43 |  |  |  | -2.43
|  |  | M3 | Deviation | weeks | 0 |  |  | -1.6539 | 0 | -34.6238 | -2.758% | 0% | -25.116 | -8.61% |  |  | -4.459 | -8.2162 | -3.3778 | -3.9016 | -19.9546 | -2.43 |  |  |  | -2.43
| PG75 | EG | Artemis | Target | M1 | 2005-01-07 |  | ü | 4.251 |  | 52.2165 | 23.9% |  | 7.8867 | 3.6% |  |  | -1.6638 | 1.6239 | 1.0243 | 2.6942 | 3.6785 | 3.0139 | 0.9981 | 0.19818 |  | 4.2102
|  |  |  | Current | 2005-07-26 | 2005-01-14 |  |  | 0.70357 |  | 7.6926 | 20.02% |  | -1.1946 | -3.807% |  |  | -0.64867 | 0.35327 | -0.75262 | -0.40289 | -1.4509 | -0.012278 |  |  |  | -0.012278
|  |  | pre-M3 | Deviation | weeks | 1 |  |  | -3.5474 | 0 | -44.524 | -3.888% | 0% | -9.0813 | -7.407% |  |  | 1.0152 | -1.2706 | -1.7769 | -3.0971 | -5.1294 | -3.0262 |  |  |  | -4.2225
| PG75 | EG | Libra | Target | M1 | 2005-05-09 |  | ü | 6.14 |  | 74.5469 | 23.46% |  | 7.2008 | 2.266% |  |  | -2.1889 | -3.7108 | -0.48376 | 7.5289 | 1.1455 | 8.1185 | 0.069853 | -1.1202 |  | 7.0681
|  |  |  | Current | 2005-07-26 | 2005-05-24 |  |  | 2.564 |  | 21.2408 | 16.73% |  | -13.4864 | -10.62% |  |  | -2.1969 | -3.6805 | -5.5201 | 0.44042 | -10.9571 | 0.35386 | -0.83555 | -1.0347 |  | -1.5164
|  |  | DS | Deviation | weeks | 2.1429 |  |  | -3.576 | 0 | -53.3061 | -6.73% | 0% | -20.6872 | -12.89% |  |  | -0.0080675 | 0.030241 | -5.0363 | -7.0885 | -12.1027 | -7.7646 | -0.90541 | 0.08548 |  | -8.5845
| PG75 | EGL | Dorado | Target | M1 | 2005-05-19 |  | ü | 11.532 |  | 84.4067 | 20.74% |  | 7.9916 | 1.963% |  |  | -1.6735 | -2.9824 | -0.83512 | 4.466 | -1.0251 | 8.7452 | 3.3302 | -2.9822 |  | 9.0933
|  |  |  | Current | 2005-07-28 | 2005-06-07 |  |  | 5.8223 |  | 22.9388 | 11.74% |  | -19.3293 | -9.89% |  |  | -2.1106 | -2.8306 | -0.76589 | -4.5349 | -10.242 | -5.9904 | -3.0496 | -0.0029082 |  | -9.0429
|  |  | DS | Deviation | weeks | 2.7143 |  |  | -5.7097 | 0 | -61.4679 | -8.999% | 0% | -27.3208 | -11.85% |  |  | -0.43711 | 0.15185 | 0.069228 | -9.0009 | -9.2169 | -14.7356 | -6.3798 | 2.9793 |  | -18.1361
| PG75 | SGL | Sirius | Target | M1 | 2005-06-28 |  | ü | 1.35 |  | 94.1447 | 38.37% |  | 24.7312 | 10.08% |  |  | -4.4331 | -5.5005 | -1.7756 | 14.713 | 3.0038 | 18.7561 | 5.6929 | 0.17863 |  | 24.6276
|  |  |  | Current | 2005-06-27 | 2005-06-27 |  |  | 0.55401 |  | 28.8964 | 31.23% |  | -9.2569 | -10% |  |  | -3.9799 | -4.5422 | -3.8348 | 2.418 | -9.9389 | 2.7388 | 0.45719 | 0.38618 |  | 3.5822
|  |  | DS | Deviation | weeks | -0.14286 |  |  | -0.79599 | 0 | -65.2483 | -7.143% | 0% | -33.9881 | -20.08% |  |  | 0.45324 | 0.95832 | -2.0592 | -12.295 | -12.9427 | -16.0173 | -5.2357 | 0.20755 |  | -21.0454
| PG75 | EGL | Pegasus | Target | M1 | 2005-05-26 |  | ü | 5.111 | 328 | 80.5855 | 24.72% | 17.3% | 5.5723 | 1.709% |  |  | -2.004 | -2.9916 | -0.88771 | 6.0067 | 0.12334 | 8.4863 | 0.78563 | -2.6346 |  | 6.6373
|  |  |  | Current | 2005-06-30 | 2005-06-17 |  |  | 2.5655 | 62.9 | 20.4 | 32.4% | 26.1% | -8.136 | -5.942% |  |  | -2.621 | -3.2344 | -3.196 | 1.0602 | -7.9913 | 1.5889 | -0.010382 | -1.0699 |  | 0.50861
|  |  | DS | Deviation | weeks | 3.1429 |  |  | -2.5455 | -265.1 | -60.1855 | 7.678% | 8.8% | -13.7082 | -7.652% |  |  | -0.61699 | -0.24276 | -2.3083 | -4.9466 | -8.1146 | -6.8974 | -0.79601 | 1.5647 |  | -6.1287
| PG75 | SGL | Phoenix | Target | M1 | 2005-06-10 |  | ü | 1.95 |  | 102.7868 | 33.51% |  | 23.7527 | 7.743% |  |  | -4.7798 | -6.0456 | 0.62009 | 20.9189 | 10.7136 | 15.976 | 2.0229 |  |  | 17.9989
|  |  |  | Current | 2005-07-26 | 2005-06-27 |  |  | 1.562 |  | 64.9686 | 28.54% |  | -2.1399 | -0.94% |  |  | -4.5309 | -6.5662 | -5.0135 | 7.6192 | -8.4913 | 10.1052 | 1.2062 |  |  | 11.3114
|  |  | DS | Deviation | weeks | 2.4286 |  |  | -0.388 | 0 | -37.8182 | -4.971% | 0% | -25.8926 | -8.683% |  |  | 0.24894 | -0.52066 | -5.6335 | -13.2997 | -19.2049 | -5.8708 | -0.81673 |  |  | -6.6876
| PG75 | SGL | Adonis | Target | M1 | 2005-07-11 |  | ü | 3.537 |  | 100.8147 | 27.88% |  | 8.2761 | 2.289% |  |  | -1.9818 | -3.5789 | -4.4205 | 10.1699 | 0.18862 | 6.9033 | 1.3168 | 0.16377 |  | 8.3839
|  |  |  | Current | 2005-06-03 | 2005-07-11 |  |  | 2.6086 |  | 65.9669 | 26.18% |  | -5.1788 | -2.055% |  |  | -2.1476 | -2.8109 | -4.903 | 0.22948 | -9.632 | 6.4986 | 0.89933 | -2.6236 | -0.024765 | 4.7496
|  |  | pre-DS | Deviation | weeks | 0 |  |  | -0.92843 | 0 | -34.8478 | -1.7% | 0% | -13.4549 | -4.344% |  |  | -0.16574 | 0.76807 | -0.4825 | -9.9404 | -9.8206 | -0.40475 | -0.41745 | -2.7873 |  | -3.6343
| PG75 | EGL | Leopard ref. | Target | M1 | 2005-02-04 |  | ü | 2.255 |  | 30.8785 | 19.36% |  | 0.26589 | 0.1667% |  |  |  | -0.0143 | 3.4543 | -3.1741 | 0.26589
|  |  |  | Current | 2005-07-26 | 2005-02-04 |  |  | 1.4858 |  | 15.1857 | 14.52% |  | -3.9466 | -3.773% |  |  |  | 1.3193 | -0.29949 | -2.1462 | -1.1265 | -2.8201 |  |  |  | -2.8201
|  |  | M3 | Deviation | weeks | 0 |  |  | -0.76918 | 0 | -15.6928 | -4.844% | 0% | -4.2125 | -3.94% |  |  |  | 1.3336 | -3.7538 | 1.0279 | -1.3923 | -2.8201 |  |  |  | -2.8201
| PG65 | SGL | Leopard | Target | M1 | [16 empty] | 0 |  |  |  |  | 0
|  |  |  | Current | 2005-04-12 | [16 empty] | 0 |  |  |  |  | 0
|  |  |  | Deviation | weeks | 0 |  |  | 0 |  | 0 | 0% |  | 0 | 0% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Target | M1 | [16 empty] | 0 |  |  |  |  | 0
|  |  |  | Current | 2005-04-12 | [16 empty] | 0 |  |  |  |  | 0
|  |  |  | Deviation | weeks | 0 |  |  | 0 |  | 0 | 0% |  | 0 | 0% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Target | M1 | [16 empty] | 0 |  |  |  |  | 0
|  |  |  | Current | 2005-04-12 | [16 empty] | 0 |  |  |  |  | 0
|  |  |  | Deviation | weeks | 0 |  |  | 0 |  | 0 | 0% |  | 0 | 0% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Target: Basis is Scenario 2C-Strich; no detailed figures underneath Sales Margin as well as for break-down to quarters
|  | Ready to copy: |  |  |  | Traffic light - Time to market: | [5 empty] | automatic fill-in |  |  |  | Traffic light - Time to market: |  |  |  |  | manual entry
[6 empty] | green | No delay or earlier than target | [8 empty] | green
[6 empty] | yellow | Delay to target is < 4 weeks | [8 empty] | yellow
[6 empty] | red | Delay to target is > 4 weeks | [8 empty] | red
-
[6 empty] | Trend - Time to market: | [5 empty] | manual entry
|  |  |  | ü |  |  | Positive trend, e.g. significant positive delta to last reported value
No significant change
Negative trend, e.g. significant negative delta to last reported value