| Mailing List: | Mailing List |
| --- | --- |
| Date: | 29.11.05 |
| Time: | 10:00-11:30 |
| Location: | Aal / KLf / Mch |
| Moderated By: | H. Asmussen Tel.: +49(2842)95-4370 |
| Minutes by: | P. Farrenkothen Tel.: +49(2842)95-4422 |
| Action Items: | Action Items |
| Participants: | Alkämper, Thomas; TAl; Klebsch, Wolfgang; WKl. Asmussen, Holger; HAs; Kroesen, Klaus; KKr. Bauregger, Josef; JBa; Kockmann, Jürgen; JKo. Betting, Andreas; ABe; Lang, Andreas; ALa. Christiansen, Keld; KCr; Neumann, Thomas; TNe. Friedl, Claus; CFr; Roehrig, Daniel; DRö. Dalmose, Claus; CDa; Rudolph, Tom; TRu. Faessler, Georg; GFä; Soerensen, Karsten Roer; KRS. Farrenkothen, Peter; PFa; Stokholm, Tony; TSt. Feldhoff, Markus; MFe. Geiger, Ulrich; UGe; Deputies:. Karacelik, Hasan; HKa; Hermanns, Thomas; THe. Kern, Ralf; RKe. |
| Meeting Reason | ### PG2 weekly (CW 48) |
| Organisation | ### Dial In: +49 69 4035 9803 ### Code: 94096 # ### Support: using *0 (Serv.-Nr. 0180 2 0161 33) ### Mute phone: *6 |
| Topic | Agenda Topic Title Owner Time |
| Next Meetings | ### CW 47 Tue 22.11. PG2 weekly 10:00 – 11:30 ### CW 48 Tue 29.11. PG2 weekly 10:00 – 11:30 ### CW 49 Tue 06.12. PG2 weekly 10:00 – 11:30 |

| Topic No. | General | Who | When |
| --- | --- | --- | --- |
| 1 | Classification: New classification for products decided by PD board for different complexity classes in the system. Class 1: Smallest class like Condor, 4'0 EUR, some changes in ID and for PCB Class 2: like Aries, 6'5 EUR Class 3: more complex product, 16'5 EUR, product with basis like W5 upgraded to to a Kestrel, new form factor of PCB, general complexity class issues Class 4: highest complexity class, ≥ 40'0 EUR like Minos, Swan Apoxi, Diamond Note: Class 1 phone do not indicate phones only for beginners! For future decisions, it need to be clarified what the program is able to do in order to set up the right skills and to ensure the resources. Due to site strategic issues, ME85 (Jerry) could be possible for Aal, but not committed so far. Pls. do not communicate! |  | Info |
| 2 | Meeting Schedule: Due to OC (Operational Council) with Dr. Eickholt each Thuesday, PG2 weekly was decided to be shifted to Thursday 10:00 – 12:00. HAs will invite by separate mail. | HAs | CW 48 |
| 3 | Organization: AI: HAs to send out slides about new organizational set up (PHE/PG1-2/TPM site) to each of his Direct Reports. | HAs | CW 48 |
| 4 | Travel Request: Point out reason for travel and write a travel report afterwards (highlight participants, content/topics of the meeting, result/conclusion, make side talk about the professionalism, meeting organisation,…). It's not allowed to forward travel reports to 3rd persons w/o having agreed with HAs/CoC. | All | Info |
| 5 | Update PMC: Project Manger are requested to continuously update planning data base in order to secure reliability of milestone planning and other project related data (documentation, project description,…). | TPM | Regular |
| Topic No. | Product Projects | Who | When |
| 6 | Condor: General S4-date for all parties (except MD, QM and SDQM) planned for Dec, 16th and earlier as aspected (M1-plan was: DS 25.11.05, S4 13.01.06). Actually, 13k of phones have been sold and another 25k of no ID's (due to missing battery covers) are on stock. In total an 80k order was placed, but no possibility to deliver due to missing parts. AI: DRö to take care that SW-R7* will be available in the market asap. Tops & Flops: | DRö |  |
| 7 | Hydra: SW Quality is not ensured. See Tops & Folps for further details. Flash topic only relevant for Hydra because Minos uses different flash. Don't focus only on SW platform but take care on specific variants of SW! Verify requirements together with PM. Time schedule as agreed: 25.11.05: limited SW check-in, operator things included (appr. 40 topics), start system test on weekend 26.11.05: unlimited SW check-in 28.11.05: deliver SW to O2 and T-mobile 07.12.05: Approval assumed by Operator 08.12.05: Delivery of phones Quality related errors are: 1) Vibration stops (necessary to remove the battery from device) 2) Lost of network connection (phone isn't able to re-connect by it's own) 3) Audio problem under certain condition (audio in uplink as well as in downlink direction) Tops & Flops: |  |  |
| 8 | Obsidian: M0 milestone planned for Nov. 29th with only 4 days delay to former schedule. High attractive liquid design is actually under discussion, but only makes sense if thickness of << 15 mm will be achieved. This seems of course to be realistic from technical point of view and a thickness of 12 mm was guaranteed by MD KKr today. Timeline as well seems to be not critical. AI: EMC/Antenna, RF and BB to be double checked! Enable site pass in order to clearly figure out what we can get! Tops & Flops: | TSt |  |
| 9 | Philippe: Request for introduction of side keys to the product (only needed for volume). S0 milestone (Plan: 18.11.05) delayed by appr. 2 weeks. Milestone planning to be re-worked, PMC to be updated accordingly. Tops & Flops: | CDa |  |
| 10 | Polaris: The 6 pogo-pins within the product are not implemented due to SAR reason, but part of the antenna concept to ensure the right antenna performance. These 6 pins are really needed. Solution was found to overcome the ST resource problem for tests. Tops & Flops: |  |  |
| 11 | Swan Apoxi: No actual status presented by TPM due to limited time. See Tops & Flops for details. Tops & Flops: |  |  |
| 12 | Swift: Only MM SW has influence on time schedule. Other features do not have impact on time line. PMC to be updated accordingly. ST with same resource problems as in Polaris, potential risk for S25. AI: UGe together with GFä to evaluate for SW features possible to be disabled in order to save SW resources. AI: CFr to show up gaps in SW / ST and point out measures how to increase ST1 resources for system test phase in Jan/Feb timeframe. Feedback needed by latest Dec. 13th to secure availability of needed consultants beginning next CJ. Tops & Flops: | CFr UGe GFä | 13.12.05 |

29.11.05

Peter Farrenkothen