## Agenda
Agenda PG 2 weekly F2F
Date: | 2005-12-20
Start: | 10:00
End: | 11:30
Nr. | Initiator | Project Name | Who | Planned [min] | Time need [min] | Time | Status
[6 empty] | 10:00 | Start
0 | HAs | Gerneral Topics + Delays | HAs | 0:10 | 0:15 | 10:15 | Done
1 | HAs | Swift | JKo | 0:10 | 0:30 | 10:45 | Done
2 | HAs | Swan Apoxi | RKe / RGa | 0:10 | 0:09 | 10:54 | Done
3 | HAs | Polaris | TNe / ALa | 0:10 | 0:13 | 11:07 | Done
4 | HAs | Philippe | CDa | 0:10 | 0:05 | 11:12 | Done
5 | HAs | Obsidean | TSt | 0:10 | 0:08 | 11:20 | Done
6 | HAs | Minos | MFe / UBa | 0:05 | 0:05 | 11:25 | Done
7 | HAs | Hydra | KRS | 0:05 | 0:07 | 11:32 | Done
8 | HAs | Hawk (ME85) | DRö | 0:10 | 0:05 | 11:37 | Done
9 | HAs | Condor | ABe | 0:05 | 0:00 | 11:37 | Cancelled
10 | HAs | Aries i-mode | DRö | 0:05 | 0:00 | 11:37 | Cancelled
|  | Sum |  | 1:30 | 1:37 | 11:37 | End
|  | available |  | 1:30 | 1:30
|  | Margin |  | 0:00 | 0:07
Meeting running out of time!
Note on H8: Farrenkothen: Choose Status

## Tops & Flops
TPM 2 weekly CW 51
Tops | Flops
Swift
B2 tape out on Wednesday 21.12.2005 | painting company and probably color supplier has to be changed between B2 and pilot for KHVartec metal parts current ST S25 testplan: some tests could be started earlier -> increases risk on S25 Statement from PM: Fastrack with DRM needed (not planned by PD at M1) No agreement with SD QM if Twigo4+ to be qualified, CR process started to estimate effort
Swan Apoxi
SWAN APOXI Team has declared M0 milestone on 09.12.05 / DS delay not accepted by OPC Resource situation within SW Customization/Variants under clarification with SWK
Polaris
Antenna detection is working now SAR/ EMI Measurements started at IMST Modification of Speaker Box ensured for B2.3 and ff Display Static Load Test passed | Fast B2.2 Antenna Samples not as specified (hand modification done) No calibrated Network Analyzer available at Ulm site -> FCC Approval endangered TMO/ Orange Operator Approval endangered due to missing operator requirements
Philippe
M1 declared by team and granted by OPC and PBR | Assembly (pressing of IMD foil) tool for MMI module in Leipzig not secured for B1 series: Quality risk
Obsidian
Everything is ready for running A1 prototype series before Christmas (2weeks ahead of schedule) | S0 will be delayed by 1-2 weeks due to missing clearance on final design details and No-ID concept
Minos
delivered to VKL: 43 k INTEL flash PF38F4460LVYTB1: no sourcing-issue visible AMD testing running ok so far; release expected this week | ALPS display reworked samples: drop-test shows significant failures on boards (not neccessarily the displays) Cushion: feedback from LPZ (quotation) pending 13k backlog, due to problems with the new production equipment in the packaging-lines and -organisation and number of workers in Config Center
Hydra
SW fix found for secure production with Spansion Flash from 9. Jan. 06. Fix needs to be available Wed. 20.12 at noon. CR will be raised so the resistor can be changed on the board. Test procedure: o ST and production to verify until Fri. 23.12. o SMS on exit test on both Flash types (Intel & AMD) until ECW01. S25 Full and AS Full declared 16.12.05. Next milestones: 25.01.06 S3 Basic = DS Basic 22.02.06 S3 Full = DS Full 14.12 Approval given by E-plus enabling us to deliver also BRD handel! | PL-T’s is out of communication loops. Who is the cock and what is agreed! Gives problems in daily work to secure timelines.
Hawk
Kick-off-Workshop in Aalborg successfully done | confidence level 60% to reach the desired quality of mechanics-parts at DS in June, due to short development time (same situation as in Condor)
Condor
Aries (i-mode)
SW Program Manager
SG2 Release 1
Wishlist of bugs to be fixed until 7.1. available. SW workaround for Spansion Flashes available in order to compensate Intel shortages | Even a lot of new informations are retrieved from fieldtest Network search problem still not solved. no approval from TMO/O2
SG2 Release Swift
for all known performance problems solutions defined. availability of resources in SW according plan ? Only 25 S25 blockers identified. | System test Resources busy in other projects, planned budget can not be spended.
Apoxi
offers from all vendors are available | money needed to be spend before 1st delivery at least factor 2 higher than granted budget.