| Mailing List: | Mailing List |
| --- | --- |
| Date: | 14.02.06 |
| Time: | 15:30-17:00 |
| Location: | KLf (BZ-Video / PL-T room) / Mch / Aal |
| Moderated By: | H. Asmussen Tel.: +49(2842)95-4370 |
| Minutes by: | P. Farrenkothen Tel.: +49(2842)95-4422 |
| Action Items: | Action Items |
| Tops & Flops: |  |
| Participants: | Alkämper, Thomas; TAl; Hartmann, Ralf; RHa. Asmussen, Holger; HAs; Hohenleitner, Markus; MHo. Barner, Ulrich; UBa; Karacelik, Hasan; HKa. Bauregger, Josef; JBa; Kern, Ralf; RKe. Betting, Andreas; ABe; Klebsch, Wolfgang; WKl. Bonde, Lars; LBo; Kroesen, Klaus; KKr. Byrdal, Ole; OBy; Kockmann, Jürgen; JKo. Christiansen, Keld; KCr; Lang, Andreas; ALa. Flierl, Brigitte; BFl; Neumann, Thomas; TNe. Friedl, Claus; CFr; Roehrig, Daniel; DRö. Dalmose, Claus; CDa; Rudolph, Tom; TRu. Faessler, Georg; GFä; Stokholm, Tony; TSt. Farrenkothen, Peter; PFa. Feldhoff, Markus; MFe; Hermanns, Thomas; THe. Geiger, Ulrich; UGe; Thonhauser, Hermann; HTh. Gallos, Reihard; RGa. |
| Meeting Reason | ### TPM2 weekly (CW 07) |
| Organisation | ### Dial In: +49 69 4035 9803 ### Code: 36111 # ### Support: using *0 (Serv.-Nr. 0180 2 0161 33) ### Mute phone: *6 |
| IP-ADDRESSES | ### For Windows Netmeeting ### PFa: 10.97.112.79 |
| Next Meetings | ### CW 08 Tue. 21.02. TPM2 weekly 15:30 – 17:00 (PL-T room KLF) ### CW 09 Tue. 28.02. TPM2 weekly 15:30 – 17:00 (PL-T room KLF) |
| Topic | Agenda Topic Title Owner Time |

| Topic No. | General | Who | When |
| --- | --- | --- | --- |
| 0 |  |  |  |
| Topic No. | Product Projects | Who | When |
| 1 | Diamond: SW feature definition critical due to unclear process and responsibilities. See T&F's for detail. |  | Info |
| 2 | Hawk: Evaluation of current time schedule shows that DS will not be possible on 11.08.06. Since Hawk is using a similar design as Condor, the mechanical time line (22 weeks between S0 and DS) should be feasible from HTh point of view. AI: CDa to deliver reasons for delays. Write down 5-10 lines in order to describe in detail what we didn't achieve for Hawk until now. | CDa | CW 08 |
| 3 | Hydra: See T&F's for detail. |  | Info |
| 4 | Jerry: no contribution |  | Info |
| 5 | Minos: no contribution |  | Info |
| 6 | Obsidian: M1 milestone now scheduled for 03.03.06, originally planned date was 20.01.06. Delay is mainly related to CPM and due to very late design fix. Correction: Delay is partly related to the late design fix and mainly to the very late supplier selection by PE. Some suppliers are not even settled yet. FM-Radio topic came in as a change request. Effort estimation for JSR implementation is about 120 man days. From HAs point of view this seems to be far away from benchmark. AI: TRu and UGe to clarify in terms of effort estimation and cost. Mechanical timeline (22 weeks between S0 and DS) has been agreed by HTh. Correction: 33 weeks (Obsidian is a category 2 product) AI: KKr / HTh to give feedback by latest end of CW 07. | TRu UGe KKr HTh | CW 08 17.02.06 |
| 7 | Philippe: Actually, France will not take the Philippe. There is of course a really good chance to sell the product as well in France when it is listed on the global O2-roadmap again. |  | Info |
| 8 | Polaris: Improvement on side keys only tested on a few samples which do no longer show the original behaviour, but side key problem not finally fixed yet. Offline discussion between TNe and HTh for both, problem on side keys and south catchers, will be take place on Thu, 16th. |  | Info |
| 9 | Swan Apoxi: Totally unclear situation in terms of time schedule. See T&F's for detail. |  | Info |
| 10 | Swift: S25 blocked due to significant increase of BOM (12% above M1 target). BYD approval for Battery expected by Sanyo B 04/06. |  | Info |
| 11 | Wireless Connectivity Program Management: BT: 21 Bugs found in BT implementation for Swift/Polaris, evaluation is ongoing. DVB-H: Fist product (Amethyst) intended to use the DVB-H technology most likely shifted to year 2008, but not finally decided yet. Fallback plan currently under evaluation. WLAN: Category Management is evaluating for two 150 Euro dual mode handsets based on Philips (done by Taiwanese company) and Vistron (in context to Acer). Pending request to re-place employee from T-Systems who is leaving the company by M 03/06. No feedback available until now. AI: HKa to contact Günter Seidel in order to clarify for substitute. |  | Info |
| 11 | SW Program Management: See T&F's for detail. |  | Info |

16.02.06

Peter Farrenkothen