| Mailing List: | Mailing List |
| --- | --- |
| Date: | 09.05.06 |
| Time: | 15:30-17:00 |
| Location: | KLf (BZ-Video / PL-T room) / Mch / Aal |
| Moderated By: | H. Asmussen Tel.: +49(2842)95-4370 |
| Minutes by: | P. Farrenkothen Tel.: +49(2842)95-4422 |
| Action Items: | Action Items |
| Tops & Flops: |  |
| Participants: | Alkämper, Thomas; TAl; Hänsel, Dirk; DHä. Asmussen, Holger; HAs; Hartmann, Ralf; RHa. Barner, Ulrich; UBa; Hohenleitner, Markus; MHo. Bauregger, Josef; JBa; Karacelik, Hasan; HKa. Betting, Andreas; ABe; Kern, Ralf; RKe. Bonde, Lars; LBo; Kroesen, Klaus; KKr. Byrdal, Ole; OBy; Kockmann, Jürgen; JKo. Christiansen, Keld; KCh; Lang, Andreas; ALa. Flierl, Brigitte; BFl; Neumann, Thomas; TNe. Friedl, Claus; CFr; Rasmussen, Ole; ORa. Dalmose, Claus; CDa; Roehrig, Daniel; DRö. Faessler, Georg; GFä; Stokholm, Tony; TSt. Farrenkothen, Peter; PFa; Zimmer, Alois; AZi. Feldhoff, Markus; MFe; Albrecht, Stefan; SAl. Geiger, Ulrich; UGe; Hülsmann, Andreas; AHü. Gallos, Reinhard; RGa. |
| Meeting Reason | ### TPM2 weekly (CW 19) |
| Organisation | ### Dial In: +49 69 4035 9803 ### Code: 136111 # ### Support: using *0 (Serv.-Nr. 0180 2 0161 33) ### Mute phone: *6 |
| IP-ADDRESSES | ### For Windows Netmeeting ### PFa: 10.97.112.79 |
| Next Meetings | CW 20 Tue. 16.05. TPM weekly 15:30 – 17:00 (PL-T room KLF) CW 21 Tue. 23.05. TPM weekly 15:30 – 17:00 (PL-T room KLF) |
| Topic | Agenda Topic Title Owner Time |

| Topic No. | General | Who | When |
| --- | --- | --- | --- |
| 0 |  |  |  |
| Topic No. | Product Projects | Who | When |
| 1 | Chameleon: Project was stopped due to cost reasons and negative impact on BoM. |  | Info |
| 2 | Diamond: Transparency in terms of SW missing from TPM point of view. Clear statement given from GFä that high level planning does exist. AI: GFä to contact PF project manager and PL SW to provide the TPM everything what is available. TPM need to be sufficiently informed. Release button: Currently no solution. Critical for S0. See T&F's for detail AI: AHü/KKr to double check. | GFä AHü KKr |  |
| 3 | Hawk: Actually 4 days delay due to problems at toolmaker for B1+. See T&F's for detail. |  | Info |
| 4 | Hydra: UBa will overtake responsibility for the project. See T&F's for detail. |  | Info |
| 5 | Jerry: Transfer to China in progress. Aal is only supporting the Beijing activities. |  | Info |
| 6 | Minos: No contribution. |  | Info |
| 7 | Obsidian: Qualification of 2nd source components not critical in terms of RU. Resources sufficient in order to perform the qualification. Actually, 850 MHz SW support delayed from Comneon. Contract only existing on developer level. Comneon delay is therefore more than a risk, but not a real delay in project. AI: TSt to contact SW Günter Seidl in order to escalate to IFX. | TSt | CW 19 |
| 8 | Philippe: S3 delayed due to failures in environmental test (butter test). KKr will directly clarify with PQA on Thursday this week. No blocking point for whole device. Actually two blocking points in SVN 37 (TTA & GCF), therefore QM will not accept this version. Remaining bugs incl. streaming issues to be corrected in SVN 38. |  | Info |
| 9 | Polaris: Route cause clarified regarding bad tactility of Navi Key. Actually, 100% of phones are handled by manual inspection at factory. |  | Info |
| 10 | Silverstone: DS planned on 23.05.06. Two add. MD resources allocated to the project. Actually, MD resources as available are sufficient for the current project phase. Check on M(alpha) feasibility is planned for end of CW 20. |  | Info |
| 11 | Swift: DS declared on 03.05.06 and already agreed by PBR today. All resources secured in order to perform Step II. SVN 8 approval not given because of some remaining bugs, but Orange approval completely independent from Step II and therefore actual possibility to speed up this step. |  | Info |
| 12 | Wireless Connectivity Program Management: No contribution. |  | Info |
| 13 | SW Program Management: No contribution. |  | Info |

12.05.06

Peter Farrenkothen