| Mailing List: | Mailing List |
| --- | --- |
| Date: | 06.12.05 |
| Time: | 10:00-11:30 |
| Location: | Aal / KLf / Mch |
| Moderated By: | H. Asmussen Tel.: +49(2842)95-4370 |
| Minutes by: | P. Farrenkothen Tel.: +49(2842)95-4422 |
| Action Items: | Action Items |
| Participants: | Alkämper, Thomas; TAl; Klebsch, Wolfgang; WKl. Asmussen, Holger; HAs; Kroesen, Klaus; KKr. Barner, Ulrich; UBa; Kockmann, Jürgen; JKo. Bauregger, Josef; JBa; Lang, Andreas; ALa. Betting, Andreas; ABe; Neumann, Thomas; TNe. Christiansen, Keld; KCr; Roehrig, Daniel; DRö. Friedl, Claus; CFr; Rudolph, Tom; TRu. Dalmose, Claus; CDa; Soerensen, Karsten Roer; KRS. Faessler, Georg; GFä; Stokholm, Tony; TSt. Farrenkothen, Peter; PFa. Feldhoff, Markus; MFe; Deputies:. Geiger, Ulrich; UGe; Albrecht Stefan; Sal. Karacelik, Hasan; HKa; Hohenleitner, Markus; MHo. Kern, Ralf; RKe; Seidel, Günter; MHo. |
| Meeting Reason | ### PG2 weekly (CW 49) |
| Organisation | ### Dial In: +49 69 4035 9803 ### Code: 94096 # ### Support: using *0 (Serv.-Nr. 0180 2 0161 33) ### Mute phone: *6 |
| Topic | Agenda Topic Title Owner Time |
| Next Meetings | ### CW 47 Tue 22.11. PG2 weekly 10:00 – 11:30 ### CW 48 Tue 29.11. PG2 weekly 10:00 – 11:30 ### CW 49 Tue 06.12. PG2 weekly 10:00 – 11:30 ### CW 50 Thu. 13.12. PG2 weekly 10:00 – 11:30 |

| Topic No. | General | Who | When |
| --- | --- | --- | --- |
| 0 |  |  |  |
| Topic No. | Product Projects | Who | When |
| 1 | Condor: SW R7* available, tested and released for production. S4 planned on January, 20th. Tops & Flops: |  | Info |
| 2 | Minos / Hydra: Very critical situation in terms of SW for both products. Delay on SW time schedule due to bugs as caused by change of EPS file. Bug was introduced from SW V6 to V7. AI: SAl to figure out the reason why EPS file (audio parameter settings) was changed. Tops & Flops: | SAl | CW 49 |
| 3 | ME 85: Outdoor variant of Philippe. All features as included in the package for Hydra/Minos are as well a part of ME 85 (see also Philippe). No new features will be accepted by HAs. AI: Find alias name for ME 85 and set up preconditions for planning in PMC. Inform involved functionalities before the start of planning round. In order to reduce overall R&D costs, 1.600 samples are agreed for test purposes. Tops & Flops: | DRö | CW 49 |
| 4 | Obsidian: See Tops & Flops for details. Tops & Flops: |  |  |
| 5 | Philippe: Add request from customer Orange to increase feature set by: * Enhanced backup * Group messaging distribution list * Fast track (taken back again) HAs will not accept any additional things which are not part of the package for Minos/Hydra. Only bug fixing issues and minor customer support will be accepted! Possible risk with new GCF version, as well for ME 85. AI: CFr to clarify for GCF delta to Philippe and ME 85 compared to Minos/Hydra full version as the jumping point. AI: UGe to check up for add. effort for 1) Enhanced backup and 2) Group messaging distribution list in terms of shift back from Swift to Minos. Tops & Flops: | CFr UGe | CW 50 CW 50 |
| 6 | Polaris: S25 signature from QM department still missing due to stability test issue for Nano I/O. Potential risk for break of connector in xyz-test. Modification have been started. MD is going to realize lower distance between Polaris housing and I/O-connector to increase stability against twist. B2.3 part tool delivery endangered, 2nd source (Nolato) is under evaluation. Actually no blocking points for ST. SW as well not on the critical path for S25. System Test Approval is planned on Jan, 2nd 2006. S25 planned by end of next week. Tops & Flops: |  | Info |
| 7 | Swan Apoxi: M0 declaration declined due to missing SW release schedule. Potential 3-4 weeks delay, e. g. due to SW. No add. delay due to design issues. No delta approval possible for TA, therefore effort increased by appr. 7 wd compared to first calculation of time schedule. Tops & Flops: |  | Info |
| 8 | Swift: MM SW w/o further delay, project schedule shows that S25 is back on track. Tops & Flops: |  | Info |

07.12.05

Peter Farrenkothen