| Mailing List: | Mailing List |
| --- | --- |
| Date: | 04.04.06 |
| Time: | 15:30-17:00 |
| Location: | KLf (BZ-Video / PL-T room) / Mch / Aal |
| Moderated By: | H. Asmussen Tel.: +49(2842)95-4370 |
| Minutes by: | P. Farrenkothen Tel.: +49(2842)95-4422 |
| Action Items: | Action Items |
| Tops & Flops: |  |
| Participants: | Alkämper, Thomas; TAl; Hänsel, Dirk; DHä. Asmussen, Holger; HAs; Hartmann, Ralf; RHa. Barner, Ulrich; UBa; Hohenleitner, Markus; MHo. Bauregger, Josef; JBa; Karacelik, Hasan; HKa. Betting, Andreas; ABe; Kern, Ralf; RKe. Bonde, Lars; LBo; Klebsch, Wolfgang; WKl. Byrdal, Ole; OBy; Kroesen, Klaus; KKr. Christiansen, Keld; KCh; Kockmann, Jürgen; JKo. Flierl, Brigitte; BFl; Lang, Andreas; ALa. Friedl, Claus; CFr; Neumann, Thomas; TNe. Dalmose, Claus; CDa; Rasmussen, Ole; ORa. Faessler, Georg; GFä; Roehrig, Daniel; DRö. Farrenkothen, Peter; PFa; Stokholm, Tony; TSt. Feldhoff, Markus; MFe; Zimmer, Alois; AZi. Geiger, Ulrich; UGe; Seidel, Guenter; GSe. Gallos, Reinhard; RGa. |
| Meeting Reason | ### TPM2 weekly (CW 14) |
| Organisation | ### Dial In: +49 69 4035 9803 ### Code: 36111 # ### Support: using *0 (Serv.-Nr. 0180 2 0161 33) ### Mute phone: *6 |
| IP-ADDRESSES | ### For Windows Netmeeting ### PFa: 10.97.112.79 |
| Next Meetings | CW 15 Tue. 11.04. TPM weekly 15:30 – 17:00 (PL-T room KLF) CW 16 Tue. 18.04. TPM weekly 15:30 – 17:00 (PL-T room KLF) |
| Topic | Agenda Topic Title Owner Time |

| Topic No. | General | Who | When |
| --- | --- | --- | --- |
| 0 | Roadmap: RM agreed on 03.04.06. Emergency meeting planned for CW 14. New wishes in terms of timeline and features will be announced by Mr. Gast. HW will deliver clear statements what is possible to do within requested timeline. |  | Info |
| Topic No. | Product Projects | Who | When |
| 1 | Chameleon: Slider mechanism does require 2nd source. New suppliers to be considered since SCM QM Mr. Amann does not accept KH Vatec as a 2nd source. Stable fallback solution has already been installed. The slider mechanic from KH Vatec consists of a magnesium solution where Nolato is the integrator and Dyncast the second supplier for the magnesium. A cancellation of KH Vatec would cause a delay of appr. 4 weeks. Fallback solution for Dynacast magnesium is a glass fiber-reinforced synthetic material from Nolato. |  | Info |
| 2 | Diamond: No contribution. |  | Info |
| 3 | Hawk: S0 declared on 10.03.06. Further decrease on LC volume (-30% since M1). General comment: Critical to present the project within an OPC since M1 milestone hasn't been declared, but this was strongly requested here. |  | Info |
| 4 | Hydra: SVN 31 aproval from ST. Ten open issues found in SW, but not violating the DS date. Video-streaming for Minos & Hydra is enabled and already communicated to the regions to take it as it is. There will be made no further improvements for this feature. |  | Info |
| 5 | Jerry: See T&F's for detail. |  | Info |
| 6 | Minos: No contribution. |  | Info |
| 7 | Obsidian: Great sales feedback from Latin America. Planning on LAM 850 variant is still ongoing. Actually resource problems on SW. |  | Info |
| 8 | Philippe: Project going according schedule, but significant drop in LC volume (about 50%) compared to M1 and also increase of BoM (about 10%). |  | Info |
| 9 | Polaris: See T&F's for details. |  | Info |
| 10 | Swift: Production start planned on 03.04.06. S3 not declared. Forecast on KH Vatec not possible to be done. Development of 2nd source for KH Vatec will take appr. 18 weeks following the secure way and 10 weeks for the risky way. A lot of vendors are considered but tools not possible to be done the same way as from KH Vatec. Redesign is necessary. |  | Info |
| 11 | Wireless Connectivity Program Management: See T&F's for details. |  | Info |
| 12 | SW Program Management: See T&F's for details. |  | Info |

11.04.06

Peter Farrenkothen