| Mailing List: | Mailing List |
| --- | --- |
| Date: | 31.01.06 |
| Time: | 14:00-15:30 |
| Location: | KLf (BZ-Video / PL-T room) / Mch / Aal |
| Moderated By: | H. Asmussen Tel.: +49(2842)95-4370 |
| Minutes by: | P. Farrenkothen Tel.: +49(2842)95-4422 |
| Action Items: | Action Items |
| Tops & Flops: |  |
| Participants: | Alkämper, Thomas; TAl; Karacelik, Hasan; HKa. Asmussen, Holger; HAs; Kern, Ralf; RKe. Barner, Ulrich; UBa; Kockmann, Jürgen; JKo. Betting, Andreas; ABe; Lang, Andreas; ALa. Bonde, Lars; LBo; Neumann, Thomas; TNe. Byrdal, Ole; OBy; Roehrig, Daniel; DRö. Christiansen, Keld; KCr; Rudolph, Tom; TRu. Dalmose, Claus; CDa; Stokholm, Tony; TSt. Farrenkothen, Peter; PFa. Feldhoff, Markus; MFe. Flierl, Brigitte; BFl. Gallos, Reinhard; RGa. Geiger, Ulrich; UGe. Hohenleitner, Markus; MHo. Houen, Ole; OHo. |
| Meeting Reason | ### TPM2 int. weekly (CW 05) |
| Organisation | ### Dial In: +49 69 4035 9803 ### Code: 36111 # ### Support: using *0 (Serv.-Nr. 0180 2 0161 33) ### Mute phone: *6 |
| IP-ADDRESSES | ### For Windows Netmeeting ### PFa: 10.97.112.79 |
| Next Meetings | ### CW 05 Tue 31.01. TPM2 int. weekly 14:00 – 15:30 (PL-T room KLF) ### CW 06 Tue 07.02. TPM2 int. weekly 14:00 – 15:30 (PL-T room KLF) CW 07 Tue 14.02. TPM2 int. weekly 14:00 – 15:30 (PL-T room KLF) |
| Topic | Agenda Topic Title Owner Time |

| Topic No. | General | Who | When |
| --- | --- | --- | --- |
| 1 | OPC: Decision taken that Planning Office KLF does provide the Primavera milestone reports relevant for all projects within the TPM2 on each Tuesday, 08:00 am (1 hour before the OPC) at latest. Report to be based on official 'Gallner' layout, as well including the QCT 6250 Onyx. Explanation needed from each TPM where project milestone planning does show a deviation greater than 10 days compared to the original planned dates. | TPM | Info |
| 2 | TPM set up: Alois Zimmer will join the TPM2 organisation as a new Technical Project Manager effective March, 1st. Suitable candidate (business engineer) was found to take over the role as a BO PL. New employee will be trained at Munich for the first 6 months and afterwards move from Munich to Kamp-Lintfort. |  | Info |
| Topic No. | Projects | Who | When |
| 5 | Swan Apoxi: Company Teleca is requesting for appr. 1.7 Mill. EUR if contract will be cancelled before M1. AI: RKe to ask TelCa to show up the reason for this request. What is the real amount of effort (hrs) which TelCa has spent for Swan Apoxi up to now? | RKe | CW 06 |
| Topic No. | Planning | Who | When |
| 6 | PMC: As formally agreed, all employees of TPM2 (TPM Head, Project Manager, Team Assistancy, PV Supporter) will be included in the cost centre planning. AI: PFa to remove Primavera AÜG from PMC data base. | PFa | Done |
| 6 | PMC: TPM are requested to have the PMC updated at every time. Project descriptions as well as 'Steckbriefe' need to be available in the tool. AI: UBa to update 'Steckbrief' for Diamond according to switch from SG3 to SG2. AI: PFa to clarify with CDa on DS date for Philippe. Is the date as mentioned in the PMC data base the real date or are there any adaptations necessary to be done, e. g. in terms of possible risks/delays? | UBa PFa / CDa | CW 06 CW 06 |
| 6 | Projects: Due to resource situation, there seems to be no possibility at the moment to do the Sandpiper, Emerald and Lapiz Lazuli at the same time at KLf. Statements UGe: Sandpiper will only be possible at 04/07 if ST resources are available and a complete project team will be established at KLF. Jade and Sandpiper should be one common release for SG3 based UMTS phone. The only show stopper at the moment is the Emerald. Strong request from HAs to do the Aquamarine (UMTS phone, DS 09/07) as well at KLF. AI: UGe to step into the Aquamarine (4 days period, 1 day / week) in order to clarify for show stoppers for this project. Check HW wall paper and align with colleagues from TPS. Find out unexpected problems in this project (e. g. in terms of Comneon). | UGe | ongoing |

02.02.06

Peter Farrenkothen