| Mailing List: | Mailing List |
| --- | --- |
| Date: | 22.11.05 |
| Time: | 10:00-11:30 |
| Location: | Aal / KLf / Mch |
| Moderated By: | H. Asmussen Tel.: +49(2842)95-4370 |
| Minutes by: | P. Farrenkothen Tel.: +49(2842)95-4422 |
| Action Items: | Action Items |
| Participants: | Alkämper, Thomas; TAl; Klebsch, Wolfgang; WKl. Asmussen, Holger; HAs; Kroesen, Klaus; KKr. Bauregger, Josef; JBa; Kockmann, Jürgen; JKo. Christiansen, Keld; KCr; Lang, Andreas; ALa. Friedl, Claus; CFr; Neumann, Thomas; TNe. Dalmose, Claus; CDa; Roehrig, Daniel; DRö. Faessler, Georg; GFä; Rudolph, Tom; TRu. Farrenkothen, Peter; PFa; Soerensen, Karsten Roer; KRS. Feldhoff, Markus; MFe; Stokholm, Tony; TSt. Geiger, Ulrich; UGe. Karacelik, Hasan; HKa. Kern, Ralf; RKe. |
| Meeting Reason | ### PG2 weekly (CW 47) |
| Organisation | ### Dial In: +49 69 4035 9803 ### Code: 94096 # ### Support: using *0 (Serv.-Nr. 0180 2 0161 33) ### Mute phone: *6 |
| Topic | Agenda Topic Title Owner Time |
| Next Meetings | ### CW 47 Tue 22.11. PG2 weekly 10:00 – 11:30 ### CW 48 Tue 29.11. PG2 weekly 10:00 – 11:30 |

| Topic No. | General | Who | When |
| --- | --- | --- | --- |
| 1 |  |  |  |
| Topic No. | Product Projects | Who | When |
| 2 | Condor: New problem with XFS in SVN21 (wrong time stamp will cause an error message in terms of complete SW update). No big consequences on service and production. Tops & Flops: |  | Info |
| 3 | Hydra: See Tops & Flops for details. Actually SW is in very bad shape. In order not to lose the main customers, decision was taken to build up appr. 100k of phones for O2 and TMO with an more or less unstable SW on Nov, 21st. Possible return rate of appr. 30% was fully accepted by the MM. Final SW will be delivered on Dec. 11th. Tops & Flops: |  |  |
| 4 | Obsidian: Budget targets have been reached. M0 milestone expected to be declared by end of CW 47. Thickness of device is appr. 15 mm by use of another battery (second source to Polaris battery from manufacturer Samsung – min. 735 mAh). Actually, standy time of appr. 400 hours, but talk time less than 5 hours. AI: Project description (Steckbrief) does not match to new requirements. PMC to be updated by PL-T. Tops & Flops: | TSt | CW 48 |
| 5 | Philippe: Correction (last protocol): MD department did fully confirm to meet the committed time schedule (DS 04/06). Target for DS in 05/06. S0 and M0 milestone have been declared. Request from Orange for add. side keys with risk on timeline. S0/M0 milestone were signed w/o this request! Product overview for Philippe does not show any side keys. From today point of view add. request will cause delay by appr. 4 weeks due to necessary changes in UI. AI: PFa to send out planning deltas to CDa and CFr. Tops & Flops: | PFa Done | CW 47 |
| 6 | Polaris: Declaration of whole PD team not available – only EMC/Antenna and LPD have declared. S25 declaration SW is still missing but expected by end of CW 47. Current problems: Fixation of screw domes not ensured (problems detected in drop test and climatic shock). Fallback solution not yet evaluated, impact on timeline. Environmental tests for I/O connector failed in xyz tests, drop tests and lifecycle. Potential risk on high return rate due to defect of I/O connector. Battery cover locking mechanism will not be accepted by customer. Tops & Flops: No seperate input from PL-T. |  |  |
| 7 | Swan Apoxi: Minimum decision for M0 is to have the contract signed with PSE Vienna. Add. SW support on Vienna site will be established (official announcement will follow in CW 48). Worksplit currently under discussion, but good progress so far. Huge increase of total royalties per sold phones (4,52 EUR). This is much more as for Minos. AI: RKe to check the status of negotiation and content of the contract. Send out draft of contract to TRu, UGe, HKa, JBa in order to perform a review and possible to complain about. AI: Clarify for Soft BOM (e. g. royalties) compared to other phones. What is today comparable amount of money to do the phone? AI: Update product description (Steckbrief) in terms of Display within PMC. AI: Update Planning for Swan Apox LAM 850. Tops & Flops: | RKe UGe |  |
| 8 | Swift: SD-card reader: No implementation to be done if there is a significant influence on time schedule for Swift! Actually, SW timeline is slipping uncontrolled because developer are working on Minos and Hydra. Tops & Flops: |  |  |

29.11.05

Peter Farrenkothen