## Slide 1
PD Product Classes
BMG PHE RD SPC – 28th Feb 2006

## Slide 2: Definition of PD project classes The project cost and the project duration are depending on the development effort. This is described by the PD classes
Source: Collected data from PL-P & PL-T
PD project class | I | II | III | IV
Description | New ID only, same PCB, same SW | New housing, form factor derived from technical predecessor, new PCB, slight SW modifications, reuse of available HW and SW components | New form factor (concept) SW and/or HW evolution | Lead product incl. platform and component cost  Everything new
Cost range (direct cost) | 2’8 (Condor) - 5’0 (Phillipe) | 4’0 (Finch) - 7’7 (Obsidian) | 15’8 (Onyx) - 20’(Kestrel) | >30’ (Swan, Koala…)
Typical cost | 3’0 | 6’5 | 17’5 | 40’
Typical project duration (M0 till DS) | 25 weeks (driven by mechanics) Condor: 21 weeks | 33 weeks (driven by mechanics) | 45 weeks (driven by SW) | 75 weeks (driven by SW)
Prerequisites for timeline | Design must be available and aligned with Mechanics, other features identical to technical predecessor. | Design must be available and aligned with Mechanics, all features must be defined in terms of “as already available for…” | SW feature list must be finalized and agreed. Architecture to be derived from predecessor projects/platform | SW feature list must be finalized and agreed (top level), Architecture must be available from TPS, key HW features/components are defined.
Risk | low | low-mid | mid | high
Notes: <number>
Themes are defining the „center of gravity“ of a phone‘s positioning, not it‘s exclusive functionality
-> e.g., an Imaging phone might also support Music / MP 3, even though it‘s not on the „Music“ Theme roadmap

## Slide 3: BACKUP: Description of work packages for each of the project classes - HW
PD project class | I | II | III | IV
HW BB | New ID only, PCB identical, keypad PCB may be adapted | New PCB layout, form factor derived from technical predecessor, re-use of various HW components/blocks from existing platform. Master schematic is subject to reuse. | Every form factor allowed. New HW components allowed, slight changes within HW architecture/master schematic possible. | Lead product, new HW platform. New master schematic, new HW components.
HW EMC/Ant/RF | Adoptions of Antenna to new housing, adoptions on SAR concept and re-testing of changed mechanical environment | Antenna and SAR concept can be re-used from technical predecessor. Slight adoptions can be made. Master schematic is subject to reuse. | Antenna and SAR concept completely new. Master schematic is subject to reuse, adaptations possible (e.g. new RF part). | Lead product. Antenna and SAR concept completely new. New HW platform. New master schematic, new HW components.
HW LPD | Only effort for providing Production Data. Lowest effort for changing fewest components on PCB. No new layout. | Master schematic can be re-used. Existing layout blocks can be re-used (e.g. RF section). New PCB(s) to be arranged. Production data to be provided. | Master schematic can be re-used and will be adapted. Existing layout blocks can be re-used, Some layout blocks new (e.g. adding AGPS). New PCB(s) to be arranged. Production data to be provided. | New master schematic to be provided. No re-use of predecessor platforms, all layout blocks new. New HW components to e taken in layout system. Production data to be provided.
HW SP | Only minor adoptions for audio parameter setting. | Adoptions for audio parameter setting. | Adoptions for audio parameter setting. Feature enhancement for existing platform possible. | Complete new setup due to fully changed HW basis.
Notes: <number>
Themes are defining the „center of gravity“ of a phone‘s positioning, not it‘s exclusive functionality
-> e.g., an Imaging phone might also support Music / MP 3, even though it‘s not on the „Music“ Theme roadmap

## Slide 4: BACKUP: Description of work packages for each of the project classes – SW, ST SW, ST HW
PD project class | I | II | III | IV
SW | Mappings only, HW recognition for new product, minor integration and testing effort. No new SW features. | New mappings, driver adaptations, low to mid effort for integration and testing. Minor changes on SW components. No new SW features. | New mappings, driver and UI adaptations, mid to high effort for integration, testing and debugging. Major changes on existing SW components. New SW features on existing platform. | New SW platform with new architecture. First integration and debugging efforts relatively high. New SW features. Effort strongly dependent on model (in-house, SW supplier) and on supplier contract.
ST SW | Almost zero effort due to using same SW from predecessor. | Minor efforts, new “composition” of existing SW features, only critical points to be tested. | Relatively high testing effort. on new SW features. Existing features to be tested not in full depth. | High testing effort. For new bought in SW platforms only validation should be done, but depending on contract with supplier. Every feature to be tested by supplier and/or ST SW.
ST HW | Only delta approval if possible. | Full approval, but almost no debugging phase on testers. Should run smoothly, no unexpected. | Full approval, but almost no debugging phase on testers. Should run smoothly, bug rate here is low to mid. | Full approval, also new tests might be integrated in effort planning. Also rest equipment to be changed for guaranteeing testability. Bug rate with first test might be very high. Also see SW.
Mechanics | Mid effort due to known mechanical interface to PCB. Depending on mechanical complexity 2-3 mechanical runs to be made. | Increased effort to class I due to adopted stack up concept with changed mechanical interface to PCB. Effort and timeline dependent on mechanical complexity. | Increased effort to class 1 due to new stack up concept with changed mechanical interface to PCB. Effort and timeline dependent on mechanical complexity. | Additional effort to class II and III due to new platform/generic mechanics to be done (shielding, connectors etc.) Also new “unexpected” form factor may increase effort.
Notes: <number>
Themes are defining the „center of gravity“ of a phone‘s positioning, not it‘s exclusive functionality
-> e.g., an Imaging phone might also support Music / MP 3, even though it‘s not on the „Music“ Theme roadmap