### Milestone M0 - GP APE

Project: 	Description:	Obsidian

Part Number: 	A5B00100204035

Project Manager (APE):	Robert Moelgaard

#### Enclosures:	Check List (incl. Deviation)

The M0 - GP APE is	 herewith declared

herewith restrictively declared

not declared

ICM GP MP P-APE		ICM GP MP P-APE-L

Date/Signature	 Date/Signature

Copies

PL-T:

Signatory:

###### Check list M0 - GP APE Milestone

yes	no	Responsible

for result

##### Process

- Alignment with SCM NPI about project status has been done
as per Kick-Off List)			APE

##### General, Time Schedule

- Project Manager (APE) has been named by Head of Department			APE

- APE Resource has been assigned by Head of Department: 
100% dedicated through to M1, on stand-by through to S4			APE

- Project Time Schedule is available (M0 – M3)			PL-T

- Life Cycle has been defined			PM

- Total Quantity over Life Cycle as well as per Fiscal Year 
has been defined			PM

- Maximum monthly capacity has been defined			PM

- List of Restrictions has been defined			APE

- List of Open Issues has been defined			APE

##### Supplier Selection

- Components/Concepts relevant for Single and Second Source and 
Second Solution have been defined and agreed with PD-Team 			APE

- Number of HW-Variants (PCB) has been defined
(e.g. RF solutions)			PL-T

- Suppliers for Second Solution have been defined			APE, PL-T

yes	no	Responsible

for result

##### Sourcing Strategy

- Global Procurement Supplier Strategy has been fulfilled 			APE

- Conformance with contents of M Declaration (time-line, quantities,
features, etc.) has been checked, deviations have been evaluated			APE

##### Prices

- Preliminary Bill of Material (BoM) has been calculated 
(based on product parts-list within Excel)			APE

- Target costs for material have been defined			PM

- BoM Target per Fiscal Year has been agreed with M0 Core Team			APE

- BoM Target per Fiscal Year can be achieved 
(cf. list of pre-requisites)			APE

- Cost review in Purchasing has been carried out			APE

##### Material Availability

- Kick Off List has been provided to SCM NPI			APE

- Availability of Standard Mechanical Components as defined by 
Mechanics (i.e. electro-mechanic components, re-use from 
predecessor products, catalogue components) is secured			APE

##### Procedure

- Product parts-list within Excel has been generated 
by Platform PL and Platform APE, 
based on freeze version of R&D feature list			PL-T

Schedule 1

# M0	S0	M1	S2	S3	S4	M3

25/11-05	23/12-05	20/1-06	14/4-06	28/7-06	11/10-06	3/11-06

Life Cycle:                                  11 Month

Quantity Scenario 2

Total number of units:

Number of units / year:	FY 05/06	FY06/07	FY   /

585K	3.410 Mio.

Maximum monthly quantity:	600K

Start of production:	CW 2906

Current plan (production):

Number of variants: 	1

1 Changed by CR No.:

2 Changed by CR No.:

Restrictions

| Problem | Actions | Owner | Date | Comments |
| --- | --- | --- | --- | --- |

Open Issues

| Problem | Actions | Owner | Date | Comments |
| --- | --- | --- | --- | --- |
| Battery situation unclear. No standard battery can be used. | Close follow up. | PE/HW/PM | Latest S0 | Battery has to be very thin to fit the design. |
| It’s the first time we will use PVD surface treatment. | Close follow up. | The team |  |  |