95 Obsidian
M1 Statement for Digital HW

References

References are external documents (papers, files, articles, and photocopies) which are mentioned to give further information about topics in the document. Remember to write the accurate path for the reference file.

Enclosures

Enclosures are external documents (papers, files, articles, and photocopies) which are an essential part of the document itself, but which cannot be put into the word format.

Revision Information

| Created: | Revision | Name | Comments |
| --- | --- | --- | --- |
| 01.12.2005 | 0.1 | Majbritt Christensen | Initial revision in PVCS |
| Modified |  |  |  |
| 11.01.2006 | 0.2 | Trine Lendrup Bech | Updated with Obsidian information |

Contents

1	Introduction	2

2	Results and open issues M1	2

3	Conclusion	4

# Introduction

This document is the basis for the M1 milestone declaration. Section 2 contains the M1 checklist according to the MEP 7.01 and section 3 gives a statement to the milestone.

# Results and open issues M1

| - A1 tape out completed | Ok. A1 TapeOut done 06-12-2005 |
| --- | --- |
| - Connectors, keypads and debug options for wing boards defined and agreed with LPD. Circuit schematics for wing board options available and reviewed. | Ok. No wingboards will be made for Obsidian. |
| - Test plan (Master Actions Plan) according to product functionality accessories available | Ok. ..\..\..\PD-Teams\Digital_Hardware\DesignDocuments\Test_Plan\Obsidian_Test_Plan.xls |
| - Product concept validation has taken place for all areas (electronics, mechanics, optics, acoustics etc.) incl. worst case considerations | Ok. Review must be done together with mechanical department: Display: Done Speaker: Done Camera: Done |
| - Production test requirements and needs for reference samples defined and agreed with production (PT) | Ok. Test technology workshop must be performed. Reference samples: (agreed with Andre Splawski) 2 pcs. display contrast reference phones 2 pcs. Microphone/speaker reference phones |
| - RTF development adaptor available for A1 target PCB | Ok. RFT Development adaptor is ready cw3. |
| - RTF SW from platform adapted to product | Ok. 1st release done 14-12-2005. |
| - Suppliers for all key components selected and agreed with Strategic Procurement | Agreed with Procurement Engineering Robert Mølgaard AAL. Memory: A5B00075545945 Intel Sibley, STM Display: A5B00075793414 Phillips / Epson. Camera: A5B00075433829 Samsung / Premier. Speaker: A5B00075798165 Hosiden / Bujeon. Microphone: A5B00075098861 Bujeon / Hosiden Vibra: A5B00075150950 Shicoh / Copal Power Management ASIC: A5B00075644155 Mozart Boost+ / Twigo4+boost Battery: A5B00075777338 Samsung / LG FM-Radio: A5B00075407207 Philips Main PCB: 2 sources MMI PCB: 2 sources RF solution: Bright 6PL (therefore only 1 PCB) |
| - Technical Terms of Delivery (TTD) of customized components and modules created and reviewed. Exceptions latest signed by S3 HW defined | Ok. Speaker module TTD will be signed latest at S3-HW. Review done by Frank Keussen. Display TTD will be signed latest at S3-HW. Review done by Franz-Walter Engelhart. Battery TTD will be signed latest at S3-HW. Review done by Battery FBT. OK |
| - Hardware FMEAs done; measures (e.g. RDP project) agreed with PQA | Ok. No FMEA´s done on dHW issues. |
| - Detailed Primavera project plan up to M3/S4 is available, showing dedicated resources by name and on department level for external consultants | Ok. |
| - Complete project plan reviewed and agreed | Ok. PLT master plan in Primavera was reviewed and agreed. |
| - Status of product relevant pre-/component developments reviewed. Risk analysis done and measures agreed, if targets are not reached | Mozart Boost +: Will be qualified on Obsidian. Twigo Boost +: Will be qualified on obsidian if STM deliver parts. Samsung Battery: Confirmed delivery of batteries for prototype runs. LG Battery: Confirmed delivery of batteries for prototype runs. Epson Display: Epson display development is set on hold. It is known by now that Epson will not be ready to deliver a qualified display module to ramp up. A lot of open issues need to be clarified before we resume the development: NRE cost, time schedule, display driver. Philips Display: Time schedule available. Hosiden Speaker module: Time schedule available Bujeon Speaker module: Will be started up when Hosiden is in B1+ status. |
| - Accessories to be fully supported by product are defined and agreed with Accessory Devices | Ok. Accessory Portfolio: ..\..\..\PD-Teams\Accessory\AD Portfolio OBSIDIAN 2006-01-26.ppt Car Kit Line Fit: SW can not confirm SW support and therefore dHW can not confirm support for Car Kit Line Fit. |
| - Product technical specification reviewed | Ok. Performance description review done. |
| - Time schedule for provision of devices for conformity assessment and certification agreed with System Test | Ok. (Agreed with Kim Ankeraa) dHW will prepare samples for Acoustic Type approval based on B1+. Approximately cw25 2006. In case of changes from B1+ to B2 acoustic Type approval will be done on B2. |
| - PSQA plan built up and provided to PQA | Similar to point 3 |
| - Charging concept fixed Product related Technical Terms of Delivery (TTD) are available (This checkpoint shall apply only for products which are not derived from platforms developed according to the new Platform Process V 2.0 and the corresponding platform checklist MRPlatD) | n/a |

# Conclusion

M1 can be declared with above open items.