95 Obsidian
M0 Statement for Digital and mixed signal HW

References

References are external documents (papers, files, articles, and photocopies) which are mentioned to give further information about topics in the document. Remember to write the accurate path for the reference file.

Enclosures

Enclosures are external documents (papers, files, articles, and photocopies) which are an essential part of the document itself, but which cannot be put into the word format.

Revision Information

| Created: | Revision | Name | Comments |
| --- | --- | --- | --- |
| 26.10.2005 | 0.1 | Trine Lendrup Bech | Initial revision in PVCS |
| Modified |  |  |  |
| 03.11.2005 | 0.2 | Trine Lendrup Bech | Updated with information for Obsidian |

Contents

1	Introduction	2

2	Results and open issues M0	2

3	Conclusion	4

# Introduction

This document is the basis for the M0 milestone declaration. Section 2 contains the M0 checklist according to the MEP 7.01 and section 3 gives a statement to the milestone.

# Results and open issues M0

| - Project leader HW (PL HW) / part project leader (PPL dHW) has been designated by the department head | Ok. PL HW is Ole Hoven, AAL PPL dHW is Trine Lendrup Bech, AAL |
| --- | --- |
| - Detailed Primavera project plan from M0 to M1 showing dedicated resources by name is available. | Ok. Detailed Primavera plan is aligned with PMC resources. |
| - Rough Primavera project plan from M1 to M3/S4 showing dedicated resources on department level is available | Ok. Detailed Primavera plan is aligned with PMC resources. |
| - Acoustic concept available and acoustic components defined. | Ok. Single speaker solution will be used. - Speaker module (use same core as Minos/Hydra) but different housing. New SAP number - Microphone (reuse Hydra, Minos) A5B00075098861 - Vibra (reuse Hera) A5B00075150950 |
| - Assembly concept for mechanical design dependent components or modules coordinated and agreed with MD, EA and RF (e.g. display, camera, acoustics, vibra, battery, card readers, IrDa, LED flash, connectors, etc.) | Not OK - Carina display (QVGA) with new FPC (panel used in Swift) new SAP number - 1.3MPixel Camera socket mounted (reuse Hydra, Minos) A5B00075288768 / A5B00075433829 - New Battery with 730 mAh (Samsung + TBD) new SAP number - T-flash card reader hinge type (reuse Swift) A5B00075496653 - SIM reader (reuse Cormorant) A5B00075371224 |
| - Product requirements as specified in the M0 document achievable with available technologies / know-how by the specified S3 HW deadline | Ok. M0 document version: ..\Obsidian_M0_Paper_DRAFT_V0.1_2005-11-16.ppt |
| - Product relevant pre-/component developments defined. Time schedules and deliveries aligned to product development schedule | Ok. Draft version of time schedule from suppliers are available: Speaker module from Hosiden New FPC on displays. |
| - Second solutions and requirements to multiple sources agreed with Strategic Procurement | Ok. - Display: 2 sources (Philips 50%, Epson 50%) - Speaker module: 2 sources (Hosiden, Bujeon) - 1.3MPixel Camera: 2 sources (Premier, Semco) - Power Management IC Mozart Boost+/Twigo4 Boost+: 2 sources (Dialog, STM) - Battery new 730mAh: 2 sources (Samsung, TBD) - Memory (Sibley): 1 source (Intel) |
| - Platform released for start of product integration available i.e. platform master schematics, porting guide etc. | Ok. |
| - First circuit schematics extracted from master schematics | Ok. |
| - Platform features/configurations supported by product agreed with PL SW | Ok. ..\..\..\PD-Teams\Software\05_ReqSpec\Spec-Organizer-25-nov-2005.xls |
| - Product related deviations from the platform defined and agreed with involved parties i.e. SW, MD etc. | Ok. ..\..\..\PD-Teams\Digital_Hardware\DesignDocuments\HW_Configuration\Obsidian_dHW_configuration.doc |
| - RF / base band interface defined (timing diagrams, description of the radio signals) (This checkpoint shall apply only for products which are not derived from platforms developed according to the new Platform Process V 2.0 and the corresponding platform checklist MRPlatD) | Ok. Aligned with RF Lind Møller Mortensen. |

| - Accessories interface defined / specified and agreed between AD, MD and HW (This checkpoint shall apply only for products which are not derived from platforms developed according to the new Platform Process V 2.0 and the corresponding platform checklist MRPlatD) | n/a |
| --- | --- |
| - Product related Technical Terms of Delivery (TTD) are available (This checkpoint shall apply only for products which are not derived from platforms developed according to the new Platform Process V 2.0 and the corresponding platform checklist MRPlatD) | n/a |
| - Hardware / Software interface and function description coordinated (hardware description and list of requirements on the software, port pin list are available) (This checkpoint shall apply only for products which are not derived from platforms developed according to the new Platform Process V 2.0 and the corresponding platform checklist MRPlatD) | n/a |

# Conclusion

M0 can be declared with above open items.