## Participants
Name | Initials | Department | M1
Claus Dalmose | CDN | TPM
Ole Byrdal | OBY | TPM R&D
Flemming B. Kristensen | FBA | dHW
Michael Brammer | MIB | RF
Arne B. Kristensen | ABK | EA
Poul Søndergaard | PCS | QM-HW
Erik K. Jensen | EKJ | MD
Jens Riedel | JRI | LCM1
Ralf Heesch | RHE | LCM1
Ralf Ehrlich | REH | LCM4
Reiner Römer | RRO | SD QM
Thomas Limbach | THL | SD QM
Flemming Kokholm | FKO | ST-MO
Randi Bak | RBA | LPD
Bjarne L. Thomsen | BLT | OS
Robert Mølgaard | RMS | PE
Mariann Svendsen | MSV | PE
Henning Boll | HEB | CC
Thorsten Lange | TLA | AD
Separate team for SW RMEA
Yong Xia | YXI | SW
Anders Nørgaard | ANO | QM-SW
Allan S. Jensen | ASJ | ST-SW
CDN; OBY; FBA; MIB; ABK; PCS; EKJ; JRI; RHE; REH; RRO; THL; FKO; -;YXI; ANO; ASJ; - ;RBA; BLT; RMS; MSV; HEB; TLA

## Risk List
Hawk PD team Risk List |  |  |  |  | Confidential
Identified by | Owner | Date | Risk Value | Description | Preventive Action | Evaluation (date) | Impact | Probability | Correctiv Actions | Status (M1) 2006.04.20 | Status (S2/S25) 2006.mm.dd | Status (PS) 2006.mm.dd | Status (DS) 2006.mm.dd
EKJ | EKJ | 2006-03-08 | 80 | The window for the flash light in the camera shutter might create light reflections that could interfere with the camera. | Start testing ASAP in order to do improvements in the construction if necessary. Use parts from soft tools | FP (CW14) | 2 | 40 |  | Test performed and first subjective impression is that the pictures taken are of acceptable quality
EKJ | EKJ | 2006-03-08 | 400 | The minimum 25% tactility might not be reached for the integrated keys TPE (soft keys). | Start tactility test with fast prototypes Only limited options for changes - time constraints | FP (CW14) | 5 | 80 |  | Tests will be performed in week 15/16 Subjective feeling on first prototypes is good!
EKJ | EKJ | 2006-03-08 | 160 | Bonding between materials in the 2k molding (TPE and PC-ABS) might be insufficient. | Start testing (incl. sweat test) on fast prototypes in order to do improvements in the construction if necessary | FP (CW14) | 8 | 20 |  | Tests will be performed in week 15/16 Special attention will be included in PSQA planning
FKO | FKO | 08.03.2006 | 80 | TA will be done on B1+ mechanics. The approval can be challenged if there are major differences between B1+ and B2 (on the mechanics) | Only do absolutely necessary changes with impact on TA | B1+ + 1CW | 8 | 10
ANO |  | 08.03.2006 | 40 | New processes for ASP is not completely "owned" by the departments yet. Cooperation instruction | Follow the ASP Cooperation Instruction | M1 | 2 | 20 |  | The cooperation instruction must be followed
RHE | CDN | 08.03.2006 | 400 | Pilot to be started with B2 parts. Risk of corrections afterwards. | Use learnings from Philippe Detailed analysis of flow in supply chain, production and testing. Identify focus areas with responsibilities. Possibilities for assembly in AAL vs. KLF for some testing Evaluate options for optimisation of time schedule | B1+ + 1CW | 5 | 80
CDN | CDN | 08.03.2006 | 400 | Risk of quality problems and / or delay of DS. Insufficient time between B1 and B2 to evaluate mech parts in depth and do corrections. The same goes for time between B2 and Pilot | Use learnings from Philippe Detailed analysis of flow in supply chain, production and testing. Identify focus areas with responsibilities. Possibilities for assembly in AAL vs. KLF for some testing Evaluate options for optimisation of time schedule | B1+ + 1CW | 5 | 80
REH | CDN | 08.03.2006 | 400 | Compressed time line (general + critical path: MD - QM - Production) | Use learnings from Philippe Detailed analysis of flow in supply chain, production and testing. Identify focus areas with responsibilities. Possibilities for assembly in AAL vs. KLF for some testing Evaluate options for optimisation of time schedule | B1+ + 1CW | 5 | 80
CDN |  | 08.03.2006 | 400 | Risk of quality and / or time. Mechanical corrective action from B2 run will be tested on pilot series. | Use learnings from Philippe Detailed analysis of flow in supply chain, production and testing. Identify focus areas with responsibilities. Possibilities for assembly in AAL vs. KLF for some testing Evaluate options for optimisation of time schedule | B1+ + 1CW | 5 | 80
YXI | YXI | 2006-03-30 |  | If JSR 184 certification is not finalised before 01.06 a newer version is required. Significant additional SW resources might be required. | - Clarify if possible to use Philippe devices - Use B1 (fast prototype) mechanics (available in - Check timing with B1+ devices | FP (CW14) | 8 | 40
FBA | EKJ | 2006-03-30 | 100 | The distribution of the light from the flash light might not be sufficient to reach a proper picture quality in darkness (FBT requirement) | Simulation and synthesis of light guide. Start testing ASAP with parts from soft tools | FP (CW14) | 2 | 50 |  | Simulations are performed and low efficiency has to be expected with the rotational Camera lid. In the team (CPM, TPM) it has been decided to prioritise the rotational function
PCS | EKJ | 2006-03-30 | 100 | Camera lid is a new concept in BenQ Mobile. No preproject has been run | Design FMEA Start testing on fast prototypes in order to do improvements in the construction if necessary | FP (CW14) | 2 | 50 |  | Design FMEA has been performed. Test on prototypes ongoing for optimisation. Decision for implementing spring element in the movement will be decided early in week 17
PCS | EKJ | 2006-03-30 | 100 | Potential lack of resources to measure and analyse MD parts | Get commitment for resources from LM | M1 | 2 | 50 |  | Additional ressources alocated part time to the project
Note on H4: 1 = low 2,3...9 10 = high
Note on I4: 10 = low 20,...90 100 = high

## AI and Info
What | Who | When

## data
Impact | Probability
1 | 10
2 | 20
3 | 30
4 | 40
5 | 50
6 | 60
7 | 70
8 | 80
9 | 90
10 | 100

## Philippe risk for inspiration
X95 Philippe PD team Risk List
Confidential
ID | Identified by | Owner | Date | Risk Value | Description | Preventive Action | Evaluation | Impact | Probability | Correctiv Actions | Status (S2/S25) 2006.03.07
1 | Ralf | CDN | 2005-11-10 | 400 | Risk of quality problems and / or delay of DS. Insufficient time between B1 and B2 to evaluate mech parts in depth and do corrections. The same goes for time between B2 and Pilot | Detailed analysis of flow in supply chain, production and testing. Identify focus areas with responsibilities. Possibilities for assembly in AAL vs. KLF for some testing Evaluate options for optimisation of time schedule | After B2 MD pre test 24.03.06 | 5 | 80 | Improved timeschedule | Achieved for B1 to B2. Project on track.
2 | LCH | CLA | 2005-11-10 | 400 | MD time line (general + critical path: new edge key concept) | Detailed analysis of flow in supply chain, production and testing. Identify focus areas with responsibilities. Possibilities for assembly in AAL vs. KLF for some testing Evaluate options for optimisation of time schedule | After B2 MD pre test 24.03.06 | 5 | 80 |  | Project on track.
3 | PCS | CLA | 2005-11-16 | 400 | Risk of quality and / or time. Mechanical corrective action from B2 run will be tested on pilot series. | Detailed analysis of flow in supply chain, production and testing. Identify focus areas with responsibilities. Possibilities for assembly in AAL vs. KLF for some testing Evaluate options for optimisation of time schedule | After B2 MD pre test 24.03.06 | 5 | 80 |  | Project on track.
4 | PCS | CLA | 2005-11-21 | 10 | Risk of failure in environmental test for nano I/O (experience from Finch and Polaris) | Use experience from Kestrel (passed) and evaluation results from Finch and Polaris) | Done | 1 | 10 |  | Passed test
5 | RBA | tbc | 2005-11-10 | 10 | MMI board has long delivery time (via Leipzig). Risk of delay of B1 | Close control of supplier | Done | 1 | 10 |  | B1 deliveries in time.
6 | KIA | KIA | 2005-11-10 | 10 | Assume start of TA (BABT, ?) on B1 (series in Jan 06 FOT mechanics). Then if major changes retest is necessary. Potential time line risk | Only do critical changes | Done | 1 | 10 |  | No changes with impact on TA is done from B1 to B2
7 | LCH | CLA | 2005-12-07 | 10 | Risk of dely of sidekeys, due to tactility problems | Partly reuse of minos concept. Design review to take place on Friday 09-12 | Done | 1 | 10 |  | Side key tactility okay
8 | BLT |  | 2005-11-10 | 10 | The is no confirmation of DS on 1st May in Primavera plan - delay? The planning as of today show significant deviation between target plan and detailed planning. | Planning must be updated and reviewed | Done | 1 | 10 | DS date defined at M1: 29.05.2006 Matched by Primavera planning
9 | BLT |  | 2005-11-10 | 100 | Rea Team has not planned in Primavera (operator test; manual; etc.) | Inform SPM (Claudia) to do it before M1 | M1 | 5 | 20
10 | LCH | Reiner CLA | 2005-11-10 | 100 | High glossy surface is easy to scratch. Used today on Hydra/Neo. Insufficient experience from supplier side. | Use supplier with experience of high Glossy paint. Nolato has been selcted and have good experience | B2 | 2 | 50 | 2006.03.07: SQA and MD to follow up with supplier to improves painting processes. Driver: Andrea Zutz | B1 failed in abbrasion test.
11 | FBA | FBA | 2005-11-10 | 10 | Performance on some electrical parameters are close to the limit in Minos and could get on the wrong side of the limit due to new mechanical design. | None - Fixed reuse from Minos | Done | 1 | 10 |  | Performance is okay
12 | FBA | FBA | 2005-11-10 | 10 | Support of Sibley memory flash could create unforseen problems | Support of Tyax & Spansion is keept (Minos) | Done | 1 | 10 |  | Supported in SW and HW. PCB updated for B2 due to missing connection.
13 | ABK | ABK | 2005-11-10 | 20 | If FCC TA is started on B1 but there is made a new PCB (label: B2) a complete new FCC approval must be done | Only do critical changes | 16.03.06 | 2 | 10 |  | Changes done from B1 to B2 but measurements could be done on B1 and then update by paperwork. Evaluation to be done of if it makes most sense to go with B1 or B2 (time vs. effort)
14 | ABK | ABK | 2005-11-10 | 20 | If FCC TA is started on B2 then the delivery of samples is time critical | Start on B1 | 16.03.06 | 2 | 10 |  | See ID 13 the above
15 | FBA | FBA | 2005-11-10 | 10 | Potential delay of B1 (critical path). Schedule for Vibra is critical for samples and approval. Usual lead time: 40 working days | Order the tooling by now. Done by the 16.11.05 Put pressure on supplier - involve procurement (MGM) Visit supplier | Done | 1 | 10 | Close track of suppliers and a delayed time schedule reduce the risk to low. Supplier has confirmed the deliveries. No Problem any more. | B1 finished and the vibrators were available.
16 | FBA | CDN | 2005-11-10 | 10 | Support of new accessories that are not tested in the platform (R-IDB / Polaris) | Ensure only use of accessories verified by Polaris | After CR evaluation | 1 | 10 | Still open, because the accessories are not agreed with PM. | Support of Music cable is to be clarified. CR to be issued by CPM Carkit linefit is out.
17 | ABK | ABK | 2005-11-10 | 10 | Camera self interference will not fulfill General Quality Requirements (Internal). Minos does not and improvements made are not expected to be sufficient | None. Changes should not be made in order to reduce risk on schedule | Done | 1 | 10 |  | Solved on B1
18 | RBA | LCH | 2005-11-10 | 10 | MMI board outline and placement of domes is not available yet. Time critical |  | Done | 1 | 10
19 | LCH ABK | ABK | 2005-11-10 | 10 | ESD protection changed in keypad area (from MMI module to keypad). Risk of incompliance of TA req. |  | Done | 1 | 10 |  | Solved on B2
20 | LCH | Ralf E. CLA | 2006-01-11 | 60 | MMI module can not be qualified before B2 - risk for dust protection | Improved layout compared with Hydra and Hera | B2 | 3 | 20 |  | Hajo Langer (Leipzig) confirmed deliveries for B2 on 03.03.06. PO for B2 issued on 06.03.06
21 | CLA | CLA | 2006-03-07 | 250 | Bad tactility of edge keys. Seen on B1 samples. | Improved for B2. Edge key construction has been changed | After B2 MD pre test 24.03.06 | 5 | 50
22 | CLA | CLA | 2006-03-07 | 250 | Failure in butter test. Front cover and upper case cracked several places on B1 | Improved on B2. Hooks in front cover changed. Radius increased where hooks connect to upper case. Added material around screw buses, radiuses increased and diameter of holes for screws increased. | After B2 MD pre test 24.03.06 | 5 | 50
23 | CLA | CLA | 2006-03-07 | 40 | MMC tray not locking as easy as intended | Opening in front cover to be increased. | After B2 MD pre test 24.03.06 (tbc) | 2 | 20
24 | PCS | Ralf E. | 2006-03-07 | 200 | Risk of damaged/bended springs on microphone and vibrator. Seen on B1 devices. Might not be detected in production in all cases. I.e. risk of market returns. | Assembly instruction must be improved. Driver: Ralf Ehrlich Improved transportation trays. Driver: Andreas Zutz | B2 | 10 | 20 |  | Seems that the bending of the springs were not due to transportation but due to the assembly in prototype shop (evaluated 300 lower case in trays)
25 | PCS | Reiner CLA | 2006-03-07 | 160 | Failure in abbrasion test of MMC tray | 2006.03.07: SQA and MD to follow up with supplier to improves painting processes. Driver: Andrea Zutz | B2 | 2 | 80 |  | R. Römer: New samples to be delivered in KLF CW10
26 | MIB | KIA YXI (MAL) | 2006-03-07 | 150 | Minos/Hydra was close to the limit of mandatory TA test case due to a timing advance problem. Although improvement was planned for future products this has not been implemented in the SW. Current status is that Philippe fails the test case. | Check if test setup is working properly (KIA) Check what was done on Polaris (KIA) SW improvement must be done (YXI). | 07.03.06 | 3 | 50
27 | ABK | ABK | 2006-03-07 | 150 | Devices with SAR painting done by hand is used for TA SAR measurement. SAR value might deviate for final products. |  |  | 3 | 50
28 | ABK | CLA | 2006-03-07 | 500 | Tool for SAR painting has a lead time of 10 weeks. Input for correction to the tool given 24.02.06. Risk for DS. Correct SAR painting is important for SAR performance and radiated antenna performance and maybe also ESD performance. | Investigate possibilities for improving the lead time. | 10.03.06 | 10 | 50
0
Note on I8: 1 = low 2,3...9 10 = high
Note on J8: 10 = low 20,...90 100 = high