## M1-PTM
M1: SCM TLM LCM 3 Milestone
Product: | Jerry
LCM 3 | Production Technology Management |  |  | Mr. Schulte | Date:
Sign:
LCM 3 | Production Technology Management |  |  | Dr. Hilker | Date:
Sign:
Project Manager
Herewith the M1 LCM 3 - Milestone is
declared
[6 empty] | declared with restrictions |  | X
is not declared
LCM | Lifecycle Management |  |  | Mr. Dörne | Date
|  |  |  | (or substitute) | Sign
Short summary / comments / restrictions:
make-or-buy decision for VF logo on battery cover still not fixed and has to be done before S15!
packaging concept not fixed
Distribution List:
PL | Project Manager |  |  | Mr. Bonde
CCQ | Product Quality |  |  | Mr. Bartel
Mr. Sondergaard
BA C |  |  |  | Gao Jie |  | (w/o attachments)
LCM1 |  |  |  | Mr. Riedel
Attachment:
General Information
Milestones
| Target | Reached
M0 | 2006-03-17 | 2006-02-27
S0 | 2006-03-17 | 2006-03-13
M1 | 2006-03-31
S15 | 2006-04-25
S2 | 2006-07-18
S25 | 2006-07-18
SD-S3 | 2006-08-17
S3 | 2006-08-17
PS | 2006-09-08
DS | 2006-09-22
SD-S4 | 2006-10-28
S4 | 2006-11-01
SD-M3 | tbd
M3 | 2006-12-01
Planned prototype runs
Tape out |  | Main | MMI | FPC
A1 |  | 2006-03-01 | no MMI
A1+ |  | 2006-03-31
B1 |  | 2006-05-05
B2 |  | 2006-06-21
Pilot |  | tbd
Prototype run |  | SMT | Assembly
A1 |  | 2006-03-09
A1+ |  | 2006-04-12
B1 |  | 2006-05-17 | 2006-05-26
B2 |  | 2006-07-03 | 2006-07-17
Volumes / Sites
Site | Peak Vol. | RU Date | Transfer Date
Klf | not planned
SSMC | 50k | 2006-09-08 | 2006-09-22
Man | not planned
Zal
Checklist acc. to MEP
[8 empty] | Yes | No
Project plan in Primavera on work-package level until M3 showing dedicated resources by name | [6 empty] | *1 |  | X
Milestone planning is in accordance with prototype runs, PTR, FRT, ramp up plan and ramp up volume | [7 empty] | X
Committed realization plan for new product technologies is available | [7 empty] | X
Committed realization plan for new production technologies is available | [7 empty] | X
Committed calculation for process times, special tooling cost and F1 hours are available | [7 empty] | X
Committed production process flow layout is available | [7 empty] | X
Commited production process quality targets are available | [7 empty] | X
Commited result out of production and test workshop is available | [7 empty] | X
Part declaration PT is available | [7 empty] | X
1) not all resources in BMS are available in Primavera; BMS has to finish planning until S15
Checklist internal
[8 empty] | Yes | No
Availability of resources LCM 3 are secured until SD-S4 | [7 empty] | X
List of restrictions, open points and action items have been defined | [7 empty] | X
Production targets in performance description included | [7 empty] | X
PT action items adressed to PD team are commited and listed in the PD team minutes | [7 empty] | X
Ramp up categorie is fixed and line set up time for new tasks is commited | [7 empty] | X
|  | ramp up categorie |  | days
SMT |  | 2 |  | 5
SMT2
Assembly
A2T
Config
Info / Attachments
New Product Technologies
Technology |  |  | Status |  |  | Owner
Sliding switch for keypad lock |  |  | MR sensor on PCB with corresponding magnet in mounting frame (lower case) |  |  | MD (Christian Primdahl Nielsen)
On-Off key |  |  | Button on the top of the phone, Alps Microswitch on the PCB |  |  | MD (Christian Primdahl Nielsen)
New Production Technologies
Technology |  |  | Status |  |  | Owner
A new router will be used for panel separating. Jerry panel design has to be checked if one panel design for both separating technologies is feasible or if two separate panel designs are necessary. |  |  | review of A1 layout done and send to MD A1+ layout in preparation and will be checked after tapeout |  |  | Huo QiZhong (PT1 BMS)
Process times / Special tooling cost / F1 hours
Attachment
Production process quality targets
Attachment
Production process flow
Attachment
Action Items
Action / Status |  |  |  | Owner |  | Date
1) LCM responsibility will be hand over from KLf to BMS after S15 |  |  |  | Info
2) A1 and A1+ will take place in KLf, effective from B1 only BMS is production site |  |  |  | Info
3) Production site is BMS |  |  |  | Info
4) Customer test will be qualified on the manual test system from Engmatec. If required the automatic system will be qualified in BMS later, based of the utilization/capacity of the production site. This qualification need approximately 6 week. CM has to be involved in this discussion |  |  |  | info
5) Production technology workshop with focus on assembly concept held - assembly concept is accepted by PT1 |  |  |  | info
6) Production technology workshop with focus on board-level-testing and device-level-testing held - concept is accepted by PT2 |  |  |  | info
7) Prototype quantities have to be provided by TPM |  |  |  | Bonde |  | DONE
8) Display rotation by 180 degree: tape on earpiece needed; in-house assembly because earpiece is also used in other projects F1 hours updated accordingly Tolerance calculation initiated: If possible avoid tape to save money |  |  |  | Christian P.Nielsen |  | S15
9) Round VF label has to be glued on battery cover -> Make-Or-Buy-Decision open TPMs have to check how many different variants are possible number of expected variants still open, final decision until S15 needed Make-Or-Buy decision has to be done afterwards considering costs and variance of BC Evaluate concept for production avoiding misalignemt |  |  |  | Bonde/Broeze/Song (TPMs) PT1/TPM PT1 |  | S15 S15 S15
Action Items
Action / Status |  |  |  | Owner |  | Date
10) RF shielding (same as in Aries) has an interior angle greater than 180 degree; find out about failure rate in Aries and evaluate production risks Check if prem can variant is available No prem can variant is available; because of the lifecycle volume of 450k we may accept fish can solution |  |  |  | Hilker / PT1 |  | DONE
11) Evaluate feasibility in Jerry to use a standard SW for production |  |  |  | YongQiang Yang (SW), JingWen Gong (LCM3), Arjen Broeze, Sara Song (TPM) |  | S3 (17.08.06)
12) Alps Microswitch for On/Off key: SIPLACE accuracy is not suitable to use the component with taps -> has to be considered for the component selection ALPS SKRE without taps will be used and is being created in SAP right now |  |  |  | Christian P. Nielsen |  | DONE
13) Primavera planning: not all resources in BMS are available in Primavera; BMS has to finish planning until S15 |  |  |  | JingWen Gong (LCM3) and PT |  | S15
14) Packaging concept still under discussion with VF, but filling concept according to production line concept (hint is placed in the M1 document) |  |  |  | TPM |  | S15